POST-LICENSE APPLICATION FILING TIMELINE :  Source: Hydropower reform coalition and FERC

| FERC REQUIREMENTS UNDER FPA or ILP | TIMELINE | DATES |
| --- | --- | --- |
| - License Application | 2 years before license expiration | August 31, 2012 |
| - Public Notice of Application | 14 days after receipt | September 13, 2012 |
| - FERC Decision on Outstanding Additional Information Requests (AIR) | 30 days after step 2. |  |
| - Satisfaction of AIR | 90 days after Step 3. |  |
| - FERC Notice of Acceptance and Ready for Environmental Analysis (REA) . Exelon also files for 401 Water Quality Certification from State | 60 days after Step 4 | Expected Dec 2012 or Jan 2013 State has 1 year to act on water quality certification. |
| - FERC Reply to Comments on REA | 45 days after Step 5. |  |
| - FERC issues non-draft EA or 7.a FERC issues draft EA or draft EIS | 120 days after step 6. 180 days after step 6. |  |
| - Comments due on non-draft EA 8.a. Comments due on draft EA or draft EIS, | 30-45 days after step 7 30-60 days after step 7 |  |
| - Modified Terms and Conditions | 60 days after Step 8. |  |
| - FERC issues Final EA or EIS | 90 days after Step 9. |  |
| - FERC issues final license |  | Expected September 2014. |