Healthy Watersheds Tracking Project

Intended Use of project outputs: raise public awareness, inform conservation community and local governments. Track progress towards GBP GIT 4 goal.

Timeline

May 11, 2012: GIT 4 Conference Call

  - ID ad hoc group members

  - Agree on project objectives and timeline

  - Brainstorm ideas for first workshop

May 30, 2012

- States need to provide readily available data to John Wolf (JWolf@chesapeakebay.net)

June 2012: Ad Hoc Group Workshop

- Objectives

  - Review state data

  - ID other available data and gaps in data

  - ID how to fill gaps in data

  - Initiate development of threat and protection criteria

  - ID staff and funding resources

  - Lay out schedule for the rest of the project

  - Develop project milestones, e.g. intermediate products

  - Potentially have expert presentations, e.g. TNC protection layers and criteria

End of 2012

- Output:

  - Maps that ID healthy watersheds, characterize threats and protection status

  - Targeting recommendations

Beyond 2012

- Close data gaps and update key metrics periodically