(V4 DRAFT) 2012 Enhance Partnering, Leadership and Management GIT Workplan (aka GIT 6)

Purpose of This Document:  To provide an overview  of planned  work  for the Goal Team’s 2012 goals and activities.

GIT Mission:  Continually improve the governance and management of the CBP Partnership

| Goals | Priority Work (objectives) | Metrics | Leader(s) |  | GIT 6 Workgroup |  | Resources in place/needed |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Enhance meeting management | Training for Coordinators and Staffers on managing effective meetings (Skillsoft ) | Positive feedback from trainees | Tim Wilke CRC |  | Managed at the GIT level |  | Skillsoft tool |
|  | Training on video conferencing following new equipment install including states | Positive feedback from trainees | Tim Wilke CRC |  | Managed at the GIT level |  |  |
| Provide superior information technology support | Enterprise Architecture improvements |  | Brian Burch EPA |  | Managed at the GIT level |  |  |
| Support GITs in implementing adaptive management through the decision framework | Decision framework implementation per respone to NSA report |  | Carl Hershner VIMS Nita Sylvester EPA | Decision Framework Implementation Wkgp. (DFIW) |  |
| Address governance issues | Alignment Process - stage 1, begin stage 2 GAO Report Follow-up Governance issues – develop options and record changes in Gov. Doc. |  | Carin Bisland EPA |  | Reinstate Action Team |  |  |
|  | GAO report follow-up |  | Carin Bisland EPA |  |  |  |  |
|  | Governance issues – develop options and record changes in Gov. Doc. |  | ? |  | Managed at the GIT level |  |  |
| Continue to develop ChesapeakeStat website to support decision-making | ChesapeakeStat - enhance content, structural, data flows |  | Doreen Vetter EPA Brent McCloskey MD DNR |  | Within DFIW - ChesapeakeStat Development Team |  |  |
| Develop and implement options for independent evaluation of the program to promote continual improvement | Develop options for the PSC regarding the independent evaluation function |  | ? |  | Ad-hoc Action Team |  |  |
| Coordinate budgets and optimize grants | Establish priorities for coordination of partner budgets and promote transparency to include FOD budget at a minimum |  | Kevin DeBell EPA | Managed at GIT level |  |