## Slide 1: AgWG Meeting Summary
September 20, 2012
Annapolis, MD

## Slide 2: AgWG
Welcome and Introductions
Minutes
  8/9/12 meeting minutes suggested changes from Bill A. at end of meeting
  Approved as amended w/ tracked changes- VA motion/USDA seconded
  Minutes will be revisited at next meeting
BMP Verification Process
  September 12th meeting w/ Verification SC update
  AgWG presentation by Frank and Mark
  Requested protocol completion by end of January 2013 by AgWG- accepted
  Summary of Tt investigative work previously presented to the AgWG in August

## Slide 3: AgWG
BMP Verification Process cont.
  NGO- comments where provided by the VSC and would like to see these addressed today
  Frank/Mark- the Tt presentation today should address the comments
Tt Draft Summary Report
  Ppt. presentation on draft summary report
  Literature- limited documentation on five categories of protocols being discussed
  NGO/USDA- questions on studies documenting abandoned and un-installed BMPs- Don noted the information from the studies (UT/IN)
  Frank- would recommend reading original study report- Don will provide an electronic copy to the AgWG
  NGO- Jay-Lark report available from VA? Tim S. will provide electronic copy to AgWG

## Slide 4: AgWG
Tt Draft Summary Report cont.
  Tim S.- will be releasing NutMan 4 that will reduce/eliminate duplication of NMP records
  DCR does 90% of NMP in state and seeking improved methods to review records
  NGO- recommend review of Bay state records instead of using non-Bay state records- information of verification available from state agencies now as presented by VA to VSC
  NRCS- would be good to review the articles but may have issues with the file review- differences possible between file records and C/S records
  NGO- difference between presence of BMPs and functions- BMPs may degrade over time- could revise header to modify the suggested message
  NGO- suggested modify header to say degrading over time

## Slide 5: AgWG
USDA- recommend that the workgroup consider the information gained from other studies
NGO- concerned that information being provided to the public may be misleading and that this data should be replaced by local state data
Frank- Tt is providing peer reviewed literature as requested by the AgWG and the results will be considered by the workgroup to determine if and how to use along with other suggested sources of information to make a workgroup determination
Don- interview summary
Don- summary points
NGO- NY AEM program could be a good source of implementation information and costs to add to the report

## Slide 6: AgWG
Tt Draft Summary Report cont.
  NGO- the report is well accomplished based on the guidance given- USDA has additional documentation on verification for its programs
  PA- concerned that AgWG is doing more than other sectors in developing the documentation report- may be putting the sector at a disadvantage to other sectors such as WWTPs which have good documentation
  USDA- take away message that USDA/State programs may not be adequate to verify BMPs- could have serious consequences to existing programs- interested in clarification
  USDA- interested in entities providing information- Tt interviewed mostly state and academic institutions, but also local agency and those providing direct services to farmers, did not include industry representation

## Slide 7: AgWG
Tt Draft Summary Report cont.
  Steve- the report provided summary comments but did not create consensus opinions amongst interviewees
  Steve- did not exclude comments and did not condemn current program efforts, but did note opportunities to make improvements in programs
  Don- the intent of the report was to look at all BMPs; e.g. C/S and non-C/S practices
  NRCS- interested in noting that IN and UT studies are based on 20 and 10 year implementation and evaluating current O&M

## Slide 8: AgWG
Verification- States
  VA- approved QAPP already in place, possible additional options in future discussions
  NGO- question on annual audit of VA data as an added value to data verification- VA could not describe in detail but yearly audit of implementation which does not support the literature information presented earlier
  WV- need to be careful in viewing other state verification (UT/IN) programs for Bay state programs, still interested in the value to
  MD- will continue to use the trained agency and third party process for verification; already using Conservation Tracker to provide data on approved and equivalent practices to bring to the workgroup for discussion in the future; developing and using remote sensing for targeted practices; see value in working directly with producers to make improvements where needed from assessments; will consider alternatives as identified by the workgroup that are cost effective

## Slide 9: AgWG
Verification- States
  NGO- question on if MD has an annual audit review of the practices? – information included in the Tt report and part of the state QAPP
  NGO- suggest looking at state QAPPs by states to support the discussions
  Frank- identified QAPP for VA, MD; WV does not have a QAPP for a voluntary practices; DE is working to develop a more comprehensive QAPP statement
  DE- really should review data quality and performance; ensuring BMP effectiveness values represented in the models is valuable as well
  PA- implementing multiple verification processes for data for C/S BMPs; non-CS BMPs are best approached in multiple approaches as well- survey works well for some but will need other processes for other BMPs; concerns on costs and resource needs for size of area in state; permitted operations can provide another approach for verification
  PA- concerns that other sector BMPs may not be creating the same level of effort and potentially lead to discounting; Tt report includes a chart of MD NMPs could be also provided by PA to add to the report as well as Nut. Trading
  PA- WWTP sector is using the agriculture sector information to identify Ag as a source of loads
  NY- submitted comments in June discussions which still stand; overall would recommend the AEM program information for NY for C/S and permitted operations; outreach to third party for non-regulated and non-C/S data which may take time to implement; QAPP process is in place but will need to seek additional details to comment; limited funding resources to address verification and new BMPs- see new BMPs as the priority over verification of older BMPs
  NY- little science available as per the Tt report so there is already error in place with protocols; the degree of model error is also present

## Slide 10: AgWG
Verification- States
  DE- concerned that report wording may be miss-leading and should be reviewed for finalization- effectiveness values and performance are concerns
  PA- many people will be focused on the ppt. vs. the report itself and it is important to ensure that ppt. is more fully explanative of the report in this regard
Verification- Non-State
  Bill A.- sees Tt report as good summary and appreciates the incorporation of information from NASS; working towards verification for 2013-14 Progress Reporting towards Milestones; Forestry looking at gain/loss of total acres; Stormwater focused on MS4 areas and do not have a plan to verify non-MS4 areas- over a 10 year period of verification; WWT non-significant facilities, CSOs and on-lot septic are not prepared to provide a verification plan

## Slide 11: AgWG
Verification- Non-State cont.
  Bill A.- scale issue discussions; PA concerned that AgWG is over-thinking the process; he has drafted a two-page verification protocol which is simpler and has been circulated to all six jurisdictions- feed back is what has been described today by the states
  Bill A.- concerns with the letters that have been sent out to the verification panel yesterday and not representative of the balanced representation requested- outside representation, unbalanced sector representation
  VA- alternative verification protocol has been reviewed by VA and sees benefits for consideration by other states- would recommend that committee consider
  Bill A.- can provide the document for the workgroup
  NGO- compliment Tt on the report; BMP function vs. presence is an important point that should be taken into consideration for any protocol; NMPs are a major BMP for states to achieve the WIP commitments- Tt report identified differences between structural, annual and management plans- recommend a focus of attention on NMPs verification

## Slide 12: AgWG
Verification- Non-States
  NGO- create a higher level of confidence with verification and consider crediting values associated with confidence levels; consider a time phased implementation for implementation; build upon existing verification protocols and improve them over time as per the NAS independent report recommendations
  NGO- riparian buffers are subject to bypass flows over time and create concentrated flow as identified by Tt report; one practice we need to assess as per the associated model effectiveness values
  NGO- purpose of verification is not just to verify what is not in place, but to explain, educate and outreach to the producers; should be included in the report as a goal; cost need to be included in the total BMP costs
  NGO- EPA has published guidance on standards that has been provided to the partner already- establishes goals for transparency and accountability
  Frank- would like to amend the agenda to finish the verification discussion at 1:00 PM

## Slide 13: AgWG
Goal Line 2025 Report
  Mark provided an overview of the draft conference report released by STAC for review
  NGO- suggested that the ARS Manure Summit report be referred to in the Manure Management section of the report- agreed
  PA- question on this report could be used by the states and EPA for the CBP- report would be presented as a guidance support document for enhancements to existing BMPs and programs but not as a template to direct EPA grant programs and thus state programs
  Mark- comments are requested by noon tomorrow to include into a response to STAC
Verification Process
  Bill A.- presented his alternative verification proposal
  CBC- concerns that document does not fully reflect the statements offered by Bill
  NGO- process questions- do not have enough time to review and provide comment on alternative proposal
  Frank- will collect concepts now and will provide condensed proposals for the October workgroup meeting

## Slide 14: AgWG
Verification Process
  USDA- will need the services of a full-time stats staff to implement the proposal across the watershed
  MD- there are elements of the alternative proposal but there are needs for an adaptive approach when difficulties arise; not comfortable with a credit discount process and do not see documentation for that approach
  VA- suggest to have time for people to review and comment on the alternative proposal
  Bill A.- do not see his proposal in conflict with the draft matrix
  NGO- where are we on completing the last two columns on the current concept- Frank noted that the Tt information will be considered
  MD- noted that other sector workgroups are also considering BMPs that fall on agricultural lands

## Slide 15: AgWG
Verification Process cont.
  NRCS- question on the process for finalizing the verification- Mark addressed the complex review and comment process of the partnership; the workgroup is not a decision body but recommends for the CBP partnership decision (PSC)
Mid-Point Assessment- States
  Mark provided overview of the process and request from the WQGIT
  DE- provided verbally their top priorities
  NY- priorities in spreadsheet
  PA- provided generalist priorities (model related)
  WV- priorities in spreadsheet
  MD- priorities in spreadsheet
    NGO- question on the reason for state vs. county yields
  VA- no comments provided
Mid-Point Assessment- Non-State
  NRCS -did not provide recommendations but are supporting the state partners; internal discussions on the model assumptions and would be interested in holding discussions on available USDA tools for EPA use; willing to offer expertise on process based assumptions but not offering to provide data

## Slide 16: AgWG
Mid-Point Assessment- Non-State
  USDA- the use of multiple models at a variation of scale that has been proposed by others is similar to what NRCS is suggesting
  DE- the NRCS assumptions is in keeping with DE’s concerns on assumptions due to aging data- extremely important for ag
  Bill A.- lists from states are largely based on SB modeling assumptions; USDA recommended a partnership discussion on SB and EPA has recently released documentation; concerns with assumptions and background data; system review of SB needed
  CBC- defending the model results is a key element for legislative work and there is a need to be confident of the assumptions and resulting information; need to make processes and practices transparent and closer related to on-the-ground activities vs. interpretation by modelers; model uncertainly needs to be identified- how accurate are the models; can not improve them without knowing uncertainties
  USDA- verification may be one way to move away from modeling to influence policy decisions
  CBC- the model is used to look forward for policy decisions which verification may not assist

## Slide 17: AgWG
Mid-Point Assessment
  PA- concerns that the verification discussion may only be used to support the models vs. replace them
  MD- concerns for the ES that the groundwater contribution may change the future load numbers
  Bill A.- manure transport information in PA and other examples could assist with the industry involvement with improved baseline data
  NGO- concerns with assumptions of nutrient losses from poultry operations/litter; N-based NMP representation vs. P-Based in the models
  NGO- would suggest EPA reconsider protected farmland is reflected in the models; EPA-5 region has developed a calculator tool for conserved land and its benefits to water quality; farm land is more than just cropland- need to not discount other features such as forests and wetlands

## Slide 18: AgWG
Mid-Point Assessment
  Frank suggested that the recommendations of the workgroup be developed into a comprehensive document and provided to the members for comment; agreed
  Bill A.- recommend that a request for a day-long discussion on SB be sent to EPA on behalf of the workgroup; seconded by USDA
  CBC- what are the outcomes?
  Bill A.- discussion needed to support the discussions on the mid-point assessments
  USDA- feel that there is enough concerns on the models that EPA will be more open for modifications
  MD- suggests that develop broad headers with supporting bullet points; most diverse land uses of any sector
  SB Workshop discussion approved; Frank assigned committee to formulate request and will post for comments