2011/12 Year end report

Production Schedule

| DATE | ACTION/ ACTIVITY | DESCRIPTION | WHO RESPONSIBLE | NOTES |
| --- | --- | --- | --- | --- |
| Now-Nov 1 |  | RFP for designer out | Margaret |  |
| Nov 1-16 |  | Development of 1st draft | Margaret |  |
| NOV 21 | DEADLINE | GIT DATA FINAL | GIT Coord. |  |
| Nov 21-26 |  | Finalizing 1st draft | Margaret | Short week - Thanksgiving |
| Nov 26-29 | Review | CBP Leadership & GIT review (incl GIT chairs) | Nick, Jim, Carin, Rich | GITs receive only their section for review at this pt. |
| Nov 29-Dec 4 | Editing/Review |  | Margaret (& Nita) |  |
| DEC 4 | DEADLINE | 1ST DRAFT TO MB | Margaret |  |
|  |  | CBP Comm to assemble all images | Margaret, Catherine & Steve |  |
| DEC 10 | DEADLINE | MB/SIG REP EDITS DUE | MB |  |
| Dec 11-12 | Editing | 1st draft changes | Margaret |  |
| DEC 12 | DEADLINE | ALL TXT & IMAGES TO DESIGR | Margaret |  |
| Dec 19 | Deadline | 1st Design draft back fr design | Designer |  |
| Dec 20-28 | Editing/Review |  | CBP Comm/Margaret – w/ CBP Leadership & Nita | Short week - Holidays |
| Jan 2 | Deadline | 2nd Draft sent to designer | Margaret |  |
| Jan 7 | Deadline | 2nd Draft from designer |  |  |
| Jan 9 | Review / Deadline | Final edits approved | Margaret, Leadership |  |
| JAN 10 |  | FINAL TO PRINTER | Designer |  |
| Jan 14 | Print proof | Blueline for approval | Margaret |  |
| Jan 14-21 | Printing |  | Printer |  |
| JAN 21 |  | FINAL REPORT COMPLETE |  |  |
| Jan 23 (Wed) | RELEASE | News Release/Event | Margaret |  |

All deadlines are for Close of Business (COB) on the dates indicated – which means 4p.m.