## Sheet1
Status of BMP Panels Currently Underway
Sector | Panel Chair & Coordinator | BMP | Description | BMP Status (new/interim/placeholder) | Month/Year Panel Launched | Panel Status (e.g. developing recommendations) | Expected Date of Draft Report Submission to Sector Workgroup | Anticipated next steps (e.g. date of next call)
Agriculture | Chair - Jim Glancey; Coordinator - Mark Dubin | Poultry Litter Data | Review of existing poultry litter nutrient and volumetric model data and analysis process. | Model Data | 2011-05-09 | Panel membership formed. Panel developing poultry litter nutrient and volumetric database for historic and present poultry litter production. | Full panel recommendations to AgWG by Jul-13. | February conference call
Agriculture | Chair - Frank Coale; Coordinator - Mark Dubin | Agricultural Nutrient Mgnt., Precision Agriculture, and Enhanced Nutrient Mgnt. BMPs | Multiple Nutrient Management BMPs are being considered including NMP, Precision Ag, and Enhanced NM. | BMPs being considered include three existing and one approved interim NM BMP | 2011-12-08 | Panel membership and panel subgroups formed. Finalized backgroup report approved. Panel reviewed and commented on interim NM BMP proposal. Due to workload, panel chairmanship structure being revised and confirmed. | Phase 5.3.2 modeling suite panel short-term recommendations to AgWG by Jul-13. Full panel recommendations by late 2013/2014. | February conference call
Agriculture | Chair - Jack Meisinger; Coordinator - Mark Dubin | Traditional and Commodity Cover Crop BMPs. | Review of existing traditional cover crops and commodity cover crop BMPs. | Existing BMP | 2012-02-23 | Panel membership and panel subgroups formed. Draft background expert interview draft completed and under review. USDA modeling support being established. | Full panel recommendations to AgWG by Dec-13. | February conference call to establish Scenario Growth Regions to specific Panel Experts and to discuss how to proceed with commodity cover crops i.e. as a Nutrient Timing BMP or a Reduction Efficiency.
Agriculture | Chair - Wade Thomason; Coordinator - Mark Dubin | Conservation Tillage, and CNT BMPs. | Review of existing Conservation Tillage and Continuous No-Till BMPs. | Existing BMP | 2012-02-23 | Panel membership and panel subgroups formed. Draft background expert interview draft completed and under review. USDA modeling support being established. | Full panel recommendations to AgWG by Sep-13. | February conference call
Agriculture/Urban | Chair - TBD; Coordinator - Sarah Lane, UMCES; Matt Johnston, UMD | Algal Turf Scrubbers | Algal Turf Scrubbers are systems that reduce nutrient concentrations in surface waters by enhancing uptake of nutrients by the controlled growth and harvest of algae. | New BMP | 2013-02-01 | Watershed Technical Workgroup is finalizing panel charge and panelists. Panel should begin meeting in March, 2013 | 2013-07-01 | Watershed Technical Workgroup is finalizing panel charge and panelists. Panel should begin meeting March 2013
Forestry | Coordinator - Sally Claggett | Urban Tree Planting/Expanded Tree Canopy | Planting trees in "urban pervious" acreage | Existing BMP | 2012-03-01 | Developing Recommendations | 2013-03-01 | Next call not set
Forestry | Coordinator - Sally Claggett | Riparian Forest Buffers | Grass and forest buffers along streams | Existing BMP | 2012-03-01 | Developing Recommendations | 2013-03-01 | Next call 2/13
Urban | Coordinator - Tom Schueler | Urban Stream Restoration | Includes any Regenerative Stormwater Conveyance, Natural Channel Design, Legacy Sediment Removal or other restoration projects meeting the qualifying conditions of stream functional improvements and environmental limitations. | Existing BMP | 2011-12-01 | Final draft of expert report presented on December 17 to joint meeting of USWG, WTWG, Ag Work Group and Stream Committee of Habitat GIT. Comment period extended to January 30, at which time it will undergo official CBP approval process. | 2013-02-19 | USWG Approval
Urban | Coordinator - Tom Schueler | Urban Nutrient Management | Identifying how nitrogen, phosphorus, and potassium are to be annually managed for expected turf and landscape plants and for the protection of water quality. | Existing BMP | 2011-12-01 | Final draft of expert report presented on December 17 to joint meeting of USWG, WTWG, Ag Work Group and Stream Committee of Habitat GIT. Comment period extended to January 30, at which time it will undergo official CBP approval process. | 2013-02-19 | USWG Approval
Urban | Coordinator - Tom Schueler; Facilitator - Jeremy Hanson | Enhanced Erosion and Sediment Controls | Erosion and Sediment Control (ESC) is a combination of erosion prevention and sediment control practices that are progressively applied and maintained during the stages of construction. Erosion controls reduce the amount of sediment lost during construction and prevent that sediment from entering runoff, while sediment controls capture sediment from runoff before it leaves the construction site. | Existing BMP | 2012-07-01 | Panel has held four meetings, and has largely completed the research review phase. | Summer 2013 | Early March 2013
Urban | Coordinator - Tom Schueler; Facilitator - Cecilia Lane | Illicit Discharge Elimination | Illicit discharge detection and elimination programs are designed to prevent contamination of ground and surface waters by monitoring, inspection, and removal of illegal non-storm water discharges. | New BMP | 2012-07-01 | Panel has held four meetings, and has largely completed the research review phase. | Summer 2013 | TBD
Urban | Coordinator - Sadie Drescher; Chair - TBD | Urban Shoreline Erosion Control Practice | Urban shoreline erosion control practices protect shoreline from excessive wave action by creating a marsh or an offshore structure such as a sill, breakwater or sand containment structure. | New BMP | 2012-11-27 | 1st meeting 1/28/13 | Aug-13 - Dec-13 | Around 2/25/2013
Urban | Coordinator - Neely Law, PhD.; Chair - TBD | Urban Filter Strip/Stream Buffer Upgrade Expert Panel | Urban filter strips, also referred to as vegetated filter strips or grass filter strips, are designed to slow runoff velocities and treat sheetflow from adjacent impervious and pervious areas. | New BMP | 2012-11-27 | Set-up meeting | 2013-12-01 | 1st meeting 2/19/13
Wastewater | Mark Sievers & Ning Zhou | Advanced Onsite Systems | The main charge for the panel is to review available science on the pollutant removal performance treatment practices that can be used to derive nutrient removal rates for individual practices. | New BMP | 2012-01-01 | Developing recommendations | 2013-05-01 | Early February 2013