Report to Congress

Timeline

Jun 13		Present Comm Strategy and draft RTC at Management Board meeting

Jun 20 		Feedback from MB on both due

Jun 27		Present Comm Strategy and draft RTC at Principals’ Staff Committee meeting

Jul 11		Present updated RTC to Management Board

Jul 25		MB Fatal flaw review due on RTC

Aug 8		Present final RTC to MB

Aug 15		Initiate HQ review of final RTC

Sep TBD		Present final RTC to PSC

Oct TBD		Publish RTC in conjunction with new agreement