## Acronym Guide
Acronym Guide (for all workplans)
AACC – Anne Arundel Community College
ACFHP - Atlantic Coast Fish Habitat Partnership
ACJV – Atlantic Coast Joint Venture
AgNPS – AGricultural Non-Point Source Pollution Model
Appalachian LCC - Appalachian Landscape Conservation Cooperative
ASTSWMO – Association of State and Territorial Solid Waste Management Officials
BayFAST/CAST/MAST/VAST – Federal Assessment Scenario Tool/Chesapeake AST/Maryland AST/Virginia AST
BDJV – Black Duck Joint Venture
BKT – Brook trout
BMP – Best Management Practice
CAC – CBP Citizens’ Advisory Committee
CAFO – Concentrated Animal Feeding Operation
CB – Chesapeake Bay
CBC – Chesapeake Bay Commission
CBF – Chesapeake Bay Foundation
CBIBS – Chesapeake Bay Interpretive Buoy System
CBIG – Chesapeake Bay Implementation Grants
CBP – Chesapeake Bay Program
CBPO – Chesapeake Bay Program Office
CBRAP – Chesapeake Bay Regulatory and Accountability Program grants
CBSAC – Chesapeake Bay Stock Assessment Committee
CBSSC – Chesapeake Bay Sentinel Site Cooperative
CBT – Chesapeake Bay Trust
CCWC – Choose Clean Water Coalition
CEAP – Conservation Effects Assessment Project
Chessie BIBI – Chesapeake Bay Basin-wide Index of Biotic Integrity
CNMP – Comprehensive Nutrient Management Plan
CNU – Christopher Newport University
CRC – Chesapeake Research Consortium
CREP – Conservation Reserve Enhancement Program
CSN – Chesapeake Stormwater Network
CWA – Clean Water Act
DAT – CBP Diversity Action Team
DC – District of Columbia
DCNR – Pennsylvania Department of Conservation and Natural Resources
DE – Delaware
DEP – Department of Environment
DE DNREC – Delaware Department of Natural Resources and Environmental Control
DNR –Department of Natural Resources
DoD – Department of Defense
DOEE – Dist. Of Columbia Department of Energy and Environment
DOF – Department of Forestry
DOT – Department of Transportation
DST – Decision support tool
DU – Ducks Unlimited
EC – Chesapeake Executive Council
EJ SCREEN – Environmental Justice Screening and Mapping Tool
EO Strategy – Executive Order 13508 Strategy for Protecting and Restoring the Chesapeake Bay Watershed
EJ – Environmental Justice
EL – Environmental Learning
ELCSS – Environmental Literacy Challenge for Systemic Sustainability
ERP – Elizabeth River Partnership
EPA – Environmental Protection Agency
Ex Comm - Executive Committee of the Sustainable Fisheries GIT
FERC – Federal Energy Regulatory Commission
FLC - Federal leadership Committee
FOD – Chesapeake Bay Program Federal Office Directors
FTE – full time employee
FWG – Forest Work Group
FWS – Fish and Wildlife Service
GIS – Geographic Information System
GIT – CBP Goal Implementation Teams
GMU – George Mason University
GSA – General Services Administration
HBCUs – historically black colleges and universities
HSCD – EPA Hazardous Site Cleanup Division
HWGIT – Healthy Watershed Work Group
ICPRB – Interstate Commission on the Potomac River Basin
IPC – Interfaith Partners for the Chesapeake
LCC – Landscape Conservation Cooperatives
LGAC – CBP Local Government Advisory Committee
LL – Local Leadership
LU – Land Use
LUWG – Land Use Work Group
MATOS - Mid-Atlantic Telemetry Observing System
MB – CBP’s Management Board
MD - Maryland
MDE – Maryland Department of Environment
MDSG – Maryland Sea Grant
MOU – Memorandum of Understanding
MSP – Math Science Partnership
MS4 – Municipal Separate Storm Sewer System
MWCOG – Metropolitan Washington Council on Governments
MWEEs – Meaningful Watershed Educational Experiences
MWS – Master Watershed Stewards
NAAQS – National Ambient Air Quality Standards
NALCC - North Atlantic Landscape Conservation Cooperative
NATA – National Air Toxics Assessment
NCBO – NOAA Chesapeake Bay Office
NGO – Non-government organization
NEIEN – National Environmental Information Exchange Network
NERR – Chesapeake Bay National Estuarine Research Reserve
NFWF – National Fish and Wildlife Foundation
NOAA – National Oceanic and Atmospheric Administration
NP – National Parks
NPDES – National Pollutant Discharge Elimination System
NRCS – Natural Resources Conservation Service
NPS – National Park Service
NYS DEC – New York State Department of Environmental Control
ODU – Old Dominion University
ORES – Oyster Reef Ecosystem Services
ORP – Oyster Recovery Partnership
OSSE – Office of the State Superintendent of Education
PA – Pennsylvania
PA DEP – Pennsylvania Department of Environmental Protection
PCB – polychlorinated biphenyl
PMP -- Pollution Minimization Plan
PRFC – Potomac River Fisheries Commission
PSC – CBP’s Principles' Staff Committee
QA – quality assurance
RFB – Riparian Forest Buffer
RMNs - Regional Monitoring Networks
SAV – Submerged Aquatic Vegetation
SERC - Smithsonian Environmental Research Center
SHWG – Stream Health Work Group
SRBC -- Susquehanna River Basin Commission
STAC – CBP Scientific and Technical Advisory Committee
STAR – CBP Scientific and Technical Assessment Research team
TCW – Toxics Contaminants Workgroup
TEA - Tidewater Ecosystem Assessment Division of MD DNR
TMDL – Total Maximum Daily Load
TNC – The Nature Conservancy
TSCA – Toxic Substance Control Act
UMBC – University of Maryland Baltimore County
UMCES – University of Maryland Center for Environmental Science
UMCES-CBL – University of Maryland Center for Environmental Science-Chesapeake Biological Lab
UMD – University of Maryland
USACE – U.S. Army Corps of Engineers
USDA – U.S. Department of Agriculture
USFWS – U.S. Fish and Wildlife Service
USFS – U.S. Forest Service
USGS – U.S. Geological Survey
UVA – University of Virginia
VA – Virginia
VCU – Virginia Commonwealth University
VA CZM – Virginia Coastal Zone Management
VBOE – Virginia Board of Education
VDGIF – Virginia Department of Game and Inland Fisheries
VIMS – Virginia Institute of Marine Science
Virginia DEQ – Virginia Department of Environmental Quality
VMRC – Virginia Marine Resources Commission
WG – work group
WIP – Watershed Implementation Plan
WQN - Water Quality Network

## Communications and Outreach
Outcome: Diversity
Goal: Citizen Stewardship
Outcome: Diversity Outcome: By 2025, identify minority stakeholder groups that are not currently represented in the leadership, decision-making and implementation of conservation and restoration activities, and create meaningful opportunities and programs to recruit and engage them in the partnership’s efforts.
Management Approach 1: Communications and Outreach
Key Action Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap
1. Identify key trusted leaders and interests of underrepresented communities (including HBCU’s, colleges and universities, Urban League, NAACP, fraternities, sororities, disability group, religious, LGBT, etc). Establish forums and begin dialogue to better understand how community issues link to watershed restoration. During the process, assess needs and preferences for ongoing communications like online forums, food security, etc. | a. Recruit diverse stakeholders and leaders to participate in 2015 Chesapeake Watershed Forum as well as subsequent Forums. | EPA DAT PA, MD, DC, DE, VA ACB People for Change Coalition | N/A | Beginning Summer 2015
| b. Develop a jurisdiction by jurisdiction contact list of key community leaders and interests/missions/priorities/key contact and communication preferences. | DAT PA, MD, DC, DE, VA CBP | PA, MD, DC, DE, VA | Fall 2016
| c. Plan and implement jurisdictional pilot outreach sessions led by key community leaders to determine community interest and potential links to restoration. | DAT PA, MD, DC, DE, VA Communications workgroup GITs | PA, MD, DC, DE, VA | 2016-2017
| d. Develop a set of follow up actions and recommendations for CBP (Executive Council level) adoption. | DAT PA, MD, DC, DE, VA | PA, MD, DC, DE, VA
2. Work with Toxic Contaminants Workgroup, jurisdictions and a contractor to identify communities where fish advisories exist (use EJ Screen tool) and initiate pilot project to improve communications and outreach. | a. Establish review and advisory subgroup to oversee fish advisory outreach project and contractor | DAT Toxics workgroup PA, MD, DC, DE, VA |  | Winter 2016
| b. Conduct planning session meeting with contractor discuss project scope and overall approach to review fish advisories and communities affected by fish advisories. Conduct periodic meetings to review products and provide, advise DAT and provide feedback to contractor on suggested improvements to products and deliverables. | DAT Toxics workgroup PA, MD, DC, DE, VA |  | Spring 2017
| c. Advisory subgroup to work with jurisdictions, DAT, contractor to devise activities that lead to dissemination and use of new fish advisory tools and approaches. Oversee implementation of activities. | DAT Toxics workgroup PA, MD, DC, DE, VA Comm workgroup |  | Winter 2017
| d. Engage community stakeholders and explore long term process for reviewing fish consumption and alternatives such as fish swapping etc. Provide recommendations to CBP. | DAT Toxics Workgroup PA, MD, DC, DE, VA Comm workgroup |  | Winter 2016
3. Work with federal partners to identify opportunities to work with diverse communities adjacent to federal installations | a. Conduct meeting with FOD and FLC to identify diverse communities adjacent to installations and issues of importance to those communities | DAT FLC NPS | Summer 2016 | Summer 2016
| b. Conduct meeting with FLC to identify opportunities to expand, create new, or better promote programs to engage and assist these communities | DAT FLC NPS |  | 2016-2017
4. Assist the development of Tree Canopy communication and outreach strategies targeted to diverse audiences, focusing on areas with greatest need and opportunity (e.g. low canopy/underserved communities; schools, faith-based, and other civic organizations; homeowner associations; etc.) | a. Work with Urban Tree Canopy goal team to pursue a workshop and case studies on community outreach strategies for Tree Canopy with an emphasis on diversity/ environmental justice opportunities | USFS/FWG | PA, MD, DC, DE, VA | Fall 2017
5. Contribute to EPA's Environmental Justice in Action Blog and use it as a resource. https://blog.epa.gov/blog/category/environmental_justice/ |  | DAT PA, MD, DC, DE, VA | PA, MD, DC, DE, VA | Summer 2016

## Supporting Activities 1
Key Actions and Performance Targets | Associated current and ongoing activities | Partner Name | Commiting to particpate in this action? | Resources your organization can commit | Additional resources needed
1 | 1 (1): DC DOEE works closely with Howard and has an existing pledge with the university. DOEE also empowers individuals from various DC communities, called Community Ambassadors, to recruit diverse participants. DOEE hopes to expand upon in the coming period. However, we are fortunate to have a very close relationship with all of the major District colleges and universities, all of which have signed the College and University Sustainability Pledge in support of the Sustainable DC Plan goals and outcomes. The faith-based community has been named a priority for the agency and staff have already made great inroads with some of the larger institution representatives such as the D.C. Baptist Convention. The District Department of Aging serves as a great outreach resource for any initiatives we wish to share with that segment and our Sustainable Resident Engagement (SRE) project being conducted in partnership with the DC Housing Authority launched this fall to continue into 2016. A traditionally underrepresented demographic, the affordable housing residents participating in the SRE project will be involved in the program design, implementation, and assessment of sustainable infrastructure and behavior change practices. The intention is not only to “green” the complexes, but use the inspiration of residents to support the development of youth, motivate young adults to pursue green jobs, and cultivate a stronger sense of community. 1 (2) Alliance for the Chesapeake Bay will do more targeted outreach for diverse particpation through and for Watershed Forum, Project Clean Stream, and Forum PLUS. We will do more targeted outreach to expand the number and diversity of people using Chesapeake Network for job oppotunities, events, etc. 1 (3) National Aquarium recieved NFWF Environmental Solutions for Communities grant for community engagement/outreach and associated environmental projects within Brooklyn and Curtis Bay. One of the grants is specifically focused on ways to engage Hispanic communities within the larger communities. As part of these projects/grants, we were able to hire a Conservation Community Coordinator to help lead these efforts. | DC Department of Energy and the Environment (DOEE) Alliance for the Chesapeake Bay (ACB) National Aquarium | YES YES YES
1A | 1 (A) 1: DC DOEE 1 (A) 2: EPA, Outreach and engagement to underrrepresented communities through Urban Waters Federal Partnership (Baltimore and Washington DC Metro areas); Making a Visible Difference (Newport News and Norfolk, VA); Brownfields and Superfund Programs; Environmental Justice; MOU with HBCU's | DC Department of Energy and the Environment (DOEE) Environmental Protection Agency | YES YES | DC DOEE will work with the Chesapeake Bay Program (CBP) to obtain information on the forum well in advance. We will then distribute the information to our listserv, which includes members and organizations at the local level. We can also share our listserv with CBP to ensure . EPA will provide staff time.
1B | 1 (B) 1: IPC will help build list of contact organizations, names, etc. 1 (B) 2: MD DNR Equal Opporuntites office has a network of diverse stakeholders 1 (B) 3: DC DOEE, currently in the process of compiling a list of key community leaders around the area of equity, diversity and EJ. | Interfaith Partners for the Chesapeake MD Department of Natural Resources DC Department of Energy and the Environment (DOEE) | YES YES YES | IPC: Help provide names/leads | NONE
1C | 1 [C]1: Maryland, No current activities 1 [C] 2: IPC can help put together an outreach event 1 [C] 3: DC DOEE, has established a new intra-department Environmental Justice Working Group. The Working Group is comprised of members from all divisions within DOEE, and is tasked with accomplishing certain EJ and Diversity objectives. The DOEE EJ WG can evaluate this key action as a possible objective. Additionally, the newly created DOEE Small Business and Civic Leaders Workgroup, whose charge is to focus primarily on bringing resources and incentives to civic leaders serving communities of color (e.g. Mayor’s Offices of Asian, Latino, and African Affairs) and small businesses owned by members of different racial and ethnic groups. This engagement includes discussions and materials regarding regulations such as the Foam Ban, which was created to protect and restore the Anacostia, and subsequently the Chesapeake Watershed. We will be meeting with this diverse stakeholder group on a regular bi-monthly schedule to address a range of DOEE topics and needs that the group identifies as priorities over the coming year or two. | Maryland State Agencies Interfaith Partners DC Department of Energy and the Environment (DOEE) | YES YES MAYBE | Maryland: Will allocate staff time to provide any technical assistance that is needed. If funding is required, Maryland will pursue funding avenues based on availablitly. IPC: Can provide taff time and expertise with compensation
1D | 1 (D) 1: DC DOEE, has established a new intra-department Environmental Justice Working Group. The Working Group is comprised of members from all divisions within DOEE, and is tasked with accomplishing certain EJ and Diversity objectives. | DC Department of Energy and the Environment (DOEE) |  | DC DOEE EJ WG can evaluate this key action as a possible objective.
2 | 2 (1): In 2015, DC DOEE revised DC's Fish Consumption Advisory. The new Advisory will be posted online (where the majority of fishing licenses are purchased) and there are also plans to post signs around major fishing areas. | DC Department of Energy and the Environment (DOEE) | YES | DC DOEE created an interactive language isolation map which displays LEP/NEP populations in DC using the most recent census data. This is one tool we might use, in addition to EJScreen, to develop our advisory communication strategy.
2A
2B | 2 (B) 1: EPA, MAVD Norfolk engagement of Elizabeth River Partnership. EPA R3 EJ Ofice Activities | Environmental Protection Agency | YES | EPA will provide staff time.
2C | 2[C] 1: Maryland currently updates their Fish Consumption Advisory - Guidelines for Recreationally Caught Fish Species on Maryland website and sends out fish advisory press releases ass needed. 2 [C] 2: DC DOEE works closely with neighboring jurisdictions of MD and VA (which have their own, different advisories) to communicate DC's Advisory. | Maryland State Agencies DC Department of Energy and the Environment (DOEE) | YES YES | MD DNR fisheries department to provide technical assistance as needed
2D | 2 (D) 1: DC Department of Energy and the Environment | DC Department of Energy and the Environment (DOEE) | MAYBE | DC DOEE may evaluate the need to conduct outreach to anglers.
3 | 3 (1): Maryland, No current actions specific to this action 3 (2): DC Department of Energy and the Environment 3 (3): EPA, currently chairs FOD and FLC. | Maryland State Agencies DC Department of Energy and the Environment (DOEE) Environmental Protection Agency | YES MAYBE YES | Maryland will allocate staff time to provide any technical assistance that is needed. If funding is required, Maryland will pursue funding avenues based on availablitly. DC DOEE, the DOEE EJ WG can evaluate this key action as a possible objective, in conjunction with DOEE's own Brownfield Site Remediation group. Additionally, many of our environmental enforcement efforts are emphasized around federal facilities in the District which neighbor diverse communities. EPA will incorporate discussions and follow up actions as part of FOD and FLC meetings in 2016.
3A
3B
4
4A | 4 (A) 1: Marykand, No current actions specific to this action 4 (A) 2: IPC has knowledge about urban tree canopy projects in urban faith communities 4 (A) 3: Annapolis Parks and Rec, will (1) continue to indentify and research grant opportunities for environmental and watershed projects that focus on African American, Latino and other youth and young adults 6 - 25 years of age. 4 (A) 4: DC DOEE, DOEE submitted a draft legislation which broadens the definition of "special trees." Currently, the removal of public or private property trees at least 55 inches in circumference requires a Special Tree Removal Permit. With the new legislation (expected to be approved in 2016), the criteria for special trees will be expanded to include more trees. Consequently, a higher number of people will pay fees for removing trees and the fee amount charged to those who tear down trees will increase. Additionally, on December 18 2015, DC is hosting a Tree Summit to bring together stakeholders from the private, public, and non-profit sectors to: share best practices for planting trees on private, federal and District-owned properties; improve coordination and collaboration; and to identify partners that will join us in planting 3,000 new trees on private property in 2016. Lastly, the Urban Tree Council is a workgroup of stakeholders that will address barriers to accessing and planting trees. The WG will identify overlapping issues to see how tree planting intersects with other District concerns such as flooding, drainage, heat island effect, and asthma. | Maryland State Agencies Interfaith Partners Annapolis Parks and Recreation: Stanton Center DC Department of Energy and the Environment (DOEE) | YES YES YES YES | MD DNR fiorestry department to provide technical assistance as needed IPC can attend and provide input at a meeting or two Stanton Center will develop and incorporate environmental and watershed education and activities in after school programming at the Stanton Community Center. Can also provide; Facility Use - Grant Writing for Youth and Young Adult volunteers DC DOEE Hiring one Full-time Equivalent ( FTE) in 2016 that will work on trees.$3-4 K to plant trees on private lands within the District in 2016 - $1 million annually for just planting alone

## Employment and Professional Eng
Outcome: Diversity
Goal: Citizen Stewardship
Outcome: Diversity Outcome: By 2025, identify minority stakeholder groups that are not currently represented in the leadership, decision-making and implementation of conservation and restoration activities, and create meaningful opportunities and programs to recruit and engage them in the partnership’s efforts.
Management Approach 2: Employment and Professional Engagement
Key Action Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap ID related factor or gap in Mgmt. Strat
1. Designate a diversity engagement coordinator to engage underrepresented communities and historically black colleges and universities in the watershed. | a. Each Jurisdiction and the Bay Program to explore opportunities to hire new Diversity coordinator or explore reallocation of existing staff time to strengthen Diversity coordination amongst the Partnership. | DAT CBP Partners PA, MD, DC, DE, VA FOD | PA, MD, DC, DE, VA | Spring/Summer 2016 or Winter 2017
2. Host a pilot Environmental Career Event | a. The DAT to host a pilot event highlighting the different career opportunities related to a Clean Chesapeake Bay. DAT to partner with Audubon Naturalist Society on their Black History Month job fair event. | DAT CBP Partners Audobon Naturalist Society People for Change Coalition PA, MD, DC, DE, VA FOD Private Vendors | DAT pilot to happen in one location with watershed-wide promotion Audubon Naturalist Society job fair in MD | Winter 2017 February 2016
b. Making links between different cultures, arts, and entertainment with environmental career opportunities.
c. Outreach to include DAT partnership email list-serves to better promote a more diverse attendance.
3. Develop pilot curriculum for an Environmental Career-Building Day for all K-12 Schools in the Bay Watershed. Work within the environmental literacy curriculum and school principles to implement a class schedule. | a. Work with ELit group to develop specific curriculum for one day Environmental Career - Building day. | DAT Enviro Literacy Team CBP Partners | PA, MD, DC, DE, VA | Summer 2016 - Winter 2017
b. Work with ELit group to implement pilot curriculum/after school program in high schools in each Jurisdiction.
4. Connect and work with existing career service programs for job applicants (e.g., interview training,). | a. Explore developing a hard copy and digital fact sheet that walks through career application services and offer technical assistance to those applying for jobs | DAT CBP Partners Community Colleges/Univ | PA, MD, DC, DE, VA | Fall 2016
b. Communicate and promote the fact sheet at job fairs/events across the watershed
5. Identify opportunities to create an internship program specifically for individuals from diverse backgrounds working with universities like Howard, Morgan State, UMES, etc. | a. Enhance recruitment/outreach strategies of existing internship program to increase diverse applicant pool. | DAT CBP Partners Choose Clean Water Coalition CRC Community Colleges and career services dept. | PA, MD, DC, DE, VA | Fall 2016
b. Evaluate models that have been tested throughout the watershed that increase green job/career training opportunities.
c. Choose one model to begin connecting interns with in-demand employment opportunities.
6. Increase outreach to diverse groups for hiring full time employees. | a. Enhance recruitment/outreach strategies of existing hiring programs and explore options to reduce the amount of uncompetitive internal hiring in order to increase diverse applicant pool (e.g. environment and related career fairs). | USFS
| b. Jurisdictions to reevaluate hiring practices that may inadvertently make it difficult for a diverse group of applicants to obtain jobs | EPA Region 3

## Supporting Activities 2
Key Actions and Performance Targets | Associated current and ongoing activities | Partner Name | Commiting to particpate in this action? | Resources your organization can commit | Additional resources needed
1 | 1 (1): MD DNR Equal Opportunites Office - however, no staff specific to diversity inclusion in bay related activies 1 (2): DC DOEE in 2015 invested in an FTE who leads the Community Engagement and Equity work for the Urban Sustainability Administration and DOEE at-large. Other opportunities will arise through grant funding we receive and collaborative partnerships from various communities. We will also, when possible, support professional development and training opportunities for staff to learn how to better engage with diverse stakeholder and institutionalize equity throughout all programming. 1 (3): CCWC has a new Young Leaders of Color Mentorship Program. Kick off begins with a panel discussion on the importance of mentorship and meet-and-greet during Choose Clean Water Conference on May 25, 2016 in Annapolis. Mentees are assigned a mentor. Several other meetings occur throughout the year. | MD Departnment of Natural Resources DC Department of Energy and the Environment (DOEE) Choose Clean Water Coalition (CCWC) | YES YES YES | MD DNR staff to work with other MD state agencies to pursue option of full time diversty coordinator or explore realocation of exisintg staff time to meet the needs.
1A | 1 (A) 1: DC DOEE, Our Community Engagement and Equity lead staff is working closely with staff agency-wide to guide outreach, communication, and engagement efforts with an eye on diversifying our traditional early adopter audience. That work includes efforts to restore and protect the Anacostia River, and the communities and neighborhoods historically tied to its history and future: the predominantly African American residents. DOEE’s Stormwater Management Division, in partnership with the Anacostia Watershed Society and Anacostia Riverkeepers, is poised to launch educational boat tours along the Anacostia with the goal to engage the majority communities of color within Wards 7 and 8. Intentional and inclusive outreach with the communities will help inform the project’s design and implementation strategy. The recruit approach will be based on existing stakeholder groups and include as assessment of the participation gap, with action items that will close them. This project will launch in 2016 and is intended to continue for seasons to come. 1 (A) 2: EPA currently engaged in MOU's with HBCU in watershed (Norfolk State, Hampton Univ, Howard Univ, etc) | DC Department of Energy and the Environment (DOEE) Environmental Protection Agency | YES YES | EPA will provide staff time.
2 | 2 (1): MD DNR, No current actions specific to this action 2 (2): Chesapeake Research Consortium, participates in local/regional career fairs to promote the Environmental Management Career Development Program, which houses the Cheapeake Bay Program Staffers. Just this year, career fair participation was prioritized based on opportunities to interact with more diverse students and potential applicants. 2 (3): DC DOEE has a successful hiring program called Green Pathways (http://doee.dc.gov/greenpathways) Of these, the Green Zone Environmental Program recruits diverse high school, college, and recently graduated students for a short term summer employment. Every summer, GZEP partners with the Marion Barry Summer Youth Employment Program to provide over 300 youth and young adults, ages 14 to 24, with an opportunity to learn about energy and environmental issues, complete community-based environmental work projects such as rain gardens and storm drain markers, and prepare for careers. Additionally, various divisions within DOEE teach environmental classes throughout the summer at schools in low-income and minority communities. 2 (4): EPA partnership with Norfolk State, Hampton University, VA DEQ to increase environmental science and engineering careers for African American students. | MD Departnment of Natural Resources Chesapeake Research Consortium (CRC) DC Department of Energy and the Environment (DOEE) Environmental Protection Agency | YES YES YES YES | MD DNR to help lead/facilitate the Envrionmental Career Event. Staff to partner with other jurisdictions/organizations to plan and implement this event. CRC will participate in any regional environmental career event to highlight the Environmental Management Career Development Program, staff time and travel funds for CRC Staff participation at the event. DC DOEE, In 2016, DOEE plans to matriculate some GZEP staff and students into other opportunities at the Department. EPA will provide staff time and funding.
2A | 2 (A) 1: EPA | Environmental Protection Agency | YES | EPA's Urban Waters Federal Partnership - will assist with developing environmental career events. Staff time and funding.
2B | 2 (B) 1: EPA's Urban Waters Partnership Grant Funding - Baltimore Civic Works to install water efficiency products in residential units | Environmental Protection Agency | YES | Funding.
2C | 2 [C] 1: DC Department of Energy and the Environment | DC Department of Energy and the Environment (DOEE) | YES | DC DOEE is currently in the process of compiling a list of key community leaders around the area of equity, diversity and EJ. We can also include the DAT partnership email list serves in our outreach efforts.
3 | 3 (1): Maryland,No current actions specific to this action 3 (2): Annapolis Parks and Rec, Stanton Center 3 (3): Citizens Advisory Committee (CAC) | Maryland State Agencies Annapolis Parks and Rec, Stanton Center Citizens Advisory Committee (CAC) | YES YES YES | MD DNR environmental education department to work with local schools systems to plan and implement this pilot program. Stanton Center can provide some facility use - after school and out of school programs - in-kind supplies and equipment CAC is developing a student engagement program focused on students at Historically Black Colleges and Universities. The program will link students in independent study programs of all disciplines to Chesapeake Bay Watershed issues, we will link them to mentors within the membership of CAC and potentially LGAC, and when appropriate link them with experts in the Bay Program partnership.
3A | 3 (A) 1: EPA - Green School Yards Project - will include curricula related to green infrastructure as part of EPA MAVD program in Newport News, VA | Environmental Protection Agency | YES | 50000
3B
4 | 4 (1): DC Department of Energy and the Environment 4 (2): National Aquarium | DC Department of Energy and the Environment (DOEE) National Aquarium | MAYBE YES | DC DOEE will consider incorporating this into their current approach. Urban Conservation & Education Internship Program, a partnered internship program involving the National Aquarium, USFWS, the Maryland Port Administration and Living Classrooms Foundation. This program gives four college students from the greater Baltimore area the opportunity to explore career opportunities in the conservation sector. The first year the program had 10-15 applicants however this year( 2016) there are over 60. The main difference is that Curtis Bennett revamped the recruitment strategy, made connections and ultimately gave presentations at many of the local schools (UMD College Park, UMES, Coppin State, Morgan State, UMES, Towson, UMBC, Johns Hopkins, Anne Arundel Community College) about careers and internships in conservation, specifically talking about our partnered internship program.
4A | 4 (A) 1: MD DNR, No current actions specific to this action 4 (A) 2: Chesapeake Research Consortium | Maryland State Agencies Chesapeake Research Consortium (CRC) | YES YES | MD DNR staff towork with other State agencies to develop fact sheet for public use across Maryland CRC can take additional promotional materials to any career or networking events to help distribute this resource - assist in the development of such a fact sheet through identifying any known resources for inclusion and give staff time.
4B | 4 (B) 1: MD DNR, No current actions specific to this action 2 (B) 2: ACB, Businesses for the Bay Program to promote the use of fact sheet to others. | Maryland State Agencies Alliance for the Chesapeake Bay (ACB) | YES YES | MD DNR communications staff to work with other State agencies to coordinate the release of fact sheet and other job opportunites ACB will promote the fact sheet through it's new Businesses For the Bay program which is a business membership program.
5 | 5 (1): MD State Agencies currently have internship opportunites that are open to a diverse population, however no current programs directly target a diverse population. 5 (2): DC Department of Energy and the Environment | Maryland State Agencies DC Department of Energy and the Environment (DOEE) | YES YES | MD DNR staff to work with other State agencies to enhance recruitment/outreach strategies of existing internship program to increase diverse applicant pool. DC DOEE, The DOEE EJ WG can evaluate this key action as a possible objective.
5A | 5 (A) 1: Chesapeake Research Consortium | Chesapeake Research Consortium (CRC) | YES | CRC is committeed to increasing outreach efforts and relationship building with more diverse institutions and communities in an effort to incease the diversity of Environmental Management Career Development Program. Staff time. Funds for event registration and associated travel expenses.
5B
5C
6 | 6 (1): MD DNR Equal Opportunities Office directs outreach to diverse population for job opporuntites 6 (2): DC Department of Energy and the Environment | Maryland State Agencies DC Department of Energy and the Environment (DOEE) | Yes YES | MD DNR staff to work with other state agencies Enhance recruitment/outreach strategies of existing hiring programs and explore options to reduce the amount of uncompetitive internal hiring in order to increase diverse applicant pool. DC DOEE,The DOEE EJ WG can evaluate this key action as a possible objective.
6A | 6 (A) 1: IPC 6 (A) 2: Chesapeake Research Consortium 6 (A) 3: EPA's Workforce Diversity Development and Inclusion Council conducting activities to improve diverse recreuitment as well as development of diverse mployees within agency | Interfaith Partners for the Chesapeake Chesapeake Research Consortium (CRC) Environmental Protection Agency | YES YES YES | IPC will include for 1 year in their newsletters, a section devoted entirely to hiring for environmentally-related jobs. IPC's ewsletter reaches over 1,000 people of faith throughout Maryland. CRC Staff time. Funds for event registration and associated travel expenses. EPA will provide staff time.
6B | 6 (B) 1: ACB | Alliance for the Chesapeake Bay | YES | ACB could assit with develop suggested language for use in personel policies that willing CBP partners can adopt or adapt to their organizations.

## Promote Environmental Justice
Outcome: Diversity
Goal: Citizen Stewardship
Outcome: Diversity Outcome: By 2025, identify minority stakeholder groups that are not currently represented in the leadership, decision-making and implementation of conservation and restoration activities, and create meaningful opportunities and programs to recruit and engage them in the partnership’s efforts.
Management Approach 3: Promote Environmental Justice
Key Action Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap ID related factor or gap in Mgmt. Strat
1. Bay Program jurisdictions and partners will review and revise their respective grant guidance including documents, as needed, to address diversity. EPA will review and revise Bay Program grant guidance criteria for Clean Water Act Section. 117 local government funding to determine how to better address diversity and environmental justice considerations at the local level. | a. EPA will revise the FY 2016 Chesapeake Bay Program Grant Guidance to address diversity considerations and set expectations for jurisdiction reviews of their grant guidance documents | EPA PA, MD, DC, DE, VA FOD Other Partners GIT 6? |  | Fall 2015/early 2016
| b. Jurisdictions review and revise their respective grant guidance documents as needed. |  |  | Fall 2016
c. FOD review and revise their grant guidance documents as needed.
d. Other partners review and revise their grant guidance documents as needed.
e. EPA to review as part of revision of 2016 CBP Grant Guidance.
2. a. EPA will use EJSCREEN and other informational tools and databases in 2015 to offer additional information and perspective that could enhance partners’ understanding of the watershed’s diverse populations and to help target areas with potential for environmental justice concerns.. b. EPA will provide EJSCREEN to Bay jurisdictions, federal agencies and other partners to also help them target communities and organizations for grant funding opportunities. c. The Bay Program will add EJSCREEN as a new data layer for the Bay Program Watershed Model. d. The Bay Program The public access and climate resiliency workgroups should use EJSCREEN and other tools to help prioritize new public access sites and target communities that might be in areas vulnerable to climate change impacts. | a. EPA to provide training and presentations on use of EJSCREEN to GITs, CBP Workgroups and partners. | EPA | PA, MD, DC, DE, VA | 2015/2016
| b. EPA to include discussion of EJSCREEN in FY2016 CBP Grant Guidance. | EPA |  | 2015/2016
| c. CBP to add EJ SCREEN as a data layer for the Watershed Model. | EPA/CBPO |  | 2016
| d. DAT will work with the public access and climate resiliency teams to help identify potential sites in diverse communities. | DAT GIT 5 Public access team Climate resiliency team |  | 2016/2017
3. Bay Program and its partners will evaluate and improve transparency and efficiency in providing community-based grant opportunities and will work with partner funding organizations, to develop a guide to assist groups in grant competition awareness, selection criteria, accountability, capacity building and grant writing training, etc., for areas with diverse and underrepresented populations. | a. DAT to meet with Bay Funders Network to initiate discussions | DAT |  | Spring 2016
| b. DAT will consult with National Fish and Wildlife Foundation’s Technical Capacity Program | EPA PA, MD, DC, DE, VA |  | Winter 2016/2017
| c. Develop funding guide. | CBP Partners EPA
| d. EPA, jurisdictions and Federal agencies will review and revise their RFP email lists to ensure that grant opportunities are being distributed to broad and diverse constituencies. Examples, HOA’s, community centers, rec centers, etc. | FOD
e. Develop webinars/ capacity building
4. Work with local governments in the watershed to explore how the Bay Program can inform or help local decision makers maximize benefits and minimize adverse impacts from restoration project planning, siting and funding processes. | a. DAT to work with LGAC and Local Leadership Team to explore opportunities to work with local leaders on these issues. | DAT LGAC Local Leadership Team |  | 2016/2017
5. Collaborate and exchange information with various environmental justice entities throughout the Bay Watershed and incorporate their perspectives and those of community and faith-based organizations and leaders throughout the Bay Program governance structure, including its three advisory committees (citizens, local governments and scientific/technical). | a. DAT to work with community leaders to engage them in MB, PSC, CBP GITs and workgroups as active contributing members. | DAT GITs CBP Partners CAC. LGAC and STAC |  | 2017/2016
b. DAT to meet with the 3 CBP Advisory committees to seek their input on ways to help make CBP more representative of the diverse communities and people in the Bay watershed.
c. Identify key EJ groups in the jurisdictions
d. Reach out to existing groups such like those identified in the management strategy and more like WE ACT and Blackbelt EJ Center.
6. Particpate in Greater Baltimore Wilderness Coalition's newly formed Equity Workgroup. |  | DAT | Anne Arundel, Baltimore, Carroll, Harford, Howard, Montgomery, and Prince George’s Counties and Baltimore City | Ongoing

## Supporting Activities 3
Key Actions and Performance Targets | Associated current and ongoing activities | Partner Name | Commiting to particpate in this action? | Resources your organization can commit | Additional resources needed
1 | 1 (1) MD DNR, No current actions specific to this action | Maryland State Agencies | YES | MD DNR will allocate staff time to provide any technical assistance that is needed. If funding is required, Maryland will pursue funding avenues based on availablitly.
1A | 1 (A)1: EPA, Urban Waters Federal Partnership Small Grants Program and Five Star Grants Program (Checking to see if 5 star is EPA only) | Environmental Protection Agency (Fed Partners?) | YES | EPA can provide funding.
1B | 1 (B) 1: DC Department of Energy and the Environment, The DOEE grants management division addresses diversity and environmental justice by: • Publishing RFAs to announce opportunities for funding, all of which are competitions open to all eligible organizations • Announcing RFAs in the District Register, Office of Partnerships and Grants Services Funding Alert, DOEE website, and official DOEE press release • Opening competitions for at least 30 days, allowing for smaller entities without full-time grant writing staff to prepare a response and submit a complete application package | DC Department of Energy and the Environment (DOEE) | YES | DC DOEE, grants management division commits various resources to fulfilling the aforementioned activities, including: • Open access to information about grants management on the intranet • Year-round recurring training workshops on grants topics and in a one-to-one setting, if requested
1C
1D
1E
2 | 2 (1): MD DNR, Environmntal Justice layers are incoporated in certain grant soliciations, however, it is not a priority across all grant opportunties 2 (2): EPA | Maryland State Agencies Environmental Protection Agency | YES YES | MD DNR staff to work with other State agencies on the review of State grant guidance to better incorporate environmental justice EPA will hold monthly EJ Coordination meetings with jurisdictions to share latest information, tools and issues related to regional and national EJ concerns.
2A
2B
2C
2D
3 | 3 (1): MD DNR, No current actions specific to this action 3 (2): The DC DOEE grants management division utilizes various channels to advertise grant opportunities, including: • Online through the District Register, Funding Alert, DOEE website, and press releases • Informational workshops at DOEE headquarters open to nonprofits, businesses, faith-based groups, and all organizations interested in learning about DOEE’s priorities and past/current/upcoming grant competitions • District-wide government workshops hosted by the DC Office of Partnerships and Grants Services open to the public The DOEE grants management division has created various guidance tools for internal program officers on grant competitions, including: • An RFA template for announcing grant opportunities, containing information about selection criteria for the applications • Review panel guidance document, which explains the accountability of application reviewers Regarding grant writing training, the DC Office of Partnerships and Grant Services offers grant writing training to all interested individuals, across wards, for free. DOEE program staff also host pre-application conferences to answer questions posed by potential applicants. All questions and answers are posted on the DOEE website for the public. 3 (3): EPA will integrate environmental justice into EPA enforcement targeting schemes to help reduce public health and environmental concerns in diverse communities.” - 2016 | Maryland State Agencies DC Department of Energy and the Environment (DOEE) Environmental Protection Agency | YES YES YES | Maryland DNR will allocate staff time to provide any technical assistance that is needed. If funding is required, Maryland will pursue funding avenues based on availablitly. The DC DOEE grants management division commits various resources to fulfilling the aforementioned activities, including: • Open access to information about grants management on the intranet • Year-round recurring training workshops on grants topics and in a one-to-one setting, if requested EPA will provide staff time.
3A | 3 (A) 1: EPA's Building Blocks for Sustainable Communities; Green and Complete Streets Workshops - MAVD Norfolk and Newport News Green Streets, Green Jobs, Green Towns small grants | Environmental Protection Agency | YES | EPA will provide staff time and workshops.
3B
3C
3D
3E
4
4A | 4 (A) 1: MD DNR currently coordinates with LGAC on Bay Program related activiites | Maryland State Agencies | YES | MD DNR staff to work with MD LGAC representation to achieve desired actions
5 | 5 (1): MD DNR, No current actions specific to this action | Maryland State Agencies | YES | Maryland will allocate staff time to provide any technical assistance that is needed. If funding is required, Maryland will pursue funding avenues based on availablitly.
5A
5B
5C
5D

## Tracking and Assessment
Outcome: Diversity
Goal: Citizen Stewardship
Outcome: Diversity Outcome: By 2025, identify minority stakeholder groups that are not currently represented in the leadership, decision-making and implementation of conservation and restoration activities, and create meaningful opportunities and programs to recruit and engage them in the partnership’s efforts.
Management Approach 4: Tracking and Assessment
Key Action Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap ID related factor or gap in Mgmt. Strat
1. Establish a baseline of the level of diversity (staff, boards, programs and initiatives aimed at increasing internal diversity) | a. Consult with Guidestar to identify quantitative metrics that will be used for tracking | DAT, CBT, CBF Partners to be surveyed in the following Jursidictions: PA, MD, DC, VA, DE Choose Clean Water Co. FOD | PA, MD,DC,DE, VA | Winter 2016
| b. Survey Partners on existing diversity programs that aim to increase diversity and inclusion in (employment, volunteerism, programs, etc.) |  |  | Spring 2016
| c. Using a Guidestar type tool adapted for the Chesapeake region, collect diversity data of Chesapeake Bay Program Partner organizations. |  |  | Fall 2017
| d. Examine EPA’s diversity dashboard to determine if it can serve as a model for Bay Partners. |  |  | Spring 2016
e. Develop method of tracking anecdotal and qualitative metrics of Strategy implementation
2. Increase the Bay Program stakeholder base by tracking new partnerships that help to better identify and target underrepresented and underserved Chesapeake communities to engage in Partnership efforts. | a. Identify and approach organizations and groups that work within diverse Chesapeake communities | DAT Communications workgroup EPA PA, MD, DC, VA, DE | PA, MD,DC,DE, VA | Winter 2016
b. Identify community groups that may be candidates for environmental restoration projects and programs in the following jurisdictions; DE, PA, MD,DC, VA
3. Use EPA’s EJ Screening tool as a base for identifying stressed or under-served Chesapeake communities | a. Create a map that overlays data sets such as; demographic, environmental, sub-watersheds, proximity to partner organizations, environmental justice groups, community service groups, etc. | DAT EPA | Watershed Wide | Spring 2016
b.Track how partners are using the tool
4. Collect and evaluate existing diversity programs and develop a strategy for improvement. | a. Continue to develop existing baseline matrix and highlighting current gaps within the Partnership | DAT CBP Partners PA, MD, DC, VA, DE | Watershed Wide | Ongoing

## Supporting Activities 4
Key Actions and Performance Targets | Associated current and ongoing activities | Partner Name | Commiting to particpate in this action? | Resources your organization can commit | Additional resources needed
1 | 1 (1): MD DNR, No current actions specific to this action 1 (2): DC Department of Energy and the Environment 1 (3): Choose Clean Water Coalition will be tracking their Annual Conference Demographic Data CCWC. Tracked conference attendees demographic data in 2015. CCWC will track demographic data in 2016. | Maryland State Agencies DC Department of Energy and the Environment (DOEE) Choose Clean Water Coalition (CCWC) | YES MAYBE YES | Maryland will allocate staff time to provide any technical assistance that is needed. If funding is required, Maryland will pursue funding avenues based on availablitly. DC DOEE will consider incorporating this into their current approach.
1A | 1 (A) 1: EPA's Urban Waters Federal Partnership developing tracking and assessment approach; MAVD Newport News Developing Tracking and assessment tools 1 (A) 2: Choose Clean Water created a diverstiy tool-kit which gives step-by-step guidance on how to increase diversity in your organization through changes in governance, hiring, and communications. This tool-kit has been distributed widely and should help partners work towared increasing internal diversity. | Environmental Protection Agency (Region 3) Choose Clean Water Coalition (CCWC) | YES YES | EPA will provide staff time.
1B | 1(B) 1: ACB began tracking attendee demographics in 2015 for annual Chesapeake Watershed Forum. This will continue as part of the registration process | Alliance for the Chesapeake Bay (ACB | YES
1C
1D
1E
2 | 2 (1): MD DNR, No current actions specific to this action 2 (2): DC DOEE has established a new intra-department Environmental Justice Working Group. The Working Group is comprised of members from all divisions within DOEE, and is tasked with accomplishing certain EJ and Diversity objectives. DOEE makes grants to organizations, not individuals, and organizations are typically not categorized by race or economic status. | Maryland State Agencies DC Department of Energy and the Environment (DOEE) | YES MAYBE | Maryland will allocate staff time to provide any technical assistance that is needed. If funding is required, Maryland will pursue funding avenues based on availablitly. DC DOEE, The DOEE EJ WG can evaluate this key action as a possible objective.
2A
2B
3 | 3 (1): MD DNR, No current actions specific to this action | Maryland State Agencies | YES | Maryland will allocate staff time to provide any technical assistance that is needed. If funding is required, Maryland will pursue funding avenues based on availablitly.
3A
3B
4 | 4 (1): MD DNR, No current actions specific to this action 4 (2): DC DOEE has established a new intra-department Environmental Justice Working Group. The Working Group is comprised of members from all divisions within DOEE, and is tasked with accomplishing certain EJ and Diversity objectives. | Maryland State Agencies DC Department of Energy and the Environment (DOEE) | YES MAYBE | Maryland will allocate staff time to provide any technical assistance that is needed. If funding is required, Maryland will pursue funding avenues based on availablitly. The DC DOEE EJ WG can evaluate this key action as a possible objective.
4A

## Other Activities and Efforts
PARTNER NAME | Diversity Related Efforts for: Communications and Outreach | Diversity Related Efforts for: Employment and Professional Engagement | Diversity Related Efforts for: Promoting Environmental Justice | Diversity Related Efforts for: Tracking and Assesment
DC Department of Energy and the Environment (DOEE) Chesapeake Bay Commission (CBC) | Very recently, staff has been involved in neighborhood walk-throughs as a means to connect residents with DOEE resources. The walks are a collaboration between the Mayor’s Community Relations team, representatives from key District government agencies, neighborhood advisory commissions, and everyday residents. This has been extremely valuable in demonstrating not only the priority concerns of certain neighborhood communities (as they define them), but also an opportunity to share the direct resources available to them from DOEE. Some priority examples include interests/concerns pertaining to healthy homes, community solar, and Low Impact Development incentives, such as the RiverSmart Homes program, which directly supports the Anacostia and Chesapeake Watershed. As noted above, the engagement with the aforementioned groups will also provide insights into the needs and interests of some communities. Our ongoing participation in neighborhood commission meetings will also provide opportunities to listen to what resonates most. In addition to our tabling events, DOEE project staff go door-to-door to engage with residents around issues that impact their livelihood. For example, the Stream Restoration team speaks directly with residents (mostly African Americans) impacting by upcoming projects that while improving the health of streams also cause temporary disruptions to their daily lives. This practice is one that builds the relationships and trust of the communities that reside along the streambeds.
Work collaboratively with Bay Program partners to identify legislative, budgetary and policy needs to advance the goals of the Chesapeake Bay Agreement. We will, in turn, pursue action within our member state General Assemblies and the United States Congress. (Per CBC Resolution #14-1) By providing staff time, work with GIT to consider policy changes or legislative actions identified by the GIT - dependent on political climate and budgets