**POST-LICENSE APPLICATION FILING TIMELINE : Source: Hydropower reform coalition and FERC**

|  |  |  |
| --- | --- | --- |
| FERC REQUIREMENTS UNDER FPA or ILP | TIMELINE | DATES |
| 1. License Application | 2 years before license expiration | August 31, 2012 |
| 1. Public Notice of Application | 14 days after receipt | September 13, 2012 |
| 1. FERC Decision on Outstanding Additional Information Requests (AIR) | 30 days after step 2. |  |
| 1. Satisfaction of AIR | 90 days after Step 3. |  |
| 1. FERC Notice of Acceptance and Ready for Environmental Analysis (REA) .   Exelon also files for 401 Water Quality Certification from State | 60 days after Step 4 | Expected Dec 2012 or Jan 2013  State has 1 year to act on water quality certification. |
| 1. FERC Reply to Comments on REA | 45 days after Step 5. |  |
| 1. FERC issues non-draft EA or   7.a FERC issues draft EA or draft EIS | 120 days after step 6.  180 days after step 6. |  |
| 1. Comments due on non-draft EA   8.a. Comments due on draft EA or draft EIS, | 30-45 days after step 7  30-60 days after step 7 |  |
| 1. Modified Terms and Conditions | 60 days after Step 8. |  |
| 1. FERC issues Final EA or EIS | 90 days after Step 9. |  |
| 1. FERC issues final license |  | Expected September 2014. |