**POST-LICENSE APPLICATION FILING TIMELINE : Source: Hydropower reform coalition and FERC**

|  |  |  |
| --- | --- | --- |
| FERC REQUIREMENTS UNDER FPA or ILP | TIMELINE | DATES  |
| 1. License Application
 | 2 years before license expiration | August 31, 2012 |
| 1. Public Notice of Application
 | 14 days after receipt | September 13, 2012 |
| 1. FERC Decision on Outstanding Additional Information Requests (AIR)
 | 30 days after step 2.  |  |
| 1. Satisfaction of AIR
 | 90 days after Step 3. |  |
| 1. FERC Notice of Acceptance and Ready for Environmental Analysis (REA) .

 Exelon also files for 401 Water Quality Certification from State | 60 days after Step 4 | Expected Dec 2012 or Jan 2013State has 1 year to act on water quality certification. |
| 1. FERC Reply to Comments on REA
 | 45 days after Step 5.  |  |
| 1. FERC issues non-draft EA or

7.a FERC issues draft EA or draft EIS | 120 days after step 6.180 days after step 6.  |  |
| 1. Comments due on non-draft EA

8.a. Comments due on draft EA or draft EIS, | 30-45 days after step 730-60 days after step 7  |  |
| 1. Modified Terms and Conditions
 | 60 days after Step 8. |  |
| 1. FERC issues Final EA or EIS
 | 90 days after Step 9.  |  |
| 1. FERC issues final license
 |  | Expected September 2014.  |