Report to Congress

Timeline

Jun 13 Present Comm Strategy and draft RTC at Management Board meeting

Jun 20 Feedback from MB on both due

Jun 27 Present Comm Strategy and draft RTC at Principals’ Staff Committee meeting

Jul 11 Present updated RTC to Management Board

Jul 25 MB Fatal flaw review due on RTC

Aug 8 Present final RTC to MB

Aug 15 Initiate HQ review of final RTC

Sep TBD Present final RTC to PSC

Oct TBD Publish RTC in conjunction with new agreement