## (Goal Name) Workplan
Draft 2-Year Workplan (Nov 2, 2015)
Riparian Forest Buffer Outcome
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Management Approach 1: RFB Leadership
Meet with RFB leadership within each state to develop a coordinated, riparian forest buffer (RFB) strategy to boost enrollment | Hold 3-4 meetings/year | State Lead | Baywide | 2017-12-01 | staff | n/a
| Implement State Action Plan | State Lead | Baywide | 2017-12-01 | staff | n/a
| Appoint a leadership-field liaison/coordinate RFB activity in state | State Lead | As needed | 2016-07-01
| 2-3 Opportunities for state leadership to express need/RFB is a priority practice | State Lead | Baywide | 2017-12-01
| Establish a PA RFB Leadership Team a. Craft a purpose statement b. Hold first meeting | DCNR and DEP | Pennsylvania | 2016-02-01
| Host regional 2-day RFB Summit | USFS, FSA | Baywide | 2016-03-01 |  |  | Project funded by NFWF Chesapeake Bay Stewardship Fund Innovative Nutrient and Sediment Reduction Grants (INSRG)
| Host a Statewide RFB summit, led by leadership team | PA DCNR, MD CREP Committee | Pennsylvania | 2016-07-01
Make additional funding available to states to promote and improve RFB and CREP enrollments | Increase acres enrolled in Chesapeake Bay CREPS, CP22 Riparian Forest Buffer Conservation Practice | FSA | Baywide | 2017-12-01
Coordinate and support State Leads and other partners in achieving RFB goals | Achieve actions in MS 2 year workplan | USFS | Baywidee | 2017-12-01
Pilot Projects to Inform Leadership | Coordinate with Sustainable Ag community | MD DNR Forest Service | Maryland | 2016-07-01 | Staff
| Development of a flexible buffer program with innovative tools and programs to fill niches not met by traditional buffer programs | Upper Susquehanna Coalition, NFWF | Upper Susquehanna | 2016-07-01 | 300000 | 300000
Management Approach 2: RFB Enhancements
Coordinate with allied practices, especially streambank fencing, streambank stabilization and/or transitional woodland practice | Some landowners that receive funding for the allied practices will be asked about installing CP22 | NY NRCS and FSA, USC, | New York | 2017-01-01
Increase financial assistance for CREP | Continue to assess available financial assistance as needed to encourage landowner interest in CREP and implementing conservation practice | FSA | Baywide | 2017-12-01
Focus PA's Stream ReLeaf program | Map and target priority watersheds for the program | PA DEP | PA-- Priority watersheds | 2016-07-01
| Pursue permanent easements | PA DEP | PA- Priority watersheds | 2016-07-01
| Establish stronger partnerships through greater outreach | PA DEP | Pennsylvania | 2016-07-01
Program adjustments in RFB cost-share practices (i.e., CREP) per state task force reports | Work with FSA to approve CREP amendments and make practice adjustments | State leads | Baywide | 2017-12-01
Apply the Healthy Streams Farm Stewardship Program | 100 acres | Alliance for the Bay | Maryland | 2017-12-01
Develop partnership potential with NGOs | New roles for specific NGOs in the states (--may be moved to maintenance, TA, outreach?) | State Leads | Baywide | 2016-01-01
Pursue a state/privately-funded RFB program | Test methods for flexibility in buffer administration and management | DCNR, DEP | Statewide
| Pilot sites showcasing different approaches including maintenance needs | DCNR, DEP | Priority watersheds
| Incorporate agroforestry practices into the RFB program | PA DCNR | TBD
Management Approach 3: RFB Technical Assistance
Increase staffing levels to provide more technical assistance | Hire 8 additional field personnel through grant from FSA | FSA, FS, ACB, State forestry in MD, PA, VA | MD, PA, WV, VA | 2017-12-01 | 560K | 560K
| Hire Program Technician (1) and Temporary Staff (4) | NYS FSA | New York | 2016-2017 | 2016: $149,167.00 2017: $149,167.00 Total: $298,334.00 | Amount requested
| Hire Part-time Staff (5) to form a riparian buffer team | USC | New York | 2016-2017 | 2016: $253,000.00 2017: $253,000.00 Total: $506,000.00 | Amount requested (FSA Funding Request)
Increase effectiveness of landowner education on RFB establishment and maintenance through coordination and incorporating lessons learned | Identify successful programs | State Leads | Baywide | 2016-06-01
| Reach out to groups such as Clearwater Conservancy, Lancaster Farmland Trust, etc | DCNR, DEP | Baywide | 2016-04-01
| Support PACD outreach efforts in creating a clearinghouse of informational materials | DCNR, DEP, PACD | Pennsylvania | 2017-12-01
| Enhance collaboration among organizations to better understand farmers' needs | DCNR, DEP | Pennsylvania | 2017-12-01
Train NRCS employees on doing outreach and education to landowners on RFB | NRCS employees receive >10 trainings | NRCS | Baywide | 2017-12-01
Consistently inform landowners on the benefits of RFB during conservation planning process | Train and encourage employees to educate during conservation planning process | NRCS | Baywide | 2017-12-01
Pilot strategies to reinforce incentives for producers to install and maintain riparian forest buffers | Work with a SWCD to pilot higher priority for EQIP when CREP buffer is used | NRCS, SWCD | TBD | 2017-12-01
Expand partnerships to address technical assistance needs | Establish one new partner per state | State Leads | Baywide | 2016-01-01 | staff
Use Regional Conservation Partnership Program projects to increase RFB enrollment | 100 acres | Alliance for the Bay | MD and PA | 2017-12-01
Technical Assistance provided by NYS DEC Forester | Forest Service funded position to provide forestry support on EQIP projects | NYS DEC | Tioga and Broome Counties | On-going | 120,000/yr | 120,000/yr | funded, but more RFB opportunities are needed
Management Approach 4: RFB Outreach and Increasing New Enrollment
Address programmatic design/delivery that create barriers to new enrollment | Secure funding to process CRP/CREP new contracts that wish to enroll | DNREC, DE FSA/NRCS | Delaware | 2016-01-01 | staff |  | The Delaware CREP Program has a programmatic freeze until funding shortfalls are addressed. Shortfalls are approximately: $500,000 for 2015, $500,000 for 2016, and $300,000 for 2017 for current enrollments. Work-arounds are needed for new enrollees.
Execute Regional Outreach Strategy for 2016 | Improve outreach of RFB: webinar education series, information packets, posters, displays, forum, support for re-enrollment | USFS, FSA, Alliance | Baywide | 2016-05-01 | 184000 | 184000 | funded
Seek liaisons (leaders, early adopters) within farming communities | Reach out to dairy, horse, and poultry farmers, and others | Dept of Ag | Baywide | 2016-12-01
| Reach out to plain sect community | Partners | Priority watersheds | 2016-12-31
Increase MPL soil rental rates | Work with FSA to make adjustments in CREP agreements | State Leads | As needed | 2017-12-01
Share local case studies of successful buffers; consider LandCare model | Reports on case studies and how LandCare model could be used | MD DNR Forest Service | MD | 2017-12-01
Media Rebranding | Create/distribute various media products to promote RFB programs | NYS FSA/NRCS | New York | 2017-12-01 | 2016: $10,000-$20,000 2017: $10,000-$20,000 Total: $20,000-$30,000 | $15,000 requested | Potential gap of $5,000 per year, tie in with CB Program Outreach, newly hired Public Affairs staff member will be working on updates for the NYS FSA website
Database Development | Create database of ownership, land use, previous contacts, etc. for potential participants | NYS FSA/USC | New York | 2017-12-01 | N/A | N/A
Management Approach 5: Improve Establishment/Maintenance/Verification
Improve tracking and reporting | Utilize GIS, CAST, and other tools | State Leads | Baywide | 2017-12-01
| Analyze efficiencies and quantify benefits of RFB | FSA, USFS, ARS, PennState | Baywide | 2017-12-01
| Track progress through reports and maps | DEP, DCNR | Baywide | 2016-12-31
Strengthen inter-organizational operations, including reporting and verification | Enable verification to be completed by multiple entities, independent of landowner/installer | EPA, DEP, DCNR, Partners | Baywide | 2016-12-31
Evaluate State RFB Verification Protocol | Discuss with states how verification is working | USFS | Baywide | 2017-12-01
Work with FSA to see about increasing annual maintenance payments | annual maintenance payments from $5/acre to $10/acre | State leads, ACB, USFS | Baywide | 2016-12-01
Work with FSA to see about increasing establishment period | Expand the RFB establishment period from 2 years to 3-4 years | State Lead | Baywide | 2017-12-01
Determine level of invasive plant control cost-share that is part of extended establishment | CRP/CREP cost share available for herbaceous treatements during cover establishment to ensure survival of trees planted in riparian forest buffer | State, FSA | Baywide | 2016-12-01
Evaluation of Buffer Effectiveness/Tree Planting Success | Complete evaluation of tree planting mortality/success for three years after initial planting and secure additional planting stock to correct planting failures | State lead | Baywide | 2017-12-01 |  |  | start or continuation of evaluations for verification and process improvement
Management Approach 6: Improve Re-enrollment
Provide targeted outreach to CREP participants in the last 1-2 years of contract | Send postcards to expiring contract holders and follow-up with phone calls | FS, State FSA, ACB | Baywide | 2017-12-01
| Provide TA/maintainance funding to help participants resolve compliance issues | USFWS | Maryland | 2017-12-01
| Encourage participants with re-enrolling RFBs to include upgrades, such as increased acres and/or alternative water, stream crossings, fencing | TSPs | Baywide | 2017-12-01
Provide contact information for expriring contract holders to State Leads | Information provided to each state annually | FSA | Baywide | 2017-12-01
Management Approach 7: Improve Targeting of RFB
Fund trials for function-based incentives | Perform work on NFWF grant | MDA | Maryland | 2017-12-01 |  |  | NFWF funded
Utilize CREP targeting tool developed by FWG | Make maps of high-priority areas for reforestation | State Leads | As needed | 2017-12-01
Target areas of high saturation | Perform work on RCPP and other grants | TNC | Maryland | 2017-12-01
Management Approach 8: Ramp-up conservation of RFB easement programs
Increase participation with the Agriculture Conservation Partnership Program (ACEP) | Determine opportunities for CREP participants to transition enrollments to NRCS ACEP easement programs | NRCS | Baywide | 2017-12-01
Improve easement language for RFB | Suggest acceptable language standards for RFB easements | FWG/Chesapeake Working Lands Workgroup | Baywide | 2016-12-01
Management Approach 9: Focus on non-ag RFB
Programs to reduce mowing | # State/County-level programs | State Leads | Baywide | 2017-12-31
Work with federal land managers to promote RFB
| Target locations through GIS analysis | Golf courses, universities, corporate campuses, schools, public lands | PA (TBD) | 2016-12-31
Pursue options for aggreagating small landowners planting and management | Prettyboy analysis; Baltimore County Example contracts | ACB, Balt Co, | Prettyboy | 2017-12-01
Coordinate with MS4 permits | Meeting to assess options, needs | SRCC | Baywide | 2017-12-01
| Develop examples of buffers & SWM | CWP | As appropriate | 2016-12-01