## HW QPM Prep
Healthy Watersheds Outcome | Ensure 100 percent of state-identified currently healthy waters and watersheds remain healthy.
Factor | Gap | Management Approach | Work Plan Action | Responsible Party | How do you track whether action is complete | Expected Response | Lessons Learned | Adaptations Made or Recommended | Critical Action (Indicate with an X)
Scientific and Technical Understanding: Knowledge and information about healthy watersheds is critical to determining where healthy watersheds are located, which healthy watersheds are vulnerable to degradation, how the status of healthy watersheds is changing over time and whether our work is effectively sustaining their health. | The bulk of activity regarding the collection and use of watershed condition information has been used to characterize impaired watersheds for restoration, rather than identify and protect healthy watersheds. There is a lack of information for assessing “health” as opposed to “degradation,” and the routine collection of information about the status of healthy waters and watersheds is often lacking. Further, widespread assessments of healthy watershed vulnerability (which can identify various tiers of risk) are not available, and private sector resources to identify and protect watersheds are scarce overall, especially in undeveloped rural areas where healthy watersheds may be found. Healthy watershed protection programs would benefit from some knowledge regarding the type and relative effectiveness of existing safeguards. | Management Approach (1.1): Compile an inventory of healthy waters and watersheds | PA, MD, DC, NY all have actions by jurisdiction related to continued identification, assessment, and monitoring of healthy watersheds | Jurisdictions and CBP GIS team | Healthy watersheds are added as needed | Updated dataset and map of healthy watersheds as available | Jurisdiction updates and capacity to provide updates is inconsistent | It was decided that while new healthy watersheds can be added, none will be taken away.
|  | Management Approach (1.2): Develop watershed vulnerability information | WP Action (1.2.1): Develop and implement a methodology to establish climate-related baselines and targets for the Healthy Watersheds Outcome | Climate Resiliency Workgroup
|  |  | WP Action (1.2.2): Forecast land development scenarios to help jurisdictions assess healthy watershed vulnerability and develop strategies for healthy watershed protection | CBP GIS Team | The GIT Coordinator is also on the CBP GIS Team. Once the forecast land development scenarios are complete later in 2017 we will begin to incorporate the results accross Goal Teams | Understand which healthy watersheds are most vulnerable to land use conversion. |  | What is the best pathway to share this information with relevant locals in a potentially "vulernable" healthy watershed?
|  |  | WP Action (1.2.4): Compile information related to the vulnerability of healthy waters and watersheds, especially in relation to energy development, land conversion, sea level rise, storm surges and overall climate resiliency | GIT4, The Nature Conservancy
|  |  | WP Action (1.2.5) Incorporate Resource Conservation Opportunity Areas | USFWS, Maintain Healthy Watersheds GIT, and CBPO GIS Team | This dataset has been incorporated into the Cross GIT mapping effort | This layer will be used with other priority areas to help tease out where areas of highest conservation priorities exist across GITs
|  | Management Approach (1.3): Prioritize the protection of healthy watersheds | WP Action (1.3.1): Assess the protected status of healthy watersheds. | GIT4 | We have a map of "protected" healhty watersheds | We can use the "unprotected" healhty watersheds for conservation targeting, for example | Protected lands are not the only indicator of watershed protection. | Determine as a goal team what constitutes "protected" in addition to land protection.
|  |  | WP Action (1.3.2): Compile and publish a biannual Chesapeake Bay Protected Lands Dataset and overlay this dataset with healthy watershed and other conservation goals | CBP GIS Team | The indicator can be found here
|  |  | WP Action (1.3.3): Prioritize protection for healthy waters and watersheds in Maryland | MD and CBP
|  | Management Approach (1.4): Maintain and expand assessment activities and information | WP Action (1.4.1): Determine current and future monitoring gaps and needs | STAR | We have held preliminary meetings with STAR and obtained feedback on progress and recommendations on next steps. We are actively working toward tracking vulnerability of healthy watersheds for the region.
|  |  | WP Action (1.4.2): Form a workgroup to develop metrics for healthy watersheds, protocol for determining the status of watersheds in successive years, methods to track marginally healthy waters and watersheds, and assessments of watershed protection priorities | GIT4 | This workgroup is dissolved are are working with a core GIT leadership team and other CBP partners to develop an assesment methodology, this task is not dead but has gone a different direction |  |  | Adapt the EPA Preliminary Healthy Watershed assessment tool for custimized use in the CBW. | X
|  |  | WP Action (1.4.3): In Pennsylvania, refine the Landscape Conservation Design process by identifying additional model inputs and testing the information against the ability of land and resource managers to use and incorporate data into their program-related decision-making | EPA
|  |  | WP Action (1.4.4): Review high-resolution imagery assessment results to determine how to incorporate them into the assessment of healthy watersheds | GIT4 | It is unclear how the imagery and associated land use datasets will be used for outcome information and development. |  | Guidance is needed on how to use this information to meet multiple management questions.
|  |  | WP Action (1.4.5): Tracking forest cover and forest gain or loss | USFS
|  |  | WP Action (1.4.6): Identify high-value brook trout habitat to conserve and marginal brook trout habitat in need of restoration | CBP GIS Team
|  |  | WP Action (1.4.7): Use land cover datasets and healthy watershed inventories to conduct the Chesapeake Bay Comprehensive Water Resources and Restoration Plan, which will identify opportunities for ecosystem restoration or the completion of other U.S. Army Corps of Engineers mission areas | USACE
|  |  | WP Action (1.4.8): Expand assessment activities and available information related to forests and forest conservation | Forestry Workgroup
|  |  | WP Action (1.4.9): In the District of Columbia, conduct an Environmental Assessment in the Fort Dupont watershed that will determine baseline conditions, examine the feasibility of wetland restoration, investigate the impact of targeted stream restoration and explore opportunities to implement low-impact development activities in the public right of way | DC
|  |  | WP Action (1.4.10): In Maryland, develop a long-term strategy for the sustainable monitoring of existing healthy watersheds, expand stream monitoring in order to identify new healthy watersheds and integrate relevant monitoring data into the Chesapeake Bay Program’s tracking framework | MD
|  |  | WP Action (1.4.11): In Pennsylvania, maintain and expand healthy watersheds assessment activities and track the Managing Communities metric to evaluate how municipalities use forest protection ordinances and forest management planning to protect their forested watersheds | PA
Scientific and Technical Understanding/Local Government Agency and Nongovernmental Organization Engagement: Those who are making and influencing land use decisions need the best information available on healthy watersheds in order to determine where healthy watersheds are located, which healthy watersheds are vulnerable to degradation, how the status of healthy watersheds is changing over time and whether our work is effectively sustaining their health. | The status and importance of healthy watersheds are not being conveyed to local government decision makers and other organizations and entities across watershed jurisdictions. As a result, these local managers are not aware of the resources that are available nor what types of protective measures are needed to protect those resources. While some level of protection prioritization may exist within agencies and private sector organizations, the details are not clear, and the information may not be readily accessible or available to external parties. Further, the array of protective measures available vary across and within states, and while the potential tools for protection are numerous, they are not infinite: a list of such tools and where they are available can be assembled. | Management Approach (2): Strengthen local commitments and capacity to protect healthy watersheds | WP Action (2.1): Improve strategies to convey information on the status of healthy watersheds to local stakeholders (which can include federal and state agencies, local governments, nongovernmental organizations, agricultural producers, community leaders and youth) | GIT4
|  |  | WP Action (2.1.2): In the District of Columbia, give presentations on watershed protection at community meetings and events | DC
|  |  | WP Action (2.1.3): In the District of Columbia, work with schools on watershed restoration education and implementation projects | DC
|  |  | WP Action (2.1.4): In Maryland, work with nongovernmental organizations to coordinate watershed protection and communication efforts | MD
|  |  | WP Action (2.1.6): In Maryland, develop and implement communications and outreach strategies to encourage communities to support the integration of healthy watershed protection into local comprehensive plans and the direction of some large-scale pollution mitigation activities toward watersheds that contain healthy sub-watersheds | MD
|  |  | WP Action (2.1.8): In Pennsylvania, use state and national Environmental Education Curriculums (e.g., Project WET, Watershed Education and PA Land Choices) to train educators and community leaders about sustainable land use, clean water and watershed protection | PA
|  |  | WP Action (2.2): Identify the tools that may be used (primarily by local governments) to protect healthy watersheds | GIT4
|  |  | WP Action (2.2.2): In Maryland, finalize and implement guidance on protecting healthy watersheds and explore the necessity for updating anti-degradation regulations | MD
|  |  | WP Action (2.2.3): In Maryland, incorporate healthy watershed protection into a multi-agency tool used to target environmental protection and restoration efforts | MD
|  |  | WP Action (2.2.4): In Maryland, consider healthy watershed protection as a factor in growth offset policies | MD
|  |  | WP Action (2.2.5): In Pennsylvania, support local green space protection by incorporating conservation methods into planning efforts | PA
|  |  | WP Action (2.2.6): Healthy Watersheds TMDL Pilot Project Forestland Retention Study (Rappahanock River Basin) - Phase 2 | VA and PA
|  |  | WP Action (2.3.1): Use U.S. Fish and Wildlife Service grant programs to leverage non-federal funds to support healthy watersheds | USFWS
|  |  | WP Action (2.3.2): In Maryland, consider healthy watershed protection in the awarding of federal and state water quality grants | MD
|  |  | WP Action (2.3.3): In Pennsylvania, work with counties and municipalities to prioritize the use of open space funding to protect healthy watersheds | PA
|  |  | WP Action (2.3.5): In Pennsylvania, establish a Healthy Watersheds Initiative as a category in Growing Greener (Environmental Stewardship) funding | PA
Federal, State and Local Government Agency Engagement: Those who can take action to ensure the protection of healthy watersheds need scientific, technical and policy tools to do so | The usage of existing scientific, technical and policy tools is not universal, even within states. Furthermore, some tools are underdeveloped, poorly supported, and unsuited for widespread sharing and/or integration. Needs include: the creation of a forum for mutual learning and exploration of scientific and management issues; the further development of information resources; and the promotion of the science that supports better characterization and protection of healthy watersheds. Outreach and education will be needed to inform local governments, planning district commissions and watershed organizations of the resources and tools available, and of how they might be applied locally. | Management Approach (3.1): Leverage funding to support federal and state efforts to protect healthy watersheds Improving communication among federal agencies to encourage them to protect healthy watersheds | WP Action (3.1.2): In the District of Columbia, secure watershed protection grants | DC
|  |  | WP Action (3.1.3): In Pennsylvania, work with the Natural Resources Conservation Service to prioritize Farm Bill funding to benefit forested watershed lands | PA
|  | Management Approach (3.2): Implement new or improve existing policy, programs and research | WP Action (3.2.1): Reinstitute the Mid-Atlantic Highlands Action Program | USFWS and EPA
|  |  | WP Action (3.2.2): Integrate healthy watershed protection into U.S. Environmental Protection Agency water programs | EPA
|  |  | WP Action (3.2.3): Share information on the U.S. Environmental Protection Agency Healthy Watersheds Consortium Grant and annual opportunities to submit proposals for related sub-grants. | EPA
|  |  | WP Action (3.2.4): Engage federal agencies outside of the U.S. Environmental Protection Agency (e.g., the Federal Energy Regulatory Commission, the U.S. Department of Transportation) to leverage opportunities for states and local governments to further healthy watershed protection | GIT4
|  |  | WP Action (3.2.5): Continue to manage U.S. Army Corps of Engineers reservoirs and recreational facilities to protect, preserve and restore significant ecological resources | USACE
|  |  | WP Action (3.2.?): In the District of Columbia, use the Riversmart Homes Program to implement projects and teach homeowners to reduce stormwater runoff and increase tree canopy on private properties | DC
|  |  | WP Action (3.2.?): In the District of Columbia, use street and other public property plantings to increase urban tree canopy | DC
|  |  | WP Action (3.2.?): In the District of Columbia, maximize low-impact development retrofits in targeted public spaces | DC
|  |  | WP Action (3.2.?): In New York, purchase and protect land through the Open Space Conservation Plan | NY
|  |  | WP Action (3.2.?): In New York, address the potential environmental impacts of dairy farms that have less than 300 cows and further address the potential environmental impacts of small and medium dairies by providing partial funding to certain engineering services related to the development of best management practices through the Dairy Comprehensive Nutrient Management Plan | NY
|  |  | WP Action (3.2.?): In Pennsylvania, explore the implementation of a statewide Forest Conservation Easement Program to protect healthy watersheds with funding for clean water or safe drinking water | PA
|  |  | WP Action (3.2.?): In Pennsylvania, establish a Pennsylvania Riparian Forest Buffer Leadership Team | PA
|  |  | WP Action (3.2.?): In Pennsylvania, use the Stream ReLeaf program to track riparian forest buffer implementation and expand knowledge and access to the Stream ReLeaf system in order to capture all existing riparian forest buffers | PA
|  | Management Approach (4): Supporting state-based efforts to improve the identification, assessment, monitoring and protection of healthy watersheds | WP Action (4.1): Provide a forum for mutual learning and exploration related to healthy watersheds | GIT4
|  |  | WP Action (4.1.3): In DC, host a Youth Fair for Environmental Education | DC
|  |  | WP Action (4.1.5): In PA, hold a PA Riparian Forest Buffer Summit including all interested PA Bay stakeholders, led by the Riparian Forest Buffer leadership team | PA
|  |  | WP Action (4.2): Develop informational resources for state agencies and support state agency communications related to healthy watersheds | GIT4
|  |  | WP Action (4.2.3): In DC, develop a RiverSmart Homes Flyer Distribution | DC
|  |  | WP Action (4.2.5): In Pennsylvania, develop a public outreach strategy that considers landowner interests and values and encourages participation | PA
|  |  | WP Action (4.3.1): Promote the science: Quantify and incorporate conservation practices into the Chesapeake Bay Program’s modeling efforts and explore how land use protections might be used to quantify pollution load reduction incentives for land conservation | GIT4
Population Growth: Human-influenced land use change (i.e., the amount, type and way in which land use change occurs) | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Biota: Invasive species | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Habitat Condition: Habitat fragmentation | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Habitat condition: Stream flow | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Habitat condition: Stream channel stability | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Habitat Condition: Air deposition | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified
Climate Change | No specifically identified gap(s) correspond(s) to this Factor | No approach or action identified