## description
Phase 7 Task list 4/25/2022
Each item will have these parts: | Categories
1. What – short description | variable scale modeling
2. Why – who asked for it or why is it necessary | physical process
3. Who in CBPO or elsewhere will do the work | nutrient application
4. Where in the CBP organizational chart do the decisions lie | climate change
5. When does this need to be done, including general dependencies | General
6. How: A very short description with a link to the longer documentation | Uncertainty Quantification
High-Res Land Use
Main bay and tributary models

## task list
Item | Category | What: short description | Why: who asked for it or why is it necessary | Who in CBPO or elsewhere will do the work | Where in the CBP organizational chart do the decisions lie | When does this need to be done, including general dependencies and development time | How: A very short description with a link to the longer documentation
1 | General | Develop CalCAST. CalCAST will be a tool for comparing estimated load to monitored loads given a set of inputs and parameters. It will be used in the calibration | CalCAST allows the CBP to test various data sets and strategies to see which match monitoring data best. Primary suggestion of STAC Phase 6 STAC review and Future of Modeling workshop. Allows efficient incoporation of all other development priorities | Bertani; Bhatt; Shenk | MWG | First priority. The rest of development depends on CalCAST. | A model of loads at a point is developed in Section 12 of the documentation. It will be implemented for speed of calculation with the potential to wrap parameter estimation techiques around it
2 | variable scale modeling | Discuss scale and reach decision | Development of various Phase 7 tasks will benefit from knowledge of the output scale | Shenk | WQGIT, MWG | 2022-2025 | Presentation to WQGIT and MWG on various aspects, discussed in section 2
3 | General | determine official versions of GIS layers: NHD, county, shoreline, Lrseg | Counties have updated boundaries. NHD necessary to use many important data sets, shoreline determines watershed/estuarine parameters. Lrseg may change for NHD boundaries | McDonald, Fitch, Ahmed, Bhatt | MWG | early 2022 | CBPO discussions, with results to be written into section 2
4 | Main bay and tributary models | physical and chemical linkage with estuarine model | Needed to run estuarine models | Bhatt | MWG | late 2022. Need to determine form of dynamic model first for the variable description. | Section 2 of P7 documentation. Indentify set of terminal segments. Identify estuarine cell for each terminal segment. Compare old ICM variables with new ICM variables. Do new WSM variables match up?
5 | General | system to update meteorology data annually | Need most recent data. Annual updates are a frequent request of academic partners and needed for new total loads indicator | Bhatt | MWG | early 2022 | Update from NLDAS2 data set. Create auto-downloads system. Leave it native scale and aggregate as needed
6 | physical process | stream data: Streamflow | Needed for calCAST hydrology and dynamic model | Bhatt | MWG, ITAT | early 2022, and again in 2024 | EGRET. Also send data request to states
7 | physical process | stream data: concentration | Needed for dynamic model. Important issue for states and local govts | Gunnerson; Bhatt | MWG, ITAT | early 2022, and again in 2024 | Section 3.6. Gather from James Colgin; request from States; QA
8 | physical process | Stream data: Load estimates | Basic data for calibration of CalCAST | Zhang | MWG, ITAT | early 2022, and again in 2024 | WRTDS through EGRET
9 | nutrient application | Bring back Ag Modeling Subcommittee | WQGIT continues to bring back issue related to agricultural inputs. Unexpected results continue to occur | Butler, Collins | AgWG | Early 2022, continuing until 2025 | Identify chair, coordinator, and members; Section 4 on terrestrial inputs will be the starting point
10 | nutrient application | Consider revising the types of ag land uses simulated in the model | the number of ag classes contributes to the complexity of the nutrient spread routines | Butler | AMS | Early 2022, continuing until 2025 | Consider how BMPs are spread on different land uses and if application and loading differences are significant
11 | nutrient application | Manure nutrient generation | discussions have continuted in the AgWG and WQGIT about manure issues | Butler | AMS | Early 2022, continuing until 2025 | Revisit 'Manure Nutrient Inputs' in Section 4. See STAC nutrient inputs review (yagow et al 2016)
12 | nutrient application | fixation | Issues with soybean fixation have been rasied in the WQGIT | Butler | AMS | Early 2022, continuing until 2025 | Revisit 'Legume Fixation in Section 4
13 | nutrient application | Crop application goals | WQGIT is interested in nutrient use efficiency | Butler | AMS | Early 2022, continuing until 2025 | Revisit 'Crop Application Goals' in section 4
14 | nutrient application | Manure distribution on Crops | complex distribution scheme has lead to results that are difficult to explain | Butler | AMS | Early 2022, continuing until 2025 | Revisit 'Distributing Manure and Biosolids applications' in Section 4. reconceptualization may be warranted
15 | nutrient application | Inorganic applications | complex distribution scheme has lead to results that are difficult to explain | Butler | AMS | Early 2022, continuing until 2025 | Revisit 'Distributing fertilizer applications' in Section 4. reconceptualization may be warranted
16 | nutrient application | Urban Fertilizer applications | Urban fertilizer | Butler; Sweeney | USWG | Early 2022, continuing until 2025 | Revisit 'Urban fertlizer applications' in section 4. Look for new sources of data
17 | nutrient application | soil P data | Management board directed AgWG to gather and assess soil P data | Butler; Bertani | AMS | Early 2022, continuing until 2025 | Refer to MB decision document
18 | nutrient application | soil P model | Management board directed AgWG to gather and assess soil P data | Butler; Bertani | AMS | Early 2022, continuing until 2025 | Refer to MB decision document
19 | nutrient application | New atmospheric deposition data | Additional years of data and new CMAQ model available | Bhatt | MWG | Can be any time 2023-2025 | Consider NADP, CASTNET, CMAQ. Get an accurate trend through time
20 | physical process | Review relative loading rates by land use | Important parameters in the model that were determined by sector workgroups. Asking if update are needed | Collins, Butler, S. Claggett, Wood | AgWG, AMS, FWG, USWG | Impacts land use decisions, 2022-2023 | If satisfied with current parameters, these can stay. Potentially update with new literature. Section 5.
21 | physical process | Review relative loading rates by land class | Important parameters in the model that were determined by modeling workgroup. Asking if updates are needed | Bertani | MWG | Can be any time 2023-2025 | review any additional literature and models. Potentially estimate though CalCAST
22 | physical process | Review of sensitivities | Sensitivity to legume fixation and crop uptake has contributed to CAST results that do not match with partners expecations. | Bertani | MWG | Can be any time 2023-2025 | Literature review, section 6. General reivew of all sensitivities
23 | climate change | Review of sensitivities to climate variables | Additional sensitivities not in Phase 6 CAST were added to account for climate. These should be integrated with the rest of the sensitiviteis | Bertani; TBD | MWG | Can be any time 2023-2025 | Literature review; pull some of the section 15 sensitivities into section 6
24 | High-Res Land Use | Convert fine-scale land use to CAST land use | Not all land uses identified by the partners can be mapped. Mapped land use classes must be split into CAST classes | P Claggett, Bhatt, Devereux, Collins, Wood | MWG; LUWG; WQGIT; AgWG; FWG; USWG | land use available in 2024. Need in 2025. discussions can precede | Determine methodology to be used and final set of land uses in Phase 7 CAST; section 7
25 | General | BMP updates | Need to make sure that BMPs are carried forward | Devereux; Van Note; Hanson | WQGIT | ongoing | update section 8 of documentation as necessary. Some BMPs may require slightly different handling in P7
26 | Uncertainty Quantification | Inverse Uncertainty quantification | STAC and WQGIT have asked for this analysis | Bertani | MWG, WQGIT | initial completion in 2022; use in calibration and additional report in 2025 | Use inverse method to determine where and when model is best predicting trends in monitoring data; section 16
27 | physical process | Investigate land to water factors | new research and techniques available to map tranmissability of landscape; These could change for climate as well. STAC asked for updates in P6 review | Bhatt; Bertani; Gunnerson; TBD | MWG | Can be any time 2023-2025; geomorphometry data available 2023 | Research has identified ponds, ditches, and other landscape features as potentially important transport mediators; section 9
28 | physical process | Incorporate local data in land to water factors | Municipalities in VA and PA have collected data in developed areas that will be useful to the P7 calibration | Bertani; Bhatt; Gunnerson; Jastram | MWG; USWG | can be any time 2023-2025 | Compare loads from various area and generalize to developed lands for CB watershed
29 | General | Investigate tidal flooding loads | New research shows large loads from tidal flooding | TBD; Bertani; Wood | MWG; USWG | can be any time 2023-2025 | Margie Mulholland has significant research showing large NH3 loads
30 | General | Update to Wastewater Loads | some missing loads in P6 wastewater for drinking water flushing and cooling tower heat | Thygne; Pickford; Bertani | WWTWG | can be any time 2023-2025 | section 10; make sure all loads are accounted for
31 | General | Update to CSOs | CSO data only through 2015 and not using the same rainfall data as WSM | Bertani | WWTWG | can be any time 2023-2025 | Section 10: Start with tetratech model and convert to CBP rainfall; fix low values
32 | physical process | Tidal Shoreline loads | New estuarine model may need more precise shoreline load estimates. Boat Wake STAC review should be considered | TBD | MWG | 2022-2023 for the estuarine model | section 10: use new shoreline coverage and other information. STAC review Bilkovic et al 2017
33 | physical process | Stream to Bay factors | New high res information and floodplain measurements available | Bhatt; Bertani; Gunnerson; TBD | MWG | any time after geomorphometry data 2024-2025 | Section 11 contains suggestions related to high res data, CDFN, several STAC workshops
34 | physical process | Reservoir consideration | Important for temperature and hydrology | DEQ; ICPRB; SRBC | MWG | can be any time 2023-2025 | Section 11. See Appling work in DRB. Directly incorporate existing reservoir models from partners
35 | General | Dynamic model for hydrology, sediment, and temperature | Needed for main bay and tributary models and for some co-benefits | Bhatt | MWG | 2022 | Section 13. Likely follow same HSPF simulation as P6, but at the NHD scale. Calibration targets for surface flow, baseflow, and sediment from CalCAST
36 | Main bay and tributary models | Dynamic model for nutrients | Needed for main bay and tributary models and for some co-benefits | Bhatt | MWG | 2022 | Section 13. calibrated to calCAST. several options available; HSPF, LSTM, simple routing
37 | physical process | Lower Susquehanna Simulation | STAC has pointed out additional research since 2017 Conowingo decision | Bhatt | MWG | can be any time 2023-2025 | incorporate new information on bioavailalbility and C/Q relationships. Section 14
38 | climate change | Produce 2035 meteorology data sets | Necessary for climate assessment | Bhatt | MWG, CRWG | later will give more information on trends; 2026 | Consider feedback on delta method from CHAMP and STAC
39 | climate change | Investigate CAST sensitivities to climate | Necessary for climate assessment | Bhatt; Bertani; Gunnerson; TBD | MWG, CRWG | 2026 | Starting with section 15, go over each section an analyze for upotential updates
40 | physical process | Add solar fields as land use in developed land class | Solar fields are increasing land use in the CBW | Wood, Bertani | USWG | Initial parameters needed in 2022, but new research is likely by 2025 | Literature review to assign appropriate relative loading rates and sensitivities. Investigate if any BMPs.
41 | physical process | recalculate EOS sediment | New data available | P Claggett; Ahmen; McDonald | MWG | can be any time after land use done; 2024-2025 | use new land use, and geomorph data will make for a better calculation of RUSLE and IC
42 | General | transfer calCAST values to CAST | update CAST to P7 values | Devereux; Bertani; Bhatt | MWG | end of 2025 for 2026 review | Incorporate new parameters into CAST and verify code
43 | General | Point source location checks | VA has shown that some of the P6 point sources did not have correct locations of the outfalls and did not get assigned appropriate S2R factors | TBD; Fitch; Thygne | WWTWG | Can be any time 2023-2025 | Section 10; work with WWTWG to get the best data sources. Golomoski presentations from 2022
Note on H11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Rewording for this might be something like: re-examine the land use categories that will be used in Phase 7 and determine how to apply BMPs to altered land use categories

## Phase 7 Watershed for WQGIT
| 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Phase 7 Activity | Work plan |  |  | Build | Work plan | Build Models |  |  | Work plan | Build Models |  |  | Work plan | Build Models |  |  | Review Models |  |  |  | Apply | [5 empty] | Track
General | 1 Develop CalCAST using P6 data |  |  |  | 1 Use CalCAST as primary calibration tool
3 Determine official CBPO GIS layers
5 system of annual meteorology updates
25 BMP updates
35 Dynamic model for hydrology, sediment, and temperature
29 Investigate tidal flooding loads
30 Update to Wastewater Loads
43 point source locations
42 CalCAST transfer to CAST
31 Update to CSOs
Variable Scale Modeling | [12 empty] | 2 Partnership decision on Scales
Nutrient application Calculation | 9 Restart AMS |  | Update nutrient inputs
10 Determine Ag Land Uses
11 manure generation
12 fixation
13 crop application goals
14 Manure distribution
15 inorganic distribution
17 Soil P data
18 Soil P Model
16 Urban fertilizer
19 Atmospheric deposition
Physical Process Simulation | 6 Streamflow data
7 stream conc data
8 Stream load data
20 Review relative loading rates by land use
21 Review relative loading rates by land class
40 Add solar fields as land use in developed land class
22 Review of sensitivities
27 Investigate land to water factors
28 Incorporate local data in land to water factors
32 Tidal Shoreline loads
34 Reservoir consideration
37 Lower Susquehanna Simulation
41 Recalculate RUSLE and IC
33 Stream to Bay factors
Uncertainty Quantification | 26 Methods |  |  |  | 26 Parameters | [8 empty] | 26 Use in review
Improve climate change modeling | [8 empty] | 23 Review of sensitivities to climate variables
38 Produce 2035 meteorology data sets
39 Investigate CAST sensitivities to climate
Main Bay and Tributary Models |  |  | 4 physical and chemical linkage with estuarine model
36 Dynamic model for nutrients
High-Res Land Use | [8 empty] | 24 Convert fine-scale land use to CAST land use

## Phase 7 Watershed for WQGIT (2)
| 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Phase 7 Activity | Work plan |  |  | Build | Work plan | Build Models |  |  | Work plan | Build Models |  |  | Work plan | Build Models |  |  | Review Models |  |  |  | Apply | [5 empty] | Track
General | 1 Develop CalCAST using P6 data
3 Determine official CBPO GIS layers
5 system of annual meteorology updates
35 Dynamic model for hydrology, sediment, and temperature
36 Dynamic model for nutrients
Physical Process Simulation | 6 Streamflow data
7 stream conc data
8 Stream load data
Uncertainty Quantification | 26 Methods

## Phase 7 Watershed for WQGIT (3)
| 2022 | 2022 | 2022 | 2022 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2027 | 2027 | 2027 | 2027 | 2028 | 2028 | 2028 | 2028 | 2029 | 2029 | 2029 | 2029
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Phase 7 Activity | Work plan |  |  | Build | Work plan | Build Models |  |  | Work plan | Build Models |  |  | Work plan | Build Models |  |  | Review Models |  |  |  | Apply | [5 empty] | Track
General | Build Model Structure |  |  |  | Improve Models | [11 empty] | Review Models