## Total
Conowingo Watershed Implementation Plan - Nutrient Reduction and Pay for Performance Contracts
State | Annual Nutrient Reduction (lbs TN) | Total Cost (Annual) | $/lb TN Reduced | Total Investment to date
Pennsylvania | 89684.98 | 1399167.323 | 15.6009 | 31491324.46
Maryland | 164549.7757 | 1822423.3887 | 11.0752 | 13572882.72
New York | 2457 | 44333.15 | 18.0436 | 221665.75
TOTAL | 256691.7557 | 3265923.8617 | 12.7231 | 45285872.93
GOAL (lbs TN reduced annually) | 6000000
PERCENTAGE MET | 4.278%
Total investment to date includes Program Administrative costs
Update Date | 2026-05-11

## Detail
Conowingo Watershed Implementation Plan - Nutrient Reduction and Pay for Performance Contracts | [12 empty] | Best Management Practices
[13 empty] | Nutrient Management Nitrogen | Crop and Soil Management (Conservation Tillage, Alternative Crops) | Prescribed Grazing | Forest Buffers | Wetland Restoration - Headwaters | Wetland Restoration - Floodplain | Grass Buffers | Soil and Water Conservation Plan | Manure Incorporation | Manure Injection | Barnyard Runoff Control | Stream Restoration
Pennsylvania - administered by PADEP and PENNVEST
|  |  |  | Nutrient Reduction (total project) |  |  | Nutrient Reduction (per year) |  |  | Cost
Awardee | Project Description | Project Status | Contract Period (years) | lb TN | lb TP | lb TSS | lb TN | lb TP | lb TSS | Contract Costs (Total) | Contract Cost (Annualized) | $/lb TN Annualized
Chesapeake Conservancy, Inc. | Beef and Poultry Farm BMPs | Implementation complete | 20 | 18606.4 | 2726.2 | 70986.6 | 930.32 | 136.31 | 3549.33 | 185338.35 | 9266.9175 | 9.961 | [10 empty] | ✓
HGS, LLC | Wetland and Stream Restoration and Riparian Plantings in York County | Implementation complete | 20 | 4520 | 780 | 5841888 | 226 | 39 | 292094.4 | 675016.8 | 33750.84 | 149.34 | [5 empty] | ✓ | ✓
HGS, LLC | Wetland and Riparian Grass Buffers Restoration Conowingo Creek | Implementation complete | 20 | 588779 | 92180 | 2127240 | 29438.95 | 4609 | 106362 | 5869832.24 | 293491.612 | 9.9695 | [5 empty] | ✓ | ✓
Herbert, Rowland, & Grubic, Inc. | Dairy and Beef Farm BMPs (2 sites) | Implementation complete | 20 | 54060 | 10620 | 163760 | 2703 | 531 | 8188 | 2195998.29 | 109799.9145 | 40.6215 | [10 empty] | ✓
HGS, LLC | Wetland Restoration in Adams County | Implementation complete | 20 | 392344.8 | 98712.8 | 55415952.8 | 19617.24 | 4935.64 | 2770797.64 | 7458474.65 | 372923.7325 | 19.01 |  |  |  |  | ✓ |  | ✓
HGS, LLC | Wetland Restoration and Riparian Buffer Fencing in York County | Implementation complete | 20 | 173028.8 | 13638.2 | 7662655.8 | 8651.44 | 681.91 | 383132.79 | 4349944.03 | 217497.2015 | 25.14 | [5 empty] | ✓ | ✓
Lancaster Farmland Trust | Dairy and Sheep Farm Stormwater Management BMPs (2 sites) | Design | 20 | 180666 | 28636.2 | 3106825 | 9033.3 | 1431.81 | 155341.25 | 1248763.39 | 62438.1695 | 6.912 | [10 empty] | ✓
HGS, LLC | Wetland re-establishment, wetland restoration, pasture fencing, and forested buffers (2 sites) | Design | 20 | 131372.6 | 23118.4 | 420645.6 | 6568.63 | 1155.92 | 21032.28 | 4237883.02 | 211894.151 | 32.2585 |  |  |  |  | ✓ | ✓
Conservation Innovation Fund | Alternative Crops for Environmental Benefits | Construction | 20 | 105905.43 | 8793 | 4407405 | 11767.27 | 977.02 | 489711.68 | 1663774.31 | 83188.7155 | 7.0695
Keystone Streams, LLC | Keystone Streams Rohrer Farm Riparian Forest Buffer | Implementation complete | 20 | 14976.6 | 1207.6 | 8614326.2 | 748.83 | 60.38 | 430716.31 | 98321.38 | 4916.069 | 6.565 |  |  |  | ✓
Chester County | LGI Investments - various projects | Planning/Design | [7 empty] | 3507978 |  |  | ✓ |  | ✓
ADMINISTRATIVE (currently no administrative has been used, although PENNVEST is allowed up to 4%) | [9 empty] | 0
TOTAL |  |  |  | 1664259.63 | 280412.4 | 87831685 | 89684.98 | 14557.99 | 4660925.68 | 31491324.46 | 1399167.323 | 15.6009
Maryland - administered by MDE and Susquehanna River Basin Commission (SRBC)
|  |  |  | Nutrient Reduction (total project) |  |  | Nutrient Reduction (per year) |  |  | Cost
Awardee | Project Description | Project Status | Contract Period (years) | lb TN | lb TP | lb TSS | lb TN | lb TP | lb TSS | Contract Costs (Total) | Contract Cost (Annualized) | $/lb TN Annualized
HGS, LLC | Precision Nutrient Management | Year 1 complete | 4 | 135553.8 | - | - | 33888.45 | - | - | 2033307 | 508326.75 | 15 | ✓
Alliance for the Chesapeake | Forest Riparian Buffers and Land Use Conversion | Planning/Design | 15 | 34993.45 | - | - | 2332.8967 | - | - | 664175.68 | 44278.3787 | 18.98 |  |  |  | ✓
Rosetree Consulting, LLC | Precision Nutrient Management | Year 1 complete | 4 | 493164 | - | - | 123291 | - | - | 2889941.04 | 722485.26 | 5.86 | ✓
Keystone Stream, LLC | Forest Riparian Buffers | Implementation complete | 20 | 25742.58 | - | - | 1287.129 | - | - | 1274258 | 63712.9 | 49.5 |  |  |  | ✓
Ecotone, LLC | Stream Restoration (2 Projects) | Planning/Design | 10 | 37503 | - | - | 3750.3 | - | - | 4836201 | 483620.1 | 128.955 | [11 empty] | ✓
ADMINISTRATIVE (7.5%) | [9 empty] | 1875000
TOTAL |  |  |  | 726956.83 | 0 | 0 | 164549.7757 | 0 | 0 | 13572882.72 | 1822423.3887 | 11.0752
New York - administered by NY DEP and Upper Susquehanna Coalition
|  |  |  | Nutrient Reduction (total project) |  |  | Nutrient Reduction (per year) |  |  | Cost
Awardee | Project Description | Project Status | Contract Period (years) | lb TN | lb TP | lb TSS | lb TN | lb TP | lb TSS | Contract Costs (Total) | Contract Cost (Annualized) | $/lb TN Annualized
Upper Susquehanna Coalition | Natural filters and sustainable farm practices | Planning/Design | 5 |  |  |  | 2457 | 221 | 82577 | 221665.75 | 44333.15 | 18.0436 | ✓ |  | ✓ | ✓
ADMINISTRATIVE | [9 empty] | 0
TOTAL |  |  |  | 0 |  |  | 2457 |  |  | 221665.75 | 44333.15 | 18.0436