**Management Strategy Timeline for Public Release**

**Jan. 30** – Revised management strategy posters uploaded to the CBP website

**Feb. 2** –MB and Advisory Committee deadline for providing comments on preliminary drafts (send to Greg Barranco)

**Feb. 2**- Mar. 2 – GITs/workgroups refine draft strategies

**Mar. 2** – GITs/workgroups send revised strategies to the MB for sufficiency review

**March 6** – MB deadline for submitting fatal flaw comments to GITs/workgroups

**Mar. 16** – Post/release management strategies public input

**Apr. 20** – Public input period closes

**May 4** – GITs/workgroups revise strategies and provide to MB for final review

**June 15** – Final management strategies completed

**Dec. 15** – First Biennial workplan due