|  |  |
| --- | --- |
| **Current Schedule w/30 Day Simultaneous MB/Public Input Period** | |
| ***June 2015*** | * 30 - Final MSs completed |
| ***July*** | * TBD EC Meeting |
| ***August*** | * 13 MB call |
| ***September*** | * 17 MB meeting |
| ***October*** | * 1 - GITs: Draft workplans due * **Oct 5 – Nov. 5: 30-day public input period** (simultaneous w/MB review) * 15 – MB call |
| ***November*** | * 5 – Close public input * 5 – Nov 30 GITS – three week to review, summarize MB/public input, make edits to drafts * 12 – MB - All-day Special Session * 30– GITs send revised workplans to MB (in prep of Dec. 10 mtg.) |
| ***December*** | * 10 - MB meeting - review public comments, discuss hot issues and final workplans * Dec 10—Jan 7 - MB-4 wk review of revised drafts. |
| ***January 2016*** | * 7 – MB send comments to GITs * 14- MB meeting – fatal flaw discussion * (15 - Two-yr. WIP milestones due) * 14-21 fatal flaw review/resolve any outstanding issues * 21 – 28 Formatting   **30 - Workplans final, post on web** |