**Simplified Calendar - major milestones only**

|  |  |
| --- | --- |
| **MS Workplan Development Timeline** | |
|  |  |
| ***July***  *23* | *(Phase 1: Brainstorm initial actions)*   * EC meeting, public release of management strategies |
| ***August*** | GIT Funding: develop project proposals |
| ***September***  *7*  *TBD*  *15* | GIT Funding: final project proposals due   * GIT Chairs meeting – compare 1 early draft per GIT   GIT Funding: GIT Chairs begin prioritizing projects |
| ***October***  *9* | *(Phase 2: Matrix development, no costs/funds)*  GIT Funding: final projects submitted to CBT; sub-award process begins |
| ***November***  *2* | * GITs: Preliminary drafts due |
| ***December***  *18*  *tbd* | *(Phase 3: Costs and funding)*   * GITs: Draft workplans due to MB for 4 wk. review   GIT Funding: CBT completes sub-awards |
| ***January***  *tbd*  *15*  *22* | GIT Funding: technical leads meet with awardees to commence projects   * WQ: draft WQ programmatic milestones due   Begin 45-day public input period (Jan 22–March 8) |
| ***February****1* |  |
| ***March***  *8*  *25* | Close public input; GITs begin 2-wk. review/revision based on  comments (Mar 8-25)   * GITs: Revised drafts due to MB for April 14 meeting |
| ***April***  *15*  *22*  *30* | * WQ: final WQ milestones due (tentative) * GITs: final revisions due * **Workplans final, post on web** |
|  |  |

|  |  |
| --- | --- |
| **MS Workplan Development Timeline** | |
| ***June 2015***  *30* | * MSs final; posted on CBP website |
| ***July***  *9*  *23* | (Phase 1: Brainstorm initial actions)   * MB meeting * EC meeting, public release of management strategies |
| ***August***  *13* | * MB call |
| ***September***  *TBD*  *17*  *TBD* | * GIT Chairs meeting – compare 1 early draft per GIT * MB meeting; CAC meeting * PSC meeting |
| ***October***  *15* | (Phase 2: Matrix development, no costs/funds)   * MB call |
| ***November***  *2*  *12* | * GITs: Preliminary drafts due * MB meeting – Progress check-in |
| ***December***  *10*  *18* | (Phase 3: Costs and funding)   * MB call * GITs: Draft workplans due to MB for 4 wk. review |
| ***January***  *14*  *15*  *22* | * MB or PSC meeting – fatal flaw discussion * WQ: draft WQ programmatic milestones due * **Begin 45-day public input period** (Jan 22–March 8) |
| ***February***  *11* | * MB call |
| ***March***  *8*  *10*  *25* | * **Close public input**; GITs begin 2-wk. review/revision based on comments (Mar 8-25) * MB meeting * GITs: Revised drafts due to MB for April 14 meeting |
| ***April***  *14*  *15*  *22*  *TBD*  *30* | * MB call – discuss final changes; accept as complete * WQ: final WQ milestones due (tentative) * GITs: final revisions due * PSC call (if needed) * **Workplans final, post on web** |
|  |  |