**Timeline for Outreach to GITs - DRAFT**

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Activity** | **Jan 2016** | **Feb 2016** | **Mar 2016** | **Apr 2016** | **May 2016** | **Jun 16** | **Jul 2016** | **Aug 2016** | **Sep 2016** | **Oct 2016** | **Nov 2016** | **Dec 2016** |
| Develop questionnaire for GITs to identify local engagement needs |  |  |  |  |  |  |  |  |  |  |  |  |
| Distribute questionnaire to GIT coordinators and obtain feedback |  |  |  |  |  |  |  |  |  |  |  |  |
| Review GIT feedback and conduct follow up sessions to clarify GIT needs |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify and implement early content delivery and engagement opps. |  |  |  |  |  |  |  |  |  |  |  |  |
| Review GIT needs and conduct multi-benefits analysis (review existing CBP efforts) |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop and present to LL Workgroup recommended content and delivery mechanisms for GIT information |  |  |  |  |  |  |  |  |  |  |  |  |
| Develop and deliver content to achieve multiple benefits |  |  |  |  |  |  |  |  |  |  |  |  |

**Timeline for Outreach to State and Regional Associations - DRAFT**

|  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Activity** | **Jan 2016** | **Feb 2016** | **Mar 2016** | **April 2016** | **May 2016** | **June 2016** | **July 2016** | **August 2016** | **Sep 2016** | **Oct 2016** | **Nov 2016** | **Dec 2016** |
| Develop a list of state and regional forums of local elected officials and contacts |  |  |  |  |  |  |  |  |  |  |  |  |
| Reach out to key contacts to identify key contact needs, avenues, opps (questionnaire) |  |  |  |  |  |  |  |  |  |  |  |  |
| Review feedback and follow up with key contacts for clarification |  |  |  |  |  |  |  |  |  |  |  |  |
| Identify and implement early content delivery and engagement opps. |  |  |  |  |  |  |  |  |  |  |  |  |
| Review existing CBP content and delivery and conduct multi-benefits analysis (Mar – May) |  |  |  |  |  |  |  |  |  |  |  |  |