## Slide 1: Proposed Workplan for Completing the Alignment of the Partnership
Management Board Meeting
9/13/12
Carin Bisland

## Slide 2: Purpose
Evaluate C2K and streamlining of commitments
Ensure a set of shared priorities that fully represents the interests of the Partnership including consideration of emerging issues(e.g. climate change)
Clarify governance (roles, organization, operations)
Design efficient operational structure for collaboration
Enable effective communication of Partnership’s refreshed goals, outcomes and accomplishments

## Slide 3: Background
On July 11, 2011 the EC agreed to use a four stage process as the path forward.
At the same meeting, they agreed to use an adaptive management decision support framework.
The draft workplan was developed using these two documents as source materials

## Slide 4: Setting Goals and Outcomes
Develop Decision Support Framework
GITs use framework for at least one goal by March 31, 2012
Remaining GIT goals through Framework by end of 2012
MB discuss and provide feedback to GIT chairs the full array of draft goal beginning in Aug. 2012
Advisory Committees will provide advice through MB and PSC representation

## Slide 5: Setting Goals and Outcomes (Cont)
6. PSC (or Action Team) will review new goals/outcomes, review advice from MB and ACs, assess commitments made through EC actions to determine if new Agreement is necessary (March/Apr 2013 retreat).
7. Depending on #6, EC announces adoption of goals /new agreement (2013 EC meeting)

## Slide 6: COMMENTS?

## Slide 7: Governance
Develop survey for MB to initiate discussions on any necessary changes to the structure, operational functions and membership of the MB.
GIT 6 will analyze results
  GIT Chairs for input (Sept. 20, 2012)
  MB for recommendations to PSC (Oct. 2012)
  PSC for action (Oct/Nov 2012)
Notes: Check results of survey monkey
<number>

## Slide 8: Governance (Cont)
3. GIT 6 will develop draft protocol for “including federal, state, and local partners in the development of the new Agreement”
  MB to recommend to PSC (Nov. 2012)
  PSC for approval (Jan/Feb 2013 mtg)
Use protocol to determine goals/outcomes of Program and whether a new agreement is necessary (March/April 2013 retreat)
Notes: FLCD on PSC for this meeting
<number>

## Slide 9: Governance (Cont)
Using decision-making body identified in protocol, CBP to “revisit the governance and operations of the Chesapeake Bay Program and Partnership . . . To clarify relationships between previous agreement signatories, other federal agencies, and headwater states, and to formalize the role and relationships with the FLC . . .”
EC and FLC approve changes to governance (2013 EC meeting)

## Slide 10: COMMENTS?

## Slide 11: Discussion and Next Steps
Changes needed to workplan?
  Dates
  Steps
Recommend forwarding to PSC for approval?

## Slide 12: Discussion of Goals
Outcome of Discussion – Feedback to the GITs that will help them improve goal statements
Questions to Guide Discussion –
  Are the goals SMART? (Specific Measurable Achievable, Results-oriented, Time-Bound)
  Are there any goals that give you concern?
  Are there specific goals that you need more information on?
  Is there anything missing that would keep the Program from achieving its mission?