## Slide 1: Chesapeake EJ Screen
Status Update
John Wolf
November 13, 2018

## Slide 2: Background
FY 16 GIT Funded Project
Chesapeake Bay Watershed Environmental Justice Screening tool
Leverages National EJ Screen Tool (EPA)
Goal was to provide information on demographics and environmental conditions, and their relationship to selected Agreement outcomes
Designed as a pilot for expansion, with initial focus on the public access, toxic contaminants, and climate resiliency outcomes
One of first efforts to explicitly incorporate Cross-GIT interest into a Outcome decision support tool/framework

## Slide 3: Approach
Collaboration among Diversity Staffer and Coordinators/Staffers of…
  Climate Resiliency Workgroup
  Public Access Planning Team
  Toxic Contaminants Workgroup
Identified use cases/sample management questions
Built on services and code of National EJ Screen tool
Modified to incorporate Chesapeake Watershed data tried to pilot Outcomes
GIT Funding used to hire contractor with expertise in geospatial web development

## Slide 4: Status
Initial discovery and collaboration among Workgroup staffers and Coordinators in 2017
Beta tool launched in Spring of 2018
User testing conducted in May 2018
Project timeline extended until August 31, 2018 to incorporate feedback from user testing
Complementary story map developed to address some of the usability issues raised during testing – July 2018

## Slide 5: Outlook/Lessons Learned
Tool contains a lot of useful information
Pros and cons of leveraging a national tool and building on top of it
Difficult to navigate
Low hanging fruit improvements were made by contractor prior to end of contract
Other improvements would likely require CBP to house significant parts of EPA national tool and invest additional resources into customization and maintenance
During the course of the project, other Cross-GIT initiatives have emerged and are being pursued
  Cross-GIT Mapping Project
  SRS Management Questions
  Chesapeake Conservancy Geospatial Award

## Slide 6: Links
Chesapeake EJ Screen Story Map Tutorial - https://gis.chesapeakebay.net/cbpejscreen/tutorial
Chesapeake EJ Screen – https://gis.chesapeakebay.net/cbpejscreen/
National EJ Screen - https://www.epa.gov/ejscreen