## INSTRUCTIONS
INSTRUCTIONS FOR COMPLETING FY11 ACTIONS SPREADSHEET
Overview:
Completing this spreadsheet is the first step of a two step process for compiling a draft FY11 Action Plan. This spreadsheet is used to identify FY11 actions (and the lead agencies, and due dates for them) for each of the Strategy actions that will see activity in FY11 (based on the President's Budget). Once completed, the second step will entail use of a web based tool to identify planned agency funding for each FY11 action. Please note that the second step will require agency input of funding data between August 18 and August 20.
Structure of Spreadsheet:
The spreadsheet is organized in eight worksheets based on the four goals and four supporting strategies in the EO strategy. On each worksheet, strategy actions (and their lead and contributing agencies) are listed based on the recently completed identification of agency roles. New additional columns have been added to the right to capture FY11 action information.
The Assignment:
Each agency is responsible for taking the strategy actions for which it is the designated lead, and writing in the FY11 actions, the agency lead for the action, and the action due date. For example, agency X would submit a single spreadsheet that includes the FY11 action information for each strategy action led by agency X throughout the entire spreadsheet (all 8 worksheets); agency Y would do the same, and so on.
Lead agencies for a strategy action are responsible for consulting with their co-leads and contributing agencies in drafting the FY11 actions.
If no action is planned to occur in FY11 for a listed strategy action no entries should be made by the lead agency.
Completed spreadsheets from each agency must be submitted by COB Friday, August 13. To submit please do both of the following:
1. Load your spreadsheet to the "FY11 Actions Spreadsheets" folder on the FOD group site (http://www.chesapeakenetwork.org/library.htm?mode=view&did=43966&lid=20881&wf=20888&z=2tujs70o4)
2. Email your spreadsheet to: Aileen.Smith@noaa.gov; jdoherty@chesapeakebay.net; mlane@chesapeakebay.net
Drafting FY11 Actions:
The spreadsheet includes columns for up to three FY11 actions related to a single strategy action. This is intended to place some constraints on the level of detail to be included in the spreadsheet - it is not an agency workplan; rather it is identifying the key actions to be taken in FY11 on a given strategy action.
As an example, draft FY11 actions have been listed in the "Conserve Land" and "Citizen Stewardship" worksheets. These should be considered as draft as NPS must still consult with our contributing partners, but they are illustrative of the level of detail we seek to represent in the action plan.
At a minimum, each FY11 action description should be stated in a way that the product(s) of that task (e.g. a report, a model, a scope of work, a new regulation, etc.) is clear.
Note: If there is just one FY11 action for a given strategy action that is fine; there is no need to fill in the second and third action columns!
While we discourage going beyond three FY11 actions per strategy action, if a lead agency determines it is simply not feasible to limit the actions for a give strategy action to three, please contact Aileen Smith or Jonathan Doherty to consult on a solution.

## WATER QUALITY
Spreadsheet for Submitting FY11 Actions - FOR INTERNAL USE ONLY - DRAFT MATERIAL
FY 11 ACTION(S)
Number | Action | Lead/Co-Lead | Contributing | Keep in the Loop | Comments re. Roles | Action 1 | Action 1 Lead | Action 1 Due | Action 2 | Action 2 Lead | Action 2 Due | Action 3 | Action 3 Lead | Action 3 Due
WATER QUALITY SECTION - COORDINATING AGENCY - EPA
WQ.1 | Implement the Chesapeake Bay TMDL, a rigorous accountability framework for reducing pollution to ensure that all practices needed to reduce pollution to meet Bay water quality standards are in place by 2025 | EPA | DOD-USACE | USDA FS NOAA USGS DOD-NAVY DHS
WQ.1.a | Federal agencies will contribute to Watershed Implementation Plans | EPA | DOD-USACE USDA FS USGS DOD-NAVY DHS NPS FWS |  | EPA lead role is as "coordinator"
WQ.1.b | Create a system for tracking and reporting for TMDL pollution reduction commitments and two-year milestone commitments. | EPA | NRCS USGS | DOD-USACE USDA FS DOD-NAVY DHS
WQ.1.c | Improve mechanisms for tracking and forecasting land-use and land cover changes associated with water quality degradation. | EPA USGS | USDA FS | DOD-USACE NPS DOD-NAVY
WQ.2 | Take regulatory and other actions to support state and District plans to implement the TMDL. | EPA | DOD-USACE | USDA FS USGS DOD-NAVY DHS
WQ.2.a | Implement current regulations for concentrated animal feeding operations (CAFOs) and propose new regulations to more effectively achieve pollutant reductions necessary to meet the Chesapeake Bay TMDL. | EPA |  | USGS
WQ.2.b | Implement improvements to the current stormwater program and initiate new national stormwater rulemaking with Chesapeake Bay watershed provisions. | EPA |  | DOD-USACE USDA FS USGS DOD-NAVY DHS
WQ.2.c | Launch the Chesapeake Bay/ Anacostia Green Streets-Green Jobs Initiative | EPA |  | NPS USGS
WQ.2.d | Engage in early dialogue with Bay states and the District regarding how EPA will determine if state programs achieve TMDL pollution reduction goals and meet minimum federal program elements for stormwater and Concentrated Animal Feeding Operations. | EPA |  | DOD-USACE USGS
WQ.2.e | Reduce pollution from wastewater dischargers. | EPA | DOD-USACE | NOAA USGS DOD-NAVY DHS
WQ.2.f | Reduce pollution from septic systems. | EPA |  | USGS DOD-NAVY DHS
WQ.2.g | Reduce pollution from atmospheric deposition. | EPA |  | NOAA USDA FS USGS DOD-NAVY
WQ.2.h | Reduce costs and provide flexibility through trading and development of protocols and programs for offsetting new and expanded discharges of nutrients and sediment. | EPA |  | DOD-USACE NOAA USGS DOD-NAVY USDA FS
WQ.2.i | Reduce pollution through enforcement and compliance efforts. | EPA |  | NOAA USDA FS USGS DOD-NAVY DHS
WQ.2.j | EPA will coordinate with the Clean Water State Revolving Fund managers to build cooperation and partnership in using resources to better protect the Chesapeake Bay. | EPA |  | USGS
WQ.2.k | Provide states with additional grants for regulatory and accountability programs. | EPA |  | USGS
WQ.2.l | Pursue funding of stream restoration grants. | EPA |  | USGS
WQ.3 | Ensure the federal government leads by example in reducing pollution from federal lands and facilities. | EPA | DHS NPS FWS NOAA USDA FS DOD-NAVY | DOD-USACE EPA USGS | EPA lead role is as "coordinator"
WQ.3.a | Implement the Energy Independence and Security Act, Section 438. | EPA | DHS NPS FWS NOAA DOD-USACE DOD-NAVY | EPA USDA FS USGS | EPA lead role is as "coordinator"
WQ.3.b | Implement sustainable land management practices and programs into all federal capital improvements, public works management and energy management projects. | EPA | FWS NPS NOAA DOD-USACE USDA FS DOD-NAVY | USGS
WQ.3.c | Ensure that stormwater impacts are minimized as part of environmental review of federal-aid highway projects and other federally-assisted transportation projects. | DOT | FWS | DOD-USACE DOD-NAVY USDA FS USGS EPA
WQ.4 | Focus resources on priority watersheds and practices for agriculture to assist states in implementing their Watershed Implementation Plans (WIPs) | NRCS | FWS USDA FS | DOD-USACE DOD-NAVY USGS EPA
WQ.4.a | Target efforts at watersheds that contribute the most nitrogen, phosphorus, and sediment. | EPA NRCS | DOD-USACE FWS USDA FS USGS
WQ.4.b | Identify the most effective conservation practices. | NRCS | DOD-USACE FWS USGS USDA FS | EPA DOD-NAVY
WQ.5 | Accelerate conservation adoption by working with partners to leverage conservation funding and simplify program participation. | NRCS | DOD-USACE FWS USDA FS | EPA USGS
WQ.5.a | Leverage funding for conservation in the Chesapeake Bay watershed. | NRCS | DOD-USACE FWS USDA FS | EPA USGS
WQ.5.b | Utilize EPA funding for agriculture challenges. | EPA | NRCS | USDA FS USGS
WQ.5.c | Establish showcase projects in small watersheds. | NRCS | USGS | DOD-USACE EPA USDA FS NOAA
WQ.5.d | Monitor the results of showcase projects. | NRCS USGS |  | DOD-USACE DOD-NAVY EPA USDA FS
WQ.5.e | Simplify conservation planning for producers. | NRCS | USDA FS
WQ.6 | Accelerate development of new conservation technologies. | NRCS |  | EPA USDA FS
WQ.6.a | Fund research and development of conservation technology. | NRCS |  | EPA USDA FS USGS
WQ.6.b | Evaluate effectiveness of next generation conservation tools. | EPA NRCS |  | DOD-USACE USDA FS USGS
WQ.7 | Develop a system of accountability for tracking and reporting conservation practices. | EPA NRCS | USGS | DOD-USACE USDA FS DOD-NAVY
WQ.8 | EPA, DOI, and NOAA will work with state and local governments and stakeholders to expand understanding of the extent and seriousness of the toxic contaminant problem in the Bay and its watershed and to develop contaminant reduction goals by 201 | EPA FWS USGS | NOAA | DOD-USACE USDA FS DOD-NAVY
WQ.9 | EPA will work with DOI, states, and stakeholders to develop toxic contaminant strategies by 201 | EPA FWS | DOD-USACE USGS | NOAA USDA FS USGS
WQ.10 | Improve computer models used to guide restoration activities. | USGS | DOD-USACE | EPA FWS USDA FS | USGS suggests EPA as co-lead or contributing given their lead on WQ models.
WQ.10.a | Use results from watershed models to prioritize locations of actions. | EPA USGS | DOD-USACE | EPA NOAA USDA FS DHS
WQ.10.b | Develop groundwater models. | USGS | DOD-USACE | EPA
WQ.10.c | Ensure availability of Bay forecasts and modeling results. | NOAA | USGS | DOD-USACE DHS
WQ 11 | Improve water-quality monitoring in the watershe | EPA USGS |  | DOD-USACE DOD-NAVY
WQ 12 | Improve tracking of management actions and land use activities. | EPA | USGS | DOD-USACE USDA FS FWS DOD-NAVY
WQ 13 | Monitor and assess restoration activities in small urban and agricultural watersheds. | EPA USGS | NRCS | DOD-USACE USDA FS
WQ 14 | Improve monitoring and assessment of stream conditions. | EPA | USGS FWS | DOD-USACE USDA FS DOD-NAVY
WQ 15 | Improve monitoring of tidal waters. | EPA NOAA |  | DOD-USACE USGS DOD-NAVY
WQ 16 | Expand NOAA buoy system to improve water-quality monitoring and assess new sensors for monitoring emerging contaminants. | NOAA |  | NPS USGS DOD-NAVY
WQ 17 | Evaluate water-quality changes and progress to adjust management actions. | EPA USGS | DOD-USACE | FWS NOAA USDA FS
WQ 18 | Ensure TMDL allocations account for climate change impacts. | EPA | USGS | FWS USDA FS DOD-NAVY

## HABITAT
Spreadsheet for Submitting FY11 Actions - FOR INTERNAL USE ONLY - DRAFT MATERIAL
FY 11 ACTION(S)
Number | Action | Lead/Co-Lead | Contributing | Keep in the Loop | Comments re. Roles | Action 1 | Action 1 Lead | Action 1 Due | Action 2 | Action 2 Lead | Action 2 Due | Action 3 | Action 3 Lead | Action 3 Due
RESTORE HABITAT SECTION - COORDINATING AGENCY - FWS
RH.1. | Restore and protect priority Chesapeake marshes. | FWS | DOD-USACE NOAA USGS | NPS USDA FS
RH.2. | Increase incentives for wetland restoration and enhancement on private land. | FWS | DOT NRCS | NOAA USDA FS
RH.3. | Strengthen federal coordination on permits that impact wetlands. | FWS EPA NOAA | DOD-USACE | DHS USDA FS DOD-NAVY
RH.4. | Accelerate application of Conservation Reserve Enhancement Program (CREP) to achieve state goals for riparian forest buffer adoption. | USDA FS | NRCS USDA FSA | FWS USGS | Note - added FSA
RH.5. | Restore forest buffers in priority watersheds. | FWS USDA FS | NRCS USDA FSA | DOD-USACE DOD-NAVY USGS | Note - added FSA
RH.6. | Explore alternative payment mechanisms for incentivizing the installation of targeted riparian forest buffers. | USDA FS USDA FSA | NRCS USDA FSA | EPA FWS USGS | Note - added FSA
RH.7. | Enhance technical capacity for riparian buffer restoration. | FWS USDA FS | NRCS | USGS
RH.8. | Remove stream barriers and provide fish passage. | FWS NOAA | DOD-USACE NRCS | USGS
RH.9. | Document return of fish to opened stream reaches. | FWS | DOD-USACE NOAA | USGS
RH.10. | Combat invasive species that threaten habitat. | FWS | DOD-USACE NOAA USDA FS | USGS DOD-NAVY
RH.11. | Restore forest habitat in priority areas. | USDA FS | FWS NRCS | DOD-USACE USGS
RH.12. | Restore living shorelines. | NOAA | DOD-USACE | USGS USDA FS DOD-NAVY
RH.13. | Restore island habitats in the Bay. | DOD-USACE | NRCS USGS | NOAA USDA FS NPS | USGS suggests FWS should be contributing due to ongoing studies such as Poplar Isl.
RH.14. | Mitigate impacts of highway projects on habitat. | DOT | EPA FWS | USDA FS
RH.15. | Improve forest buffer and wetland habitat mapping. | USDA FS | FWS USGS | DOD-USACE DOD-NAVY
RH.16. | Provide forest mapping tool to watershed groups and local governments. | USDA FS | USGS | FWS
RH.17. | Improve tools for streams and fish passage. | FWS NOAA | DOD-USACE | USGS
RH 18. | Integrate watershed planning for key tributaries. | DOD-USACE |  | EPA USDA FS USGS
RH.19. | Improve monitoring of habitats. | FWS NOAA | DOD-USACE EPA USGS | USDA FS
RH.20. | Improve tracking of wetland restoration. | EPA | DOD-USACE FWS | USDA FS USGS DOD-NAVY
RH 21. | Improve baseline data for wetlands. | EPA FWS | NOAA | DOD-USACE USDA FS USGS DOD-NAVY
RH 22. | Predict impacts of stressors at the land-water interface. | NOAA | USGS | DOD-USACE FWS USDA FS
RH 23. | Evaluate use of Coastal and Marine Spatial Planning in the Bay. | NOAA | DOD-USACE | FWS NPS USDA FS USGS DHS DOD-NAVY
RH 24. | Evaluate impacts of river flow and sediment build-up on habitat. | DOD-USACE |  | FWS NOAA USGS EPA

## FISH & WILDLIFE
Spreadsheet for Submitting FY11 Actions - FOR INTERNAL USE ONLY - DRAFT MATERIAL
FY 11 ACTION(S)
Number | Action | Lead/Co-Lead | Contributing | Keep in the Loop | Comments re. Roles | Action 1 | Action 1 Lead | Action 1 Due | Action 2 | Action 2 Lead | Action 2 Due | Action 3 | Action 3 Lead | Action 3 Due
SUSTAIN FISH & WILDLIFE - COORDINATING AGENCY - NOAA
FW.1. | Launch a Bay-wide oyster strategy using scientific support for decision making. | NOAA DOD-USACE | DOD-USACE FWS | DOD-NAVY
FW.2. | Restore priority tributaries and support enforcement. | NOAA | FWS DOD-USACE
FW.3. | Expand commercial aquaculture. | NOAA |  | DOD-USACE FWS
FW.4. | Support continued inter-jurisdictional blue crab management. | NOAA |  | DOD-USACE
FW.5. | Revise blue crab population rebuilding target. | NOAA |  | DOD-USACE
FW.6. | Restore stream habitat through partnerships. | FWS | DOD-USACE | NOAA USGS
FW.7. | Consider climate change in prioritizing sub-watersheds for restoration. |  | DOD-USACE FWS | NOAA USDA FS USGS
FW.8. | Restore black duck habitat. | FWS |  | DOD-USACE USGS
FW.9. | Increase nutrient sources on refuge lands. | FWS |  | DOD-USACE USGS
FW.10. | Facilitate interjurisdictional, ecosystem-based fisheries management. | NOAA | FWS | DOD-USACE USGS
FW.11. | Consider alternative fisheries management approaches. | NOAA |  | DOD-USACE FWS
FW.12. | Support the Atlantic Coastal Fish Habitat Partnership (ACFHP) | FWS NOAA |  | DOD-USACE USGS
FW.13. | Collect and organize information to help identify and prioritize areas to restore oyster habitat and populations. | NOAA | DOD-USACE | FWS
FW.14. | Improve scientific information on selected freshwater species. | USGS | FWS | DOD-USACE EPA
FW.15. | Improve scientific information to support Bay-wide restoration efforts. | NOAA | DOD-USACE FWS | USGS EPA DOD-NAVY
FW.16. | Establish watershed program for brook trout monitoring. | FWS | USDA FS | USGS
FW.17. | Improve monitoring of black duck food sources. | FWS | USGS
FW 18. | Use science to evaluate oyster restoration progress | NOAA | DOD-USACE | USGS EPA DOD-NAVY
FW.19. | Develop ecosystem models to support decision making. | NOAA | DOD-USACE USDA FS | USGS
FW.20. | Evaluate native bivalve restoration for water quality improvement. | NOAA | DOD-USACE | FWS EPA
FW.21. | Assess quality of Black Duck habitat. | FWS | USGS

## CONSERVE LAND
Spreadsheet for Submitting FY11 Actions - FOR INTERNAL USE ONLY - DRAFT MATERIAL
FY 11 ACTION(S)
Number | Strategy Action | Lead/Co-Lead | Contributing | Keep in the Loop | Comments re. Roles | Action 1 | Action 1 Lead | Action 1 Due | Action 2 | Action 2 Lead | Action 2 Due | Action 3 | Action 3 Lead | Action 3 Due
CONSERVE LAND & INCREASE PUBLIC ACCESS COORDINATING AGENCY - NPS
CL.1. | Launch a Chesapeake Treasured Landscape Initiative. | NPS | USDA FS | DOD-USACE FWS USGS DOD-NAVY
CL.1.a | Increase Land & Water Conservation Fund allocations. | NPS |  | FWS USDA FS
CL.1.b | Create a public-private conservation funding partnership. | NPS | USDA FS FWS |  |  | Convene working session of federal and state agencies and nongovernmental organizations to create a public-private partnership to coordinate and leverage federal and possibly state conservation funding. | NPS | 2010-10-01 | Develop a formal agreement between federal partners and a non-governmental organization on the relationship and scope of activities and conduct a pilot funding project. | NPS | 2011-02-01
CL.2. | Coordinate and target federal land conservation funding. | NPS FWS | USDA FS NRCS DOD-NAVY | DOD-USACE USGS |  | Convene working session(s) of federal and state program managers for the Land & Water Conservation Fund, Forest Legacy, Coastal and Estuarine Land Conservation Program, Wetlands Reserve Program, Farm and Ranchlands Protection Program, Transportation Enhancements, and the Readiness and Environmental Protection Initiative to address how to ensure conservation planning approaches and priorities are shared and coordinated across jurisdictions and programs in the Chesapeake Bay watershed. | NPS | 2010-12-01 | TBD based on working session.
CL.2.a | Increase collaboration in the Coastal and Estuarine Land Conservation Program. | NOAA | NPS | DOD-USACE FWS USDA FS |  | Convene a meeting with coastal state partners to finalize CELCP plans within the Chesapeake region and ensure that priority acquisitions at National Estuarine Research Reserve System sites are fully incorporated into statewide CELCP planning. | NOAA | 2010-12-01
CL.2.b | Encourage consideration of Transportation Enhancements, Scenic Byways, and Recreational Trails programs to support land conservation. | DOT | NPS FWS | DOD-USACE USDA FS |  |  | DOT
CL.2.c | Conserve priority landscapes around defense installations. | NPS DOD-NAVY | NRCS | DOD-USACE USDA FS |  | Identify locations where land conservation priorities of military bases, National Wildlife Refuges, National Parks and National Trails overlap and develop coordinated land conservation strategies. | NPS | 2011-09-01 | Revise guidance for the DOD Readiness and Environmental Protection Initiative program in 2011 to ensure Chesapeake Bay projects receive the extra credit for proposed projects that result in a title fee or easement purchase of significant landscape and areas of ecological and/or cultural value. | DOD-NAVY | 2011-09-01
CL.3. | Conserve landscapes through National Park Service partnership areas. | NPS |  | USDA FS USGS
CL.3.a. | Consider a new unit of the National Park System for Chesapeake Bay & Rivers. | NPS |  |  |  | Convene representatives of the states’ governors to explore the potential for a new unit of the National Park System focused on the Chesapeake and its rivers. | NPS | 2010-12-01 | TBD based on meetings with states.
CL.3.b | Identify high priority landscapes along National Trails. | NPS |  |  |  | Identify high priority landscapes along the route of the Captain John Smith Chesapeake National Historic Trail as a focus for land conservation efforts; publish landscape and site criteria and priority locations in the trail comprehensive management plan in 2010, and incorporate into watershed-wide GIS system (CL.9). | NPS | 2010-10-01 | Identify high priority landscapes along the route of the Star-Spangled Banner National Historic Trail as a focus for land conservation efforts; publish landscape and site criteria and priority locations in the trail comprehensive management plan in 2011and incorporate into watershed-wide GIS system (CL.9). | NPS |  | Identify high priority landscapes along the route of the Potomac Heritage National Scenic Trail as a focus for land conservation efforts, and incorporate into watershed-wide GIS system (CL.9). | NPS
CL.3.c | Coordinate NPS conservation actions with FWS refuge partnerships. | NPS FWS |  |  |  | Develop a memorandum of understanding between NPS and FWS for coordination of National Wildlife Refuge conservation partnerships and planning and investments for the Captain John Smith Chesapeake National Historic Trail, Star-Spangled Banner Historic Trail and the Chesapeake Bay Gateways and Watertrails Network. | NPS | 2010-10-01
CL.4. | Achieve mutual conservation goals through National Wildlife Refuge partnerships. | FWS | NPS | USGS |  |  | FWS
CL.5. | Develop a Bay wide strategy to reduce the loss of farms and forests. | NRCS USDA FS | NPS | DOD-USACE DOD-NAVY EPA
CL.6. | Support creation and expansion of protected coastal and marine areas. | NOAA |  | DOD-USACE DOD-NAVY NPS USDA FS |  |  | NOAA
CL.7. | Provide community assistance for landscape conservation. | NPS | FWS USDA FS NRCS |  |  | Deliver coordinated community assistance for identification, assessment and conservation of priority landscapes; priority landscapes for 2011 will be along high priority segments of the Captain John Smith Chesapeake National Historic Trail. | NPS | 2011-09-01 | Convene federal and state partners to assess current technical assistance capabilities and gaps, and identify ways to improve local government and land trust access to assistance providers and capacity building support. | NPS | 2011-09-01
CL.8. | Identify culturally significant and ecologically important landscapes. | NPS | FWS USDA FS USGS NRCS | DOD-USACE DOD-NAVY |  | Convene working team of federal, state and non-governmental partners to develop a scope, approach and initial resources for conducting landscape surveys to identify landscapes of cultural significance to different communities and the region. | NPS | 2011-02-01 | Initiate pilot landscape survey. | NPS | 2011-09-01
CL.9. | Establish watershed-wide GIS-based land conservation targeting system. | NPS USGS | FWS NRCS | DOD-USACE USDA FS DOD-NAVY |  | Convene working session(s) of federal agency partners, states and non-governmental organizations to develop a scope for the system and the mechanisms to put the system into place beginning in 2011. | NPS | 2010-12-01 | Establish a decision-support specialist for land conservation to manage the system and data and develop products to help users understand the implications of different conservation options. | USGS |  | Based on scope, begin implementation of system with information currently available - details TBD.
RH 9.a. | Improve monitoring of land use changes. | USGS EPA | USDA FS | DOD-USACE NPS |  |  | USGS EPA
CL.9.b. | Describe land-cover change to evaluate progress toward land conservation. | USGS | USDA FS NOAA | DOD-USACE DOD-NAVY NPS |  |  | USGS
CL.10. | Develop integrated transportation, land use, housing and water infrastructure plans setting forth smart growth and environmental stewardship visions. | DOT | EPA | USDA FS DOD-USACE NPS DOD-NAVY |  |  | DOT
CL.11. | Develop a plan to expand public access. | NPS | FWS | DOD-USACE DOD-NAVY NOAA USDA FS |  | Convene working session(s) of federal agency partners, states and non-governmental organizations to develop scope and process for drafting a regional public access strategy. | NPS | 2010-10-01 | Initiate development of regional public access strategy based on scope; strategy to be completed by 2012. | NPS | 2011-12-01
CL.11.a | Identify public access needs and opportunities along National Trails. | NPS |  | DOD-USACE FWS |  | Identify public access needs and opportunities along the Captain John Smith Chesapeake National Historic Trail in the trail comprehensive management plan; incorporate in regional public access strategy. | NPS | 2010-10-01 | Identify public access needs and opportunities along the Star Spangled Banner NHT in the trail comprehensive management plan; incorporate in regional public access strategy. | NPS
CL.12 | Prioritize funding for public access development. | NPS | FWS | DOD-USACE |  | Revise criteria for Chesapeake Bay Gateways and Watertrails Network grants to set public access development as a priority funding focus for 2011. | NPS | 2010-10-01 | Issue 2011 grants for public access development through Chesapeake Bay Gateways and Watertrails Network grants program. | NPS | 2011-05-01

## CITIZEN STEWARDSHIP
Spreadsheet for Submitting FY11 Actions - FOR INTERNAL USE ONLY - DRAFT MATERIAL
FY 11 ACTION(S)
Number | Action | Lead/Co-Lead | Contributing | Keep in the Loop | Comments re. Roles | Action 1 | Action 1 Lead | Action 1 Due | Action 2 | Action 2 Lead | Action 2 Due | Action 3 | Action 3 Lead | Action 3 Due
EXPAND CITIZEN STEWARDSHIP COORDINATING AGENCY - NPS
CS.1. | Expand Chesapeake conservation corps workforces. | NPS | FWS |  |  | Convene working session(s) of partners to expand existing conservation corps workforces that create jobs and carry out conservation and restoration projects in priority watersheds. Coordinate development of a proposed strategy for expanding corps programs. | NPS | 2011-09-01
CS.2 | Expand master watershed stewards program. | NPS EPA |  |  |  | Convene working session(s) of partners to determine how best to expand the existing model master watershed stewards program and to develop an expansion plan and methods for measuring progress. |  | 2011-09-01
CS.3 | Prioritize citizen stewardship in Small Watershed Grants program. | EPA NPS |  | USDA FS |  | Revise criteria for Small Watershed Grants Program to make citizen stewardship-based projects a priority funding category in 2011. | NPS | 2010-10-01
CS.4. | Expand outreach to private forest landowners. | USDA FS |  | NPS
CS.5. | Enhance visitor experiences and stewardship. | NPS FWS |  | DOD-USACE
CS.6. | Build long-term local partnerships for engaging communities and citizens along national trails. | NPS |  | FWS USDA FS
CS.7. | Initiate robust elementary and secondary environmental literacy initiative. | NOAA | FWS NPS EPA | USDA FS
CS.7.a. | Support and enhance outdoor student environmental education programs. | NOAA | EPA FWS NPS USDA FS | DOD-USACE DOD-NAVY
CS.7.b. | Provide high-quality professional development, tools, and resources for educators. | NOAA | FWS | DOD-USACE NPS EPA
CS.7.c | Encourage the creation and maintenance of green schools, including schoolyard habitat and green facilities programs. | FWS | NOAA | DOD-NAVY NPS USDA FS EPA

## ENV. MARKETS
Spreadsheet for Submitting FY11 Actions - FOR INTERNAL USE ONLY - DRAFT MATERIAL
FY 11 ACTION(S)
Number | Action | Lead/Co-Lead | Contributing | Keep in the Loop | Comments re. Roles | Action 1 | Action 1 Lead | Action 1 Due | Action 2 | Action 2 Lead | Action 2 Due | Action 3 | Action 3 Lead | Action 3 Due
DEVELOP ENVIRONMENTAL MARKETS COORDINATING AGENCY - USDA
EM.1. | Establish a market for trading pollutant reduction credits for nutrients and sediments in support of the water quality goals in the TMDL. | EPA | NOAA USDA FS NRCS | DOT FWS USGS DOD-NAVY
EM.2 | USDA will lead, in coordination with EPA and other federal agencies, an interdepartmental Environmental Market Team to coordinate efforts in establishing an environmental market infrastructure for the Chesapeake Bay. | EPA USDA | DOD-NAVY DOT FWS NOAA USDA FS | NPS DOD-USACE USGS | What is proper agency for USDA?

## CLIMATE
Spreadsheet for Submitting FY11 Actions - FOR INTERNAL USE ONLY - DRAFT MATERIAL
FY 11 ACTION(S)
Number | Action | Lead/Co-Lead | Contributing | Keep in the Loop | Comments re. Roles | Action 1 | Action 1 Lead | Action 1 Due | Action 2 | Action 2 Lead | Action 2 Due | Action 3 | Action 3 Lead | Action 3 Due
RESPOND TO CLIMATE CHANGE COORDINATING AGENCY - NOAA and USGS
CC.1. | Identify communities that are vulnerable to the impacts of climate change. | NOAA | USGS | DOD-USACE DOD-NAVY DOT EPA USDA FS
CC.2. | Demonstrate and implement effective restoration planning in face of land elevation change and sea level rise. | NOAA | DOD-USACE FWS USGS | EPA NPS DOD-NAVY
CC.3. | Identify and assess risk to key tidal and coastal habitats from potential impacts of changing climatic conditions and rising sea level. | NOAA USGS | DOD-USACE FWS EPA | DOD-USACE USDA FS NPS DOD-NAVY
CC.4. | Identify and assess risk to key watershed habitats from potential impacts of climate and land change. | FWS USGS | EPA | DOD-USACE DOT USDA FS NPS
CC.5. | Enhance federally-supported research to improve and streamline vulnerability assessments. | NOAA USGS |  | DOD-USACE EPA NPS
CC.5.a | Provide land use change data. | NOAA USGS |  | DOD-USACE DOD-NAVY EPA USDA FS
CC.5.b | Provide projections of land use changes. | EPA USGS |  | DOD-USACE DOD-NAVY USDA FS
CC.5.c | Assist states and local communities with topographic data. | USGS |  | DOD-USACE EPA
CC.6. | Develop tools and training to provide states, local communities, and resource managers with effective climate adaptation planning and implementation resources. | NOAA | USGS NPS EPA | DOD-USACE FWS USDA FS
CC.6.a. | Strategic land use decision support | EPA | USGS | DOD-USACE FWS USDA FS
CC.6.b. | Adapting wetland restoration techniques. | NOAA FWS | DOD-USACE USGS | EPA
CC.7. | Improve monitoring of climate change impacts in the Bay and watershed. | NOAA USGS | FWS | DOD-USACE DOD-NAVY EPA NPS USDA FS
CC.7.a | Implement the Climate Effects Network. | USGS | FWS | NPS USDA FS
CC.7.b | Develop monitoring framework for streams. | EPA | FWS USGS | DOD-USACE USDA FS
CC.7.c | Develop a complementary estuarine monitoring network. | NOAA | USGS | DOD-USACE EPA
CC.8. | Ensure monitoring results are integrated and available to assess effectiveness and adjust management actions as necessary. | EPA | USGS NOAA | DOD-USACE FWS
CC.9. | Integrate climate change adaptation into the Chesapeake Bay Program. | EPA NOAA USGS | FWS | DOD-USACE NPS USDA FS
CC. 10. | Conduct technical performance review of agencies’ climate response effectiveness. | EPA | NOAA | DOD-USACE DOD-NAVY USDA FS USGS
CC.11. | Predict potential changes in pollution loads due to climate change. | EPA | USGS | DOD-USACE DOD-NAVY
CC.12. | Develop adaptation strategies to manage vulnerable habitats and public infrastructure on federal lands to increase resiliency to climate change impacts. | FWS | USGS USDA FS NPS | DOD-USACE DOD-NAVY DOT EPA NOAA
CC.13. | Integrate climate response into federal growth and development programs and strategies. | EPA | NPS | DOD-USACE DOD-NAVY DOT FWS USDA FS USGS
CC.14. | Coordinate with other national initiatives to enhance federal mitigation efforts in the Bay watershed. | EPA |  | DOD-USACE DOT FWS NOAA USDA FS USGS

## SCIENCE
Spreadsheet for Submitting FY11 Actions - FOR INTERNAL USE ONLY - DRAFT MATERIAL
FY 11 ACTION(S)
Number | Action | Lead/Co-Lead | Contributing | Keep in the Loop | Comments re. Roles | Action 1 | Action 1 Lead | Action 1 Due | Action 2 | Action 2 Lead | Action 2 Due | Action 3 | Action 3 Lead | Action 3 Due
STRENGTHEN SCIENCE COORDINATING AGENCY - USGS
SS.1. | Expand scientific coordination and capabilities of the Chesapeake Bay Program. | EPA USGS | NOAA | DOD-USACE NPS USDA FS
SS.2. | Establish decision support specialists. | USGS | NOAA | DOD-USACE EPA NPS USDA FS
SS.3. | Improve communication products. | EPA | FWS USGS NOAA | DOD-USACE NPS
SS.4. | Review and improve CBP science approaches. | EPA |  | DOD-USACE EPA USDA FS USGS
SS.5. | USGS and NOAA will ensure scientific tools, data, and computer model results are available. | NOAA USGS |  | DOD-USACE EPA | USGS suggests EPA be added as contributing.
SS.6 | EPA, working with Chesapeake Bay Program partners, will establish ChesapeakeStat. | EPA | FWS NOAA USGS | DHS DOD-USACE DOD-NAVY NPS USDA FS
SS.7 | Improve modeling used for restoration activities and assessing impacts of climate change. | USGS | NOAA | DOD-USACE DOD-NAVY EPA
SS.8. | Establish a Chesapeake Monitoring Alliance. | EPA USGS NOAA | FWS | NPS DOD-NAVY
SS.9. | Coordinate regional water monitoring with national networks. | EPA NOAA USGS |  | NPS
SS.10 | Increase monitoring by state, local, and non-governmental partners. | EPA | NOAA USGS | DOD-USACE DOD-NAVY NPS
SS.11 | Improve monitoring of climate change impacts. | NOAA USGS | FWS | DOD-USACE EPA USDA FS NPS
SS.12. | Improve reporting of restoration actions and land use activities. | EPA | FWS USGS | DOD-USACE DOD-NAVY NOAA USDA FS
SS.13. | Improve management of environmental information through a Data Enterprise. | EPA | NOAA USGS | DHS DOD-USACE DOD-NAVY NPS USDA FS
SS.14. | Improve indicators of environmental conditions. | EPA | NOAA USGS | DOD-USACE DOD-NAVY USDA FS | Question: Shouldn't every agency with lead for an outcome have contributing role here?
SS.15 | Create case studies of targeted restoration activities. | NOAA USGS | FWS | DOD-USACE EPA USDA FS
SS.16 | Explain the factors affecting progress toward restoration goals and the effects of management actions. | EPA NOAA USGS |  | DOD-USACE DOD-NAVY FWS USDA FS
SS.17 | Assess new threats to the Bay and its watershed. | USGS | NOAA EPA | DOD-USACE EPA