## Sheet1
Toxic Contaminants Research Outcome Effective dates: 2016-2017
Goal: Toxic Contaminants
Outcome: Research
Long term Target: Develop a research agenda and further characterize the occurrence, concentrations, sources and effects of toxic contaminants of emerging and widespread concern.
2 year Target: Completion of performance targets related to key actions
Partner contributions to 2 year target: As-listed under performance targets
Management Approach 1: Supply information to make fish and shellfish safe for human consumption
Key Action | Performance Target(s) | Partners | Geographic Location | Timeline | Factors Influencing and/or Gap
Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Identify incremental steps to achieve Key Action | Responsible |  | Identify completion date (month and year) for each step. | ID related factor or gap in Mgmt. Strat
Identify responsible partner for each step.
1. Use existing information to provide overviews of the effects of multiple toxic contaminants on shellfish and fisheries. | NOAA is preparing a National Bioeffects report that will contain a chapter on Chesapeake Bay. NOAA will present the Chesapeake summary to the TCW. | NOAA | Tidal waters in MD and VA | 2016 | Different thresholds for effects on shellfish and fisheries. Resource constraints
Other existing NOAA reports include:http://ccma.nos.noaa.gov/publications/NCCOSTM47.pdf)
http://www.ccma.nos.noaa.gov/publications/nccoschesapeakebay.pdf
2. Generate further information on mercury, focused on determining whether further Chesapeake Strategies are needed to supplement national efforts to reduce its impact on fish and associated consumption advisories. | Establish a Mercury Subgroup that would begin to summarize information to be considered by TCW to minimize effects of mercury. | TCW | Watershed-wide | 2016-17 | Resource constraints
UMCES, SERC, NOAA-ARL, ERM, Inc., MDE, DNR-PPRP
| Conduct sampling of mercury in young of the year fish. Results will eventually be used to assess trends. | MDE and MD DNR |  | 2016-2017
Maryland
| Review and obtain information documented during the establishment of Maryland’s proposed Mercury TMDL. | MDE | Maryland | 2016-2017
3. Generate further information on selected pesticides to help TCW consider a future management strategy | Interact with MD Pesticide network and associated research WG (see Management Approach 4) | MD Pesticide Network | MD focused | 2016 | Staff constraints
4. Consider the development of a PCB mass balance model for the Chesapeake Bay. | Discuss utility, feasibility and practicality of developing a mass-balance model for PCBs. | TCW and science partners | Chesapeake Bay Watershed-wide | 2016-17 | Resource constraints
5. Monitor levels of PCBs in fish and shellfish and move contaminated sites towards cleanup. | (Please see the Toxic Contaminants Policy and Prevention Workplan- Management Approach 1, Key Action 1) | (See Toxic Contaminants Policy and Prevention Workplan) | (See Toxic Contaminants Policy and Prevention Workplan) | (See Toxic Contaminants Policy and Prevention Workplan) | N/A
6. Better delineate PCB sources from diffuse sources of land, release from deposits in stormwater pipes, and atmospheric deposition. | (Please see the Toxic Contaminants Policy and Prevention Workplan- Management Approach 1, Key Actions 6 and 10; Management Approach 4, Key Actions 1 and 5) | (See Toxic Contaminants Policy and Prevention Workplan) | (See Toxic Contaminants Policy and Prevention Workplan) | (See Toxic Contaminants Policy and Prevention Workplan) | N/A
Management Approach 2: Understanding the influence of contaminants in degrading the health, and contributing to mortality, of fish and wildlife
Key Action | Performance Target(s) | Partners | Geographic Location | Timeline | Factors Influencing and/or Gap
Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Identify incremental steps to achieve Key Action | Responsible |  | Identify completion date (month and year) for each step. | ID related factor or gap in Mgmt. Strat
Identify responsible partner for each step.
1.Assess the effects of contaminants on fish and shell fish in tidal waters | Continue studies of tumors found in Bullheads catfish | FWS | Tidal Potomac | 2016-17 | -Lack of comprehensive monitoring program in tidal waters.
-Complexity of relating mixtures of contaminants to effects on fish and shellfish
-resource constraints
| Evaluate findings from condition of Yellow Perch in urban areas. | FWS | Selected MD rivers
MD DNR
USGS
2.Generate information to document fish health conditions in the Bay watershed. | Conduct studies to understand the influence of contaminants and other factors degrading the health, and contributing to mortality of fish. Products include summary of fish health conditions (including intersex) over the last 10 years in the watershed. Studies have partners in several states (see below) | USGS | Susquehanna and Potomac watersheds | 2016-17 | -Lack of comprehensive monitoring program in the watershed
| Better understand the influence of endocrine-disrupting compounds (EDCs) and their effects on fish conditions. Focus on agricultural areas in 2016-17 with urban areas addressed in 2018-19. (in collaboration with project listed above) | USGS | Susquehanna and Potomac watersheds
| Continue monitoring of fish conditions in areas of concern within jurisdictions (most in cooperation with USGS projects listed above) | PA DEP | Susquehanna and Potomac watersheds | 2016-17 | -Complexity of relating mixtures of contaminants to effects on fisheries
|  | MD DNR |  |  | -resource constraints
WV DEP
| Continue studies on the relationship between the amount of impervious surface and the impact on fish conditions | MD DNR | Maryland | 2016-17
| Continue stream IBI studies as part of the Maryland biological stream survey to evaluate health of fish communities and identify potential linkages to toxic contaminants. | MD DNR and MDE | Maryland | 2016-17
3.Assess the effects of toxic contaminants on wildlife by summarizing existing studies and considering additional research activities. Information will be used to TCW on implications for relative risk (see management approach 4) | Complete and present review of EDC found in wildlife within the Chesapeake watershed. Based on results consider additional studies. | USGS | Chesapeake Bay Watershed-wide | 2016 | -Lack of wildlife monitoring program
-Complexity of relating mixtures of contaminants to effects on wildlife
| Publish results from the recently published Chesapeake Bay osprey food study. Assess if results from the Delaware-based osprey food study are applicable. | USGS | Baltimore Harbor, Anacostia, Elizabeth River | 2016 | -resource constraints
Management Approach 3: Document the occurrence, concentrations, and sources of contaminants causing fish and wildlife degradation
Key Action | Performance Target(s) | Partners | Geographic Location | Timeline | Factors Influencing and/or Gap
Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Identify incremental steps to achieve Key Action | Responsible |  | Identify completion date (month and year) for each step. | ID related factor or gap in Mgmt. Strat
Identify responsible partner for each step.
1. Better define the sources and occurrence of EDCs and other contaminant groups that are affecting the health of fish and wildlife in the watershed. | Conduct projects to identify the sources and occurrence of toxic contaminants contributing to degraded fish health. Prepare initial summary of the occurrence and sources of contaminants based on information collected by USGS over the last 10 years in the Bay watershed. Assess the potential association with nutrients. Studies have partners in several states (see below). | USGS | Multiple locations, mostly in Susquehanna and Potomac | 2016-17 | -Lack of comprehensive monitoring programs in watershed.
-Lack of consistent information on the occurrence of contaminants.
| Continue study of sources and occurrence of EDCs in agricultural watersheds (same locations as USGS fish health studies). Collect samples for Gather information for GIS analysis of sources and occurrence of EDCs in the watershed. Begin planning for study of urban watersheds, focusing on impact of BMPs on EDCs in the environment. | USGS |  | 2016-17 | -resource and lab constraints
| Continue Pennsylvania studies on pesticides and hormones. | PA DEP | Susquehanna basin | 2016
| Continue studies on the impacts of algal toxins on fish kills in West Virginia and identify potential links to toxic contaminants. | WV DEP (working with USGS) | Upper Potomac basin, WVA | 2016-17
| Evaluate outcomes from Anacostia River sediment investigation to improve understanding of contaminants other than PCBs. | DOEE | Anacostia River, MD-DC | 2016-17
2. Better define sources and occurrence contaminant groups occurring in tidal waters | -use new Chesapeake bio-effects summary and Utilize information from existing NOAA documents http://ccma.nos.noaa.gov/publications/NCCOSTM47.pdf | NOAA | Tidal waters | 2016 | -Lack of comprehensive monitoring programs in tidal waters.
-Lack of consistent information on the occurrence of contaminants.
-resource and lab constraints
Management Approach 4: Assess the relative risk of contaminants, and options for mitigation, to inform policy and prevention
Key Action | Performance Target(s) | Partners | Geographic Location | Timeline | Factors Influencing and/or Gap
Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Identify incremental steps to achieve Key Action | Responsible |  | Identify completion date (month and year) for each step. | ID related factor or gap in Mgmt. Strat
Identify responsible partner for each step.
1. Develop approaches to assess the relative risk of contaminants to help inform policy and prevention strategies. | Develop approaches to assess relative risk to help inform policy and prevention strategies. | EPA Office of Water, Office of Science and Technology | Chesapeake Bay Watershed-wide
Mixtures of contaminants complicate risk assessment
Lack of toxicity thresholds.
| Begin to develop methods for summarizing existing information on Hg, pesticides, PAHs, for future consideration within the Policy and Prevention Management Strategy. | TCW | Chesapeake Bay Watershed-wide | 2016-17
2. Share approaches for assessing relative risk with the TCW so that they can consider options for mitigating impacts of toxic contaminants. | Develop a lessons learned document based on the results from the Anacostia River study. | DOEE | Anacostia | 2016-17
TCW
| Begin a risk assessment study of EDCs compounds with occurrence of intersex and other fish health conditions | USGS | Focused on Susquehanna and Potomac basins | 2016-17 | Limited information on effectiveness of BMPs for reducing contaminants.
| Conduct GIS analysis to identify toxic contaminant “hotspots” based on land use. Relate to areas of nutrient loading | USGS | Watershed wide
| Evaluate outcomes from the literature review on the potential toxic contaminant reductions provided by traditional stormwater BMPs, and conduct outreach efforts to share those results. | CSN | Watershed-wide
TCW
| Have MD Pesticides share methodology for prioritizing pesticides. Work with them to assess use for TCW | MD Pesticide Network (research workgroup) | Mostly MD | 2016
3. The Chesapeake Bay Commission will work collaboratively with the Bay Program partners to identify legislative, budgetary and policy needs to advance the goals of the Chesapeake Watershed Agreement. | CBC will, in turn, pursue action within our member state General Assemblies and the United States Congress. See CBC Resolution #14-1 for additional information on the CBC’s participation in the management strategies. | Chesapeake Bay Commission | Watershed-Wide | 2016-2017
Management Approach 5: Gather information on issues of emerging concern
Key Action | Performance Target(s) | Partners | Geographic Location | Timeline | Factors Influencing and/or Gap
Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Identify incremental steps to achieve Key Action | Responsible |  | Identify completion date (month and year) for each step. | ID related factor or gap in Mgmt. Strat
Identify responsible partner for each step.
1. Better delineate potential impacts of UOG activities. | Conduct research on impacts of UOG activities (part of wider studies of UOGs) | USGS with partners | Upper Susquehanna River, Pennsylvania and NY | 2016-17 | Limited knowledge, resource constraints
Definitions:
EPA | U.S. Environmental Protection Agency
DE DNREC | Delaware Department of Natutral Resources and Environmental Control
DOEE | District of Columbia Department of Energy and Environment
MDE | Maryland Department of the Environment
MD DNR | Maryland Department of Natural Resources
NYS DEC | New York State Department of Environmental Control
PA DEP | Pennsylvania Department of Environmental Protection
VA DEQ | Virginia Department of Environmental Quality
WV DEP | West Virginia Department of Environmental Protection
USGS | U.S. Geological Survey
FWS | U.S. Fish and Wildlife Service
UMCES | University of Maryland Center for Environmental Science
UMBC | University of Maryland Baltimore County
NOAA | National Oceanic and Atmospheric Administration
USDA | U.S. Department of Agriculture
NRCS | National Resource Conservation Service
DoD | U.S. Department of Defense
USACE | U.S. Army Corps of Engineers
DOT | Department of Transportation
SRBC | Susquehanna River Basin Commission
CBP | Chesapeake Bay Program Partnership
CBPO | Chesaoeake Bay Program Office
WQGIT | Water Quality Goal Implementation Team
STAC | Scientifical and Technical Advisory Committee
MB | Chesapeake Bay Program's Management Board
PSC | Chesapeake Bay Program's Principles' Staff Committee
WIP | Watershed Implementation Plan
TMDL | Total Maximum Daily Load
NATA | National Air Toxics Assessment
DAT | Chesapeake Bay Program Diversity Action Team
HSCD | EPA Hazardous Site Cleanup Division
TSCA | Toxic Substance Control Act
PMP | Pollution Minimization Plan
ASTSWMO | Association of State and Territorial Solid Waste Management Officials
CSN | Chesapeake Stormwater Network