## Management Strategy Timeline
Engaged Communities Management Strategy Timeline
| May 04–May 10 | May 11–May 17 | May 18–May 24 | May 25–May 31 | Jun 01–Jun 07 | Jun 08–Jun 14 | Jun 15–Jun 21 | Jun 22–Jun 28 | Jun 29–Jul 05 | Jul 06–Jul 12 |  | Jul 13–Jul 19 | Jul 20–Jul 26 | Jul 27–Aug 02 | Aug 03–Aug 09 | Aug 10–Aug 16 | Aug 17–Aug 23 | Aug 24–Aug 30 | Aug 31–Sep 06 | Sep 07–Sep 13 | Sep 14–Sep 20 | Sep 21–Sep 27 | Sep 28–Oct 04 | Oct 05–Oct 11 | Oct 12–Oct 18 | Oct 19–Oct 25 | Oct 26–Nov 01 | Nov 02–Nov 08 | Nov 09–Nov 15 | Nov 16–Nov 22 | Nov 23–Nov 29 | Nov 30–Dec 06 | Dec 07–Dec 13 | Dec 14–Dec 20 | Dec 21–Dec 27 | Dec 28–Jan 3 | Jan 4-Jan 10 | Jan 11-Jan 17 | Jan 18-Jan 24 | Jan 25-31
| Phase 1: Logistics |  |  | Phase 2: Baselines |  |  | Phase 3: Situation Analysis, Management Approaches | [8 empty] | Phase 4: Editing and crosswalks |  |  |  | Phase 5: Full draft circulation and review | [5 empty] | Phase 6: PSC review and approval | [10 empty] | Phase 7: Public Feedback Period
Goal Team | May 8: (1) Create drafting folders and documents for each section (2) Determine overall timeline | May 17: Assign section leads for each template component | [5 empty] | June 22: Monthly EComm GT/WG Leads Meeting |  |  | July 9: Engaged Communities Goal Team Meeting |  |  | July 27: Monthly EComm GT/WG Leads Meeting | August 4: Share current MS draft w/ other Goal Teams | August 14: Complete Goal Challenges and Goal Management Approaches |  | August 24: Monthly EComm GT/WG Leads Meeting |  | Sept 11: Fully Complete Draft Circulation (share w/ GT and WG members) |  |  | Sept 28: Monthly EComm GT/WG Leads Meeting |  | Oct 16: All materials completed, including presentation materials |  | Oct 26: Monthly EComm GT/WG Leads Meeting | Nov 5: Present to PSC |  | Nov 20: Complete Strategic Plan Revisions based on PSC feedback | HOLIDAY BREAK |  |  | Dec 18: PSC approves Strategic Plan | HOLIDAY BREAK |  | Jan 5: Public Feedback Period begins for Strategic Plan |  |  | Jan 31: Public Feedback Period ends
Workgroups | May 8: (1) Create drafting folders and documents for each section (2) Determine overall timeline |  |  | May 29: (1) Assign section leads for each template component and (2) confirm Management Strategy timeline within individual workgroups (teams can change specific deadlines if wanted) |  | June 12: Complete (1) Baseline and Current Conditions for the Outcome (2) Complete Monitoring Progress and Indicator details | June 19: Complete Outcome Challenges |  |  | July 7: Complete initial draft Outcome Management Approaches |  |  |  |  | August 7: Complete Outcome Management Approaches | August 14: Identify which Goal Management Approaches will be addressed in which Outcome Workplans | August 21: Complete (1) Snapshot of Signatory Programs, (2) Participating Partners for Outcome, (3) Signatory Statutory Authorities for Outcome |  |  | Sept 11: Fully Complete Draft Circulation (share w/ GT and WG members) |  |  |  |  | Oct 16: All materials completed, including presentation materials
Drafting Phases | Phase 1: Logistics (timeline, roles, deadlines)
Phase 2: Baseline and Current Conditions, Monitoring Progress, Indicator Details
Phase 3: Situation Analysis, Management Approaches
Phase 4: Editing and crosswalks
Phase 5: Full draft circulation and review
Phase 6: PSC review and approval
Phase 7: Public Feedback Period