## (Climate Resiliency) Workplan
Outcome: Climate Adaptation
Goal: Climate Resiliency
Outcome: Continually puruse, design and construct restoration and protection projects to enhance the resiliency of the Bay and aquatic ecosystems from the impacts of coastal erosion, coastal flooidng, more intense and more frequent storms and sea level rise.
Long term Target: ...by 2025
2 year Target: ...by 2016
Management Approach 1: Compile and assess current efforts and lessons-learned
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Current Efforts Activities underway or proposed that could support key action | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy | Funding Proposal Concepts
Compile and assess lessons learned from past and ongoing adaptation planning and programmatic efforts within the Chesapeake Bay Watershed. | Working from Appendix B, compile an expanded list of current planning and programmatic efforts that support key elements of the Management Strategy. |  | Climate Resiliency Work Group; STAC; STAR | [6 empty] | AD#1
| Design assessment tool |  | Partner x | [6 empty] | option 2
| Conduct 75 assessments and 45 construction designs |  | Jurisdiction x | [6 empty] | option 3
|  |  | Jurisdiction x | [6 empty] | option 4
|  |  | Jurisdiction x | [5 empty] | Funding Proposal Concepts
| Assess status of proposed federal actions indentified in the 2010 “Strategy for Protecting and Restoring the Chesapeake Bay Watershed” (Federal Leadership Committee for the Chesapeake Bay, 2010) . | [8 empty] | AD#2/MA#3
| Prepare a synthesis of key lessons learned from past and current efforts. | [8 empty] | AD#3/MA#1
| Develop methdology for updating list and synthesis on a continual basis. | [8 empty] | AD#4
Share current efforts, including policy, tools, products, and scientific understanding with all interested parties engaging in adaptation work or discussions. | Develop an information portal or central data/project database.
| Host a "Chesapeake Bay Climate Adaptation Workshop" or offer "Climate Adaptation" sessions at other appropriate regional forums and conferences. |  | CBP with NGO and Academic Partners
Management Approach 2: Assess climate impacts and vulnerabilities
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Current Efforts Activities underway or proposed that could support key action | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Compile a state-of-the-science synthesis of climate change impacts, vulnerabilities and adaptation strategies. | Conduct a review and update of 2008 Scientific and Technical Advisory Committee (STAC) report “Climate Change and the Chesapeake Bay, State-of-the-Science-Review and Recommendations” |  | STAR & STAC
Management Approach 3: Review and revise conservation, restoration and protection goals and objectives.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Current Efforts Activities underway or proposed that could support key action | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Revise or reconsider Watershed Agreement Management Strategies to accommodate anticipated climate-related changes or impacts. | Develop a science-based framework to engage one-on-one with GITS to identify, assess, evaluate and revise, as necessary, climate-related elements of individual management strategies.
| Develop a climate change conservation analysis matrix to enable analysis of existing management goals and outcomes | Coastal SEES: Chesapeake Bay Sustainability: Implications Of Changing Climate And Shifting Management Objectives - A National Science Foundation funded collaborative project lead by VIMS that aims to develop an advanced modeling framework that integrates the physical, biogeochemical, and human components needed to simulate and select climate change adaptation strategies that will support a sustainable system. | EPA, STAC, CBP, Work Group
| Develop a decision framework to identify climate change effects on the performance of specific management practices (i.e., BMP’s), restoration actions, and protection measures |  | Climate Work Group; Individual GITs
| Incorporate specific or revised climate change goals into 2015-16 Forest Action Plans |  | USFS
Management Approach 5: Increase the institutional capacity of the Chesapeake Bay Program to prepare for and respond to climate change
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Current Efforts Activities underway or proposed that could support key action | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Build the capacity among the Chesapeake Bay Program partnership to understand and address the consequences of climate change. | Compile a compendium of guidance on implementation of climate change science within adaptation decision making processes.
Inform decision-makers and stakeholders of the data, tools, resources and support to assess climate vulnerability and develop adaptation strategies.
| Compile and synthesyze available data, tools and resources that can be used to support vulnerability assessments | Collaborators in the NE Vulnerability Assessment (USFWS) have developed a Climate Change Vulnerability Index (CCVI) to provide a rapid, scientifically defensible assessment of species' vulnerability to climate change.
Develop list of policy, programmatic and regulatory enhancements that will increase capacity
Develop an Adaptation Network and Collaboration Strategy focused on increasing opportunities for formal and informal communication and the exchange of ideas among the Chesapeake Bay watershed’s existing “adaptation planning network.” | Develop a comprehensive framework and list of organizations within the “Chesapeake Bay Adaptation Network”
Create "communities of practice" around specific adaptation planning areas
Increase participation of regional collaborations of local governments and other stakeholders | Identify cross-state assessments |  | Greater Baltimore Wilderness Coalition; Metro Washington COG; USDA Climate Hubs; LCC's
Management Approach 6: Implement priority adaptation actions
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Current Efforts Activities underway or proposed that could support key action | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Plan and implement restoration and protection efforts that build community and ecosystem resilience within the Bay watershed | Compile climate-related siting and design guidance for on-the-ground protection and restoration projects
| Identify funding availability, needs and mechanisms | VA Climate Change and Resiliency Update Commission (created in 2014) to review, update, and prioritize the recommendations of VA's 2008 Climate Change Action Plan and to identify sources of revenue to fund the implementation.
Identify and assess institutional barriers
Explore mechanisms to encourage the integration of climate change consideratios in the design and implementation of on-the ground "resiliency" projects
Pursue specific adaptation projects to enhance the resiliency of Bay and aquatic ecosystems from the impacts of coastal erosion, coastal flooding, more intense and more frequent storms and sea level rise. | Implement 1-2 on the ground adaptation or "resiliency" projects in the Chesapeake Bay watershed | NOAA is concentrating its resources to improve and sustain the ecological health of the Delmarva/Choptank River Complex. This could be a good location to see how habitat can be a part of increased coastal resilience. One key objective for the Choptank Habitat Focus area is to improve the decision-making and resilience of coastal communities by improving the delivery of NOAA’s habitat and climate science. | Note: This will be a major undertaking on the part of the Partnership and an effort that will be carried out, most likely by participating partners, agencies, local government and stakeholders.
Management Approach 7: Track adaptation action effectiveness and ecological response
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Current Efforts Activities underway or proposed that could support key action | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Establish performance metrics to assess progress | Identify how lessons learned from implementation of priority actions will support the feedback loop
| Track public and local stakeholer opinion of actions as well as ecological response |  | GMU, Climate Change Communication Consortium
Management Approach 8: Increase Local Engagement
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Current Efforts Activities underway or proposed that support key action | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Incorporate Information regarding climate adaptation into the Management Strategy for the Local Leadership Outcome, as appropriate.
Management Approach 9: Undertake Public and Stakeholder Engagement
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Current Efforts Activities underway or proposed that could support key action | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Conduct targeted conversations, focus groups and other appropriate mechanisms, with stakeholder groups that may help to establish and implement Adaptation Outcome priorities. | Engage Local governments and natural resource groups alongside the broader community.
Engage stakeholders through existing community development, economic development, floodplain management, shoreline protection, hazard and flood mitigation, emergency management, and coastal zone management programs.
Management Approach 10: Foster a larger discussion on the linkage between climate impacts and diversity
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Current Efforts Activities underway or proposed that could support key action | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Ensure that a diverse group of local stakeholders are engaged in discussion related to climate change and the Chesapeake Bay. | Identify mechanisms that can increase community engagement and provide communities and diverse stakeholders with a voice and opportunity to engage in climate adaptation planning and policy decision-making processes for their communities | NPS could add an interpretive component to climate change vulnerability assessments being conducted for each park. | Diversity Action Team
| Explore effective formal and informal education tools to increase climate resilience literacy among multiple audiences in the Bay. | MD to add a "diversity climate change" filter to BMP targeting efforts | MD
| Undertake a pilot project with diverse communities vulnerable both physically and socially |  | GMU, Climate Change Communication Consortium
Management Approach 11: Conduct Targeted Education and Outreach
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Current Efforts Activities underway or proposed that could support key action | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Provide both practitioners (including consultants) and the general public the opportunity to learn about adaptation science, approaches, and demonstration projects and feel empowered to have a voice in the decisions being made in their communities. | Release a periodic “special issue” newsletter to disseminate adaptation-related information.
| Engage the Stewardship Work Group in support of climate outreach and education. | Chesapeake Bay NERRS Contribution to Climate Change (Stewardship) - NERRS to provide educational opportunities and training related to effects of climate change on human and estuarine systems to increase public awareness and foster behavior change.
| Develop broad Chesapeake Bay Program climate messaging, including information on how it integrates climate science into restoration efforts and impacts of climate on restoration work in progress. |  | Collaborate with GMU Science Communication Program and Center for Climate Communcations
Collaborate with the NOAA Mid Atlantic Focus Area Coastal Storms Program to create and disseminate information materials.
Total
Provide support for decision-makers and community leaders to engage on climate change adaptation planning efforts at multiple levels (county, city, state, federal)
Engage the academic community to develop effective collaborative learning approaches for informing and empowering communities across the watershed
Test and develop new communication tools that are audience specific so that climate information is accessible and understandable across multiple audiences and communities. |  | In 2015, the NOAA Coastal Storms Program will be focusing on the Mid-Atlantic/Chesapeake Bay area and will have a coordinator working in the region. The Program is a nationwide effort to make communities safer by reducing the loss of life and negative impacts caused by coastal storms. Program results often include new data and predictive tools, new ways of keeping the public informed and enlightened, and new partnerships that strengthen existing resilience efforts.