## Slide 1: AgWG Ad Hoc CAST Issues
February 11, 2021

## Slide 2: CAST-21 Workplan (Working Draft) *Approved data and method changes need to be finalized through the WQGIT by Sept. 1, 2021*
KEY ACTION | STATUS
Task 1: Updates to data & methods that typically occur every 2 years. | On-going In process: “Rules of the Road” document for data submissions
Task 2: Investigate alternative forecasting methods for ag land uses & animals | Nov 19 AgWG: CBPO presentation on 4 methods of forecasting Feb AgWG; Decision Mar AgWG
Task 3: Investigate 2012-2017 Ag Census change for fallow/idle acres | AgWG Sept 17; NASS consulted; no new information; No further action; Decision Jan AgWG*
Task 4: Investigate use of latest landcover & LiDAR imagery to better define changes in total ag (& other land use) acres | Oct 15 AgWG; Jan AgWG; Feb AgWG; Decision Mar AgWG
Task 5: Investigate alternatives for double-crop acre estimates | Oct 15 AgWG; NASS consulted- no new information; No further action; TASK COMPLETED? Decision Mar AgWG
Task 6: Consider supplemental NM for soybeans | In process Dec Ad Hoc; Jan Ad Hoc; Mar Ad Hoc discussion
Task 7: QA/QC’d historic & current layer pop. data for Hillandale Farms (PA) | In process Feb Ad Hoc- general discussion
Task 8: Build-in Verification Ad Hoc Team products | In process
Questions/Comments?
TODAY
*Decision: The AgWG reached consensus regarding CAST-21 Workplan Task 3: Investigate 2012-2017 Ag Census change for fallow/idle acres, recognizing that the 5-year census indicates a significant increase in fallow & idle acres within some counties in the Chesapeake Bay watershed. The AgWG acknowledges that investigation has not provided evidence to indicate that the 2017 Ag Census data is or is not reflective of on-the-ground change, therefore cannot recommend adjustment to CAST-21 model inputs at this time. The AgWG has exhausted its available resources to investigate this issue, but this decision does not preclude interested parties from pursuing further lines of inquiry and bringing information back to the workgroup for review.

## Slide 3
Animal Data
Animal Populations: explore other estimating options (MD/NY; Task 1)
Crop Production/Acres
Crop Production Acres: improve annual estimates (MD; Task 1)
Nutrient Applications/Assumptions
Fertilizer Sales and Use Data (MD; Task 1)
BMP Tracking & Reporting
Dairy Precision Feeding (PA)
BMP Effectiveness/Modeling
Winter Crop (NY/PA)
Manure Transport / Manure Treatment Technologies (PA)

## Slide 4
Animal Data
Animal Populations: explore other estimating options (MD/NY; Task 1)
Crop Production/Acres
Crop Production Acres: improve annual estimates (MD; Task 1)
Nutrient Applications/Assumptions
Fertilizer Sales and Use Data (MD; Task 1)

## Slide 5: Improving Ag Data? (TASK 1)
CRITICAL CONCEPT:
To maintain integrity of CBWM there are two options for new data sets:
Provide data all the way back through 1985.
OR
Use the trend in new data sets for the years available.
CBWM= Chesapeake Bay Watershed Model
Crop Acreage Data
Alternative methods to account for fitting Ag Census data to CBP needs?
  Adjusting methods for estimating crop acres (e.g. double crops)
Alternative/supplemental data sets
  Other data sets at the state or federal level?
Animal Population Data
Additional NASS Annual Survey Data may be available to inform population trends between census years (incorporated every two years)
  Dairy, Beef Cattle, Layers, Swine…
Direct from industry data can inform animal population trends between census years.
  Requires careful cooperation
  Legal, privacy assurances
Other Data Issues (new data incorporation every 2 years)
Soil P data
  Gary Shenk Sept 2018 presentation to AgWG on data set incorporated into the CBWM
  Additional soil P data is welcome and encouraged (NY & WV have made inquiries)
    Contact Gary Shenk
Manure Nutrient Concentration Data
  Changes in management may result in changes in nutrient concentrations
  Additional manure concentration data is welcome and encouraged
  Fertilizer Data
  More accurate allocation of fertilizer within the CBW?
    Jurisdictions working with state chemists
      Understand/clean up data sent to AAPFCO
Crop Application Goal
Manure Generated
4. Define Inorganic Fertilizer Available to Crops
TODAY
UPDATES?

## Slide 6
BMP Tracking & Reporting
Dairy Precision Feeding (PA)

## Slide 7
BMP Effectiveness/Modeling
Winter Crop (NY/PA/MD)
Manure Transport / Manure Treatment Technologies (PA/MD)

## Slide 8
Feb 18 AgWG
  Discussion Landcover/ LiDAR Data (Task 4)
  Discussion Forecasting Ag Trends (Task 2)
March Ad Hoc:
  Updates on NM soybean issue (Task 6)
  Clarify Winter Crop Proposal?
March 18 AgWG
  Decision Forecasting Ag Trends (Task 2)
  Decision Landcover/ LiDAR Data (Task 4)
  Decision Double Crop methods (Task 5)

## Slide 10
BMP Concern | CBP BMP Effectiveness Source | Next Steps
Dairy Precision Feeding (PA) | Definitions and reductions approved by the WQGIT in 2009 | PA Action Team
Rotational/Prescribed Grazing (PA) | Definitions and benefits were reviewed and approved by the Agriculture Workgroup and WQGIT in 2010 | RESOLVED
Heavy Use Area Protection- NRCS 561 (PA) | Loafing Lot Management definitions and reductions approved by the Chesapeake Bay Program’s Nutrient Subcommittee in 2003. | RESOLVED
Nutrient Management on Pasture (NY/PA) | Nutrient Management Practices for use in the Phase 6.0 Chesapeake Bay Program Watershed Model (2016) | RESOLVED
Commodity Cover Crops Winter Crop (NY/PA) | Cover Crops Practices for use in Phase 6 of the Chesapeake Bay Watershed Model (2016) | EP Chair discussion with AgWG (Dec 2020) AgWG presentation Charlie White (Jan 2021)
Manure Transport / Manure Treatment Technologies (PA) | Manure Treatment Technologies: Recommendations from the Manure Treatment Technologies Expert Panel to the CBP’s WQGIT to define Manure Treatment Technologies as a Best Management Practice (2016) Manure Transport: definition and benefits have remained in use since review and approval by the CBP partnership’s source sector workgroups for tributary strategy development. | Work with MWG
Protocol for the Development, Review, and Approval of Loading and Effectiveness Estimates for Nutrient and Sediment Controls in the Chesapeake Bay Watershed Model

## Slide 11: What is driving these N load concerns?
Agricultural Loading Rates? VA
Ag Census (i.e. Source Of Crop Data) DE
The NM BMP Recommendations? PA
  NM Expert Panel Members (Phase 6)
    Response From 2 of 6
    Changed Professional Status, Lack Context (it’s been 5 or 6 years…)
  Changing An Approved EP Recommendation Must Follow Science (BMP protocol)
    Protocol for the Development, Review, and Approval of Loading and Effectiveness Estimates for Nutrient and Sediment Controls in the Chesapeake Bay Watershed Model

## Slide 12: Agricultural Loading Rates
Based on available literature & best professional judgement
“N losses from soybeans are only somewhat lower than corn, because N fixation inputs (which are poorly characterized) are apparently substituting for fertilizer inputs.” (p.11)

## Slide 13: Census of Agriculture
Accuracy of Ag Census crop acres questioned
  spatially distributed land use from the Land Cover/Land Use data team starting with the CAST-21 could be an improvement
Method of modeling double-crop soybeans approved by CBP partnership
  Determined sound by USDA-NASS

## Slide 14: NM Expert Panel Recommendations
Soybeans NM controlling for P (not N)
LGUs do not recommend N application on soybeans BUT…
  Real-world N application occur
  Crop Application Goal @ 0.12 lbs N/bu  CBW avg 3.58 lbs N/ac
Core N NM available
  Reduces modeled N application
Supplemental N NM NOT available
  Timing & Placement of excess N irrelevant (still subject to loss)
  Rate? Excess N reduced is still excess N subject to loss…

## Slide 15
1.Define Crop Application Goal
A
Crop Application Goal/Yield Unit
B Yields/Acre
C
Acres
Crop Application Goal
2. Define Manure Available to Crops
Manure Generated
Direct Deposition on Pasture
Direct Deposition to Riparian Pasture Areas
Deposited within Barnyard
Storage and Handling Loss
Stored Manure
Manure Transport
Feed Additive BMPs
Volatilization
Available for Application
Barnyard BMPs
Ammonia Reduction BMPs
Available for Transport
Mineralization
3. Spread Manure to Crops
4. Define Inorganic Fertilizer Available to Crops
5. Spread Fertilizer to Crops
Ag Census or
NASS Annual Surveys
(Animal populations dictate manure load estimates)
A AMS
B NASS Annual Survey
C Ag Census
AAPFCO Fertilizer Sales Data
Allocation of Ag Nutrients in the Watershed Model
AMS= Agricultural Modeling Subcommittee
https://www.dreamstime.com/stock-images-square-peg-round-hole-image12777364

## Slide 16: Source for distribution of statewide populations can change.
  Example: Pennsylvania provides fraction of cattle in every county for the year 2019, and these fractions are used to distribute TOTAL statewide cattle populations from the Census of Agriculture.
Census
100 Cattle
County A
35%
Outside Watershed
15%
County C
50%
County B
0%
PA Data
(75 Cattle)
100 Cattle
County A
25%
Outside Watershed
25%
County C
40%
County B
10%
Source of TOTAL statewide populations will not change for Phase 6 Watershed Model.
CRITICAL CONCEPT