## Sheet1
Agriculture Workgroup Rolling Master 2017 Timeline DRAFT 10/18/17
Panels Key:
Panel convenes, deliberates, and drafts report.
Panel releases report. Coordinator and chair usher it through partnership approval.
WQGIT approval.
Group: | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | Additional Notes
Agriculture Workgroup | Conference Call 7/20: Decision: Revised draft Phase 6 E3 and No Action Scenarios Discussion: Fatal Flaw review of Phase 6 model and review of inputs. | Face-to-Face Meeting 8/3: Decision: Agreement on recommendations for Phase 6 model input and fatal flaw review. Face-to-Face Meeting 8/17: Decision: Finalization of Expert Panel Establishment Group to develop scope and charge for Ag Stormwater and Nursery Tailwater Panel. Conference Call 8/24: Decision: Approve final version of Phase 6 No Action & E3 Scenarios. Discussion: Applicability of APLE for soil P across land uses Decision: Approval of AMS recommendations | Face-to-Face 9/20: Decision: Potentially distinguishing nursey capture and resuse practices as a separate EPEG Decision: Approval for Agricultural Stormwater and Nursery Capture Reuse interim BMP representation Decision: Approval of temporary hiatus for AMS Briefing: Update on development of alternatve BMP verification evaluation standards for producer surveys | Conference Call 10/19: Decision: Approval of Animal Mortality Management EPEG membership Briefing: Update on Phase 6.0 Model and timeline Decision: Approval of representation of Agricultural Stormwater Interim BMP in NEIEN Decision: Approval of representation of Nursery Capture and Reuse Interim BMP in NEIEN | Face-to-Face 11/16: Briefing: Phase 6 model scenarios intended to be used in Phase III WIP process Decision: Approval of Nursery Capture and Reuse EPEG membership | The following actions and decisions resulted from the September 20th meeting: DECISION: The AgWG approved the EPEG’s initial recommendation for enabling the group to focus on the development of a report specifically for agricultural stormwater management practices associated with agricultural livestock production areas. The AgWG agreed to separately convene an EPEG for nursery capture and reuse management practices associated with nursery production acreages. DECISION: The AgWG approved the CBPO recommended interim BMP definitions and effectiveness values for agricultural stormwater practices for future planning purposes only. ACTION: The AgWG will work to develop an interim BMP reporting mechanism for tracking nursery capture and reuse practices in Phase 6. ACTION: AgWG members should submit comments on the BMP verification standards for producer surveys draft report to Mark Dubin (mdubin@chesapeakebay.net) by the end of October. DECISION: The AgWG approved a proposal to temporarily place the AMS on hiatus, but retain a placeholder structure for the subcommittee for reactivation by the Workgroup for future Phase 6 model updates.
Ag Modeling Subcommittee (AMS) |  | 8/18: 1) Discuss/approve USDA crop nutrient tool removal data for use in recalibrated Phase 6 Model. 2) Discuss change to stream exclusion default stocking rate when no stocking rate is provided. 8/24 AgWG: Decision: Approval of AMS recommendations | 9/17: The AgWG made a decision to temporarily place the AMS on hiatus until further notice. |  |  | 9/17: The AgWG made a decision to temporarily place the AMS on hiatus until further notice.
Cropland Irrigation Panel | Panel holds regular conference calls. | Panel holds regular conference calls. | Panel holds regular conference calls. | Panel holds regular conference calls. | Panel holds regular conference calls.
Agricultural Ditch Panel | Panel holds regular conference calls. | Panel holds regular conference calls. | Panel holds regular conference calls. | Panel holds regular conference calls. | Panel holds regular conference calls.
Agricultural Stormwater EPEG |  | AgWG 8/17: Decision: Finalization of Expert Panel Establishment Group membership to develop scope and charge for panel. | AgWG 9/20: Decision: Interim approval for Agricultural Stormwater Management interim BMP | AgWG 10/19: Briefing: Update on agricultural stormwater interim BMP |  | The proposed membership for the panel EPEG was approved by the AgWG during their August 17th, 2017 meeting, and the EPEG has met twice since that time.
Mortality Management EPEG |  |  |  | AgWG 10/19: Decision: Confirmation of EPEG membership |  | Panel coordinator has compiled the proposed membership to serve on an EPEG to draft panel charge and scope. The membership will be presented for AgWG approval during their 10/19 meeting.
Nursery Capture and Reuse EPEG |  |  |  |  | AgWG 11/16: Decision: Confirmation of membership | Panel coordinator is working to compile proposed membership to serve on an EPEG to draft panel charge and scope. Membership will be presented for AgWG approve on 11/16.