## Monitoring & Assessment
b
Outcome: Monitoring and Assessment | [6 empty] | Funding Priorities
Goal: Climate Resiliency | [7 empty] | Priority #1
Outcome: Continually monitor and assess the trends and likely impacts of changing climatic and sea leel conditions on the Chesapeake Bay ecosystem, including the effectiveness of restoration and protection policies, programs and projects | [7 empty] | Priority #2
Long term Target: ...by 2025 | [7 empty] | Priority #3
2 year Target: ...by 2016 | [7 empty] | Priority #4
Management Approach 1: Define Goals and Establish Baselines
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Individual Partner Efforts Activities underway or proposed that support key action or performance target | Collective Effort - Activity to be led by CBP or Climate Resiliency Work Group | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step)
Establish baselines for the monitoring, modeling, and assessment of different aspects of climate change | Develop methodogy and assessment tool (i.e., matrix) to analyze climate related factors for individual Management Strategies |  | Collective Effort/Funding Priority #1
| Develop a process for coordination with and among individual GITs, the larger research community and stakeholders to identify the linkages of climate to each outcome |  | Collective Effort/Funding Priority #1
| Select several (<2) Management Strategies to conduct thorough documentation and evaluation |  | Collective Effort/Funding Priority #1
| Perform analysis using methodology and process developed above. |  | Collective Effort/Funding Priority #1
| Identify climate related factors, metrics and/or indicators for all Management Strategies |  | Collective Effort/Funding Priority #1
Management Approach 2: Prioritize climate impacts
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Individual Partner Efforts Activities underway or proposed that support key action or performance target | Collective Effort Activity to be led by CBP or Climate Resiliency Work Group | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step)
Conduct an evaluation of existing data, research, studies, tools, as they relate to climate and the needs for select management strategies. |  |  | Collective Effort/Funding Priority #1
|  | MWCOG tracks local government and water agency climate adaptation efforts in the MWCOG region. |  |  | MWCOG | ongoing
Determine climate impacts most critical to outcome attainment. | Establish "climate impact" priorities for select management strategies |  | Collective Effort
Management Approach 3: Design monitoring and modeling plan
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Individual Partner Efforts Activities underway or proposed that support key action or performance target | Collective Effort Activity to be led by CBP or Climate Resiliency Work Group | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step)
Determine if the monitoring data being collected and the tools that are available can answer answer assessment tool questions | Evaluate existing monitoring data and available assessment tools to determine if they are adequate to fully explain the relationship of the future impact of climate on the outcome. |  | Collective Effort | Climate Work Group In coordination with GITs
| Define likely current and future monitoring needs by geography, habitat type, and BMP |  | Collective Effort
Develop an integrated monitoring and assessment plan, including necessary forecast and/or projection models, for priority aspects of climate change. | Develop a monitoring plan and research agenda for the prioritized gaps that have been identified in terms of assessment tools, scientific understanding, and baseline monitoring. |  | Collective Effort
| Identify costs associated with closing those gaps |  | Collective Effort
| Identify agencies/organizations through which commitments could be sought to achieve long-term monitoring. |  | Collective Effort
Management Approach 4: Assess Trends and Conduct Assessments
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Individual Partner Efforts - Activities underway or proposed that support key action or performance target | Collective Effort - Activity to be led by CBP or Climate Resiliency Work Group | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step)
Establish uniform climate change projections for CB Watershed | Facilitate a STAC Workshop to develop a recommended set of climate projections for use in Chesapeake Bay Program assessments |  | Collective Effort | Scientific and Technical Advisory Commitee | Watershed-Scale | Conduct Workshop - January 2016; Draft Workshop Report - March 2016; Final Workshop Report - April 2016
| Compile regional climate projections, forecasts and scenarios and determine appropriate mechanism for public access and CBP Program utility | The District of Columbia recently published a set of projections in temperature and precipitation for the DC metro area: http://green.dc.gov/publication/climate-projections-scenario-development |  | District of Columbia | DC metro area
Assess trends and document observed changes in sea level, precipitation patterns, bay temperature, and the ecosystem responses. | Synthesize latest scientific research on bay acidification and potential impact on CB waters | MD's Bay Acidification Task Force addressed how changing Bay chemistry negatively impacts Maryland’s coast and shellfish industry. The Task Force studied and assessed water quality in Maryland’s Chesapeake and coastal bays, and reviewed ocean acidification studies and findings from other states. The group presented recommendations for monitoring and addressing acidification, and its effects on Maryland’s commercial fishery and aquaculture industry in January, 2015. |  | Work Group; Federal Agencies and State Agencies; Academic Partners
Chesapeake Bay Climate Sensitivity Assessment: using weather, water, biological, and climate data from a variety of sources and a state of the art biophysical model (the Chesapeake Bay Ecological Prediction System) to address the needs and goals of the Chesapeake Bay NERRS, the Chesapeake Bay Program, and NOAA’s Chesapeake Bay Sentinel Site Cooperative. http://coastalscience.noaa.gov/about/centers/col
Chesapeake Bay NERRS can contribute to scientific understanding of climate change and monitor ecosystem changes. NERR's could assess climate change impacts on human and estuarine ecosystem communities, vulnerability of these communities, and their capacity for adaptation and mitigation.
In 2011, NOAA selected the Chesapeake Bay as one of five initial regional Sentinel Site Cooperatives to demonstrate the value of using a place-based approach to address issues of local, regional and national significance. The Coop provides integrated observations across a host of environmental monitoring programs within the Bay area. The goal of the cooperative is to provide information to Chesapeake Bay communities and managers who need to address challenges such as storm flooding, long term, local sea level rise, barrier island movement, degraded water quality, and wetland loss.
Coastal SEES: Chesapeake Bay Sustainability: Implications Of Changing Climate And Shifting Management Objectives - A National Science Foundation funded collaborative project lead by VIMS that aims to develop an advanced modeling framework that integrates the physical, biogeochemical, and human components needed to simulate and select climate change adaptation strategies that will support a sustainable system. The National Science Foundation - Science, Engineering and Education for Sustainability (SEES) Program provides a funding mechanism to advance science, engineering, and education to inform the societal actions needed for environmental and economic sustainability and sustainable human well-being.
|  | PA Act 70 of 2008 requires PA DEP to report on PA Climate Impacts and Assessment, a report that is required to be updated every 3 year. PSU researchers have been contracted to provide an assessment report to PA DEP. The most current report was updated in August 2015 (still draft and accepting comments through November 2015). |  | PA DEP | PA | Draft updated in 2015 (still draft) and requirement for updating every 3 years.
Management Approach 5: Develop a Research Agenda
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Individual Partner Efforts Activities underway or proposed that support key action or performance target | Collective Effort Activity to be led by CBP or Climate Resiliency Work Group | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step)
Compile list of data and research needs. | Catalog current data, research, studies and tools for select Mgmt. Strategies | Landscape Conservation Cooperatives are partnerships between federal agencies, states, tribes, non-governmental organizations, universities, and other entities to collaboratively define science needs and jointly address broad-scale conservation issues, such as climate change in a defined geographic area. |  | Climate Work Group; Select Work Groups; STAC
Conduct a gap analysis for select Mgmt. Strategies using the catalog of data, research and tools
Conduct a review of existing data and research needs assessment and status of implementation and identify outstanding needs and prioirties related to CB Management Strategy Goals and Outcomes
Conduct targeted research to improve understanding of cliimate impacts or fill critical data or research gaps. | Evaluate climate change mitigation and adaptation benefits of water quality BMPs for forest, ag and urban sectors |  | Collective Effort/ Funding Priority #2
|  | PA to implement Urban and Community Forestry Initiative, resulting in a draft plan which seeks to utilize the planting and maintenance of trees in urban and community settings to increase carbon storage and to reduce residential, commercial, and institutional energy use for heating and cooling purposes. |  | PA DEP/PA DCNR | PA
Identify climate "hot spot" areas that threaten the bay and local communities or infrastructure for monitoring
Management Approach 6: Reassess priorities and revise goals
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Individual Partner Efforts Activities underway or proposed that support key action or performance target | Collective Effort Activity to be led by CBP or Climate Resiliency Work Group | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step)
Review progress on a biennial basis, with particular emphasis on evaluating progress toward the closing of gaps in baseline monitoring and gaps in assessment tools and scientific research. | Re-prioritize gaps that remain in monitoring and scientific understanding.
Management Approach 7: Undertake Public, Stakeholder and Local Engagement
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Individual Partner Efforts Activities underway or proposed that support key action or performance target | Collective Effort Activity to be led by CBP or Climate Resiliency Work Group | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step)
Increase availability and access to monitoring and assessment data to support stakeholder discussions on the socioeconomic impacts of climate change on the Bay. | Collaborate with stakeholders in the development of data synthesis products for their use.
| Develop climate data and information portal |  | Collective Effort/ Funding Priority #3
| Participate in 3-5 regional climate workshops or public events to increase awareness | MWCOG is positioned to help disseminate information to metro Washington local government staff and stakeholders through existing committees or website posts.

## Adaptation
Outcome: Climate Adaptation | [6 empty] | Funding Priorities
Goal: Climate Resiliency | [7 empty] | Priority #1
Outcome: Continually puruse, design and construct restoration and protection projects to enhance the resiliency of the Bay and aquatic ecosystems from the impacts of coastal erosion, coastal flooidng, more intense and more frequent storms and sea level rise. | [7 empty] | Priority #2
Long term Target: ...by 2025 | [7 empty] | Priority #3
2 year Target: ...by 2016 | [7 empty] | Priority #4
Management Approach 1: Compile and assess current efforts and lessons-learned
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Individual Partner Efforts Activities underway or proposed that support key action or performance target | Collective Effort Activity to be led by CBP or Climate Resiliency Work Group | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step)
Compile and assess lessons learned from past and ongoing adaptation planning and programmatic efforts within the Chesapeake Bay Watershed. | Working from Appendix B, compile an expanded list of current planning and programmatic efforts that support key elements of the Management Strategy. | MWCOG tracks local government and water agency climate adaptation efforts in the MWCOG region. MWCOG is positioned to help identify sources for this goal. |  | MWCOG | MWCOG
|  | PA Act 70 of 2008 requires PA DEP to report on PA Climate Impacts and Assessment, a report that is required to be updated every 3 year. PSU researchers have been contracted to provide an assessment report to PA DEP. The most current report was updated in August 2015 (still draft and accepting comments through November 2015). |  | PA | PA | update every 3 years
|  |  | Collective effort, Funding Priority #3 | Climate Resiliency Work Group; STAC; STAR
| Assess status of proposed federal actions indentified in the 2010 “Strategy for Protecting and Restoring the Chesapeake Bay Watershed” (Federal Leadership Committee for the Chesapeake Bay, 2010) . |  | Collective Effort | Federal Leadership Committee Designees | Chesapeake Bay Watershed | 2016-03-31
Prepare a synthesis of key lessons learned from past and current efforts.
Develop methdology for updating list and synthesis on a continual basis.
Share current efforts, including policy, tools, products, and scientific understanding with all interested parties engaging in adaptation work or discussions. | Develop an information portal or central data/project database. |  | Collective effort, Funding Priority #3
|  | State of VA Climate Change Information Portal |  | State of Virginia
| Conduct targeted listening sessions in select geographic locations | PA is currently conducting 14 listening sessions across PA to hear comments from citizens regarding the development of Pennsylvania's plan to comply with the Federal Clean Power Plan. DEP plans to submit a draft plan to EPA by September 2016 |  | Pennsylvania | statewide | 2015-2016
| Host a "Chesapeake Bay Climate Adaptation Workshop" or offer "Climate Adaptation" sessions at other appropriate regional forums and conferences. |  | Collective Effort | CBP with NGO and Academic Partners
|  | Maryland Sea Grant: Climate Change Research Forum to be held in December 2015 |  | Maryland Sea Grant |  | December, 2015
Management Approach 2: Assess climate impacts and vulnerabilities
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Individual Partner Efforts Activities underway or proposed that support key action or performance target | Collective Effort Activity to be led by CBP or Climate Resiliency Work Group | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step)
Compile a state-of-the-science synthesis of climate change impacts, vulnerabilities and adaptation strategies. | Conduct a review and update of 2008 Scientific and Technical Advisory Committee (STAC) report “Climate Change and the Chesapeake Bay, State-of-the-Science-Review and Recommendations” |  |  | STAR & STAC
|  | PA Act 70 of 2008 requires PA DEP to report on PA Climate Impacts and Assessment, a report that is required to be updated every 3 year. PSU researchers have been contracted to provide an assessment report to PA DEP. The most current report was updated in August 2015 (still draft and accepting comments through November 2015). |  | PA DEP | Pennsylvania | update every 3 years
|  | Coastal SEES: Chesapeake Bay Sustainability: Implications Of Changing Climate And Shifting Management Objectives - A National Science Foundation funded collaborative project lead by VIMS that aims to develop an advanced modeling framework that integrates the physical, biogeochemical, and human components needed to simulate and select climate change adaptation strategies that will support a sustainable system. |  | VIMS, Coastal SEES
Management Approach 3: Review and revise conservation, restoration and protection goals and objectives.
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Individual Partner Efforts Activities underway or proposed that support key action or performance target | Collective Effort Activity to be led by CBP or Climate Resiliency Work Group | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step)
Revise or reconsider Watershed Agreement Management Strategies to accommodate anticipated climate-related changes or impacts. | Develop a science-based framework to engage one-on-one with GITS to identify, assess, evaluate and revise, as necessary, climate-related elements of individual management strategies. |  | Collective Effort/GIT Funding Priority #1
| Develop a climate change conservation analysis matrix to enable analysis of existing management goals and outcomes |  | Collective Effort/GIT Funding Priority #1 | EPA, STAC, CBP, Work Group
| Develop a decision framework to identify climate change effects on the performance of specific management practices (i.e., BMP’s), restoration actions, and protection measures |  | Collective Effort/GIT Funding Priority #1 | Climate Work Group; Individual GITs
Management Approach 5: Increase the institutional capacity of the Chesapeake Bay Program to prepare for and respond to climate change
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Individual Partner Efforts Activities underway or proposed that support key action or performance target | Collective Effort Activity to be led by CBP or Climate Resiliency Work Group | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step)
Build the capacity among the Chesapeake Bay Program partnership to understand and address the consequences of climate change. | Compile a compendium of guidance on implementation of climate change science within adaptation decision making processes. | Develop a “Flood Avoidance and Design Guidance” document for Delaware state agencies, under Executive Order 41, to use in the development of state projects. |  | State of Deleware | State of Deleware | 2015-12-01
|  | PA to implement the Urban and Community Forestry Initiative. The draft plan seeks to utilize the planting and maintenance of trees in urban and community settings to increase carbon storage and to reduce residential, commercial, and institutional energy use for heating and cooling purposes. |  | PA DEP/DCNR | PA | 2015-2030
| Inform decision-makers and stakeholders of the data, tools, resources and support to assess climate vulnerability and develop adaptation strategies. | NPS Northeast Region collaborators at the University of Rhode Island are developing a vulnerability assessment guidance document for NER parks based on lessons learned from completed and ongoing NER vulnerability assessments and the broader existing literature and resources applicable to coastal parks. A follow up vulnerability assessment building on that guidance for Colonial National Historical Park will begin in 2016. |  | National Park Service | NPS Northeast Region and Colonial NHP | Guidance document in review by end of 2015, final report 2016. Colonial NHP vulnerability assessment estimate completion 2017.
| Compile and synthesyze available data, tools and resources that can be used to support vulnerability assessments | Collaborators in the NE Vulnerability Assessment (USFWS) have developed a Climate Change Vulnerability Index (CCVI) to provide a rapid, scientifically defensible assessment of species' vulnerability to climate change.
Develop list of policy, programmatic and regulatory enhancements that will increase capacity
Develop an Adaptation Network and Collaboration Strategy focused on increasing opportunities for formal and informal communication and the exchange of ideas among the Chesapeake Bay watershed’s existing “adaptation planning network.” | Develop a comprehensive framework and list of organizations within the “Chesapeake Bay Adaptation Network” |  |  | MWCOG
| Create "communities of practice" around specific adaptation planning areas |  |  | SAGE - Chesapeake Bay Pilot
Increase participation of regional collaborations of local governments and other stakeholders | Identify cross-state assessments |  |  | Greater Baltimore Wilderness Coalition; Metro Washington COG; USDA Climate Hubs; LCC's
Management Approach 6: Implement priority adaptation actions
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Individual Partner Efforts Activities underway or proposed that support key action or performance target | Collective Effort Activity to be led by CBP or Climate Resiliency Work Group | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step)
Plan and implement restoration and protection efforts that build community and ecosystem resilience within the Bay watershed | Compile climate-related siting and design guidance for on-the-ground protection and restoration projects
| Identify funding availability, needs and mechanisms | VA Climate Change and Resiliency Update Commission (created in 2014) to review, update, and prioritize the recommendations of VA's 2008 Climate Change Action Plan and to identify sources of revenue to fund the implementation.
|  | PA TreeVitalize |  | PA DEP/DCNR | PA | ongoing
Identify and assess institutional barriers
| Explore and develop mechanisms to encourage the integration of climate change considerations in the design and implementation of on-the ground "resiliency" projects | PA Climate Impacts and Assessment Report |  | Pennsylvania | PA | update every 3 years
|  | Maryland Climate Resiliency Assessment |  | State of Maryland
Pursue specific adaptation projects to enhance the resiliency of Bay and aquatic ecosystems from the impacts of coastal erosion, coastal flooding, more intense and more frequent storms and sea level rise. | Implement 1-2 on the ground adaptation or "resiliency" projects in the Chesapeake Bay watershed |  | NOAA is concentrating its resources to improve and sustain the ecological health of the Delmarva/Choptank River Complex. This could be a good location to see how habitat can be a part of increased coastal resilience. One key objective for the Choptank Habitat Focus area is to improve the decision-making and resilience of coastal communities by improving the delivery of NOAA’s habitat and climate science. | Note: This will be a major undertaking on the part of the Partnership and an effort that will be carried out, most likely by participating partners, agencies, local government and stakeholders.
Management Approach 7: Track adaptation action effectiveness and ecological response
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Individual Partner Efforts Activities underway or proposed that support key action or performance target | Collective Effort Activity to be led by CBP or Climate Resiliency Work Group | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step)
Establish performance metrics to assess progress | Identify how lessons learned from implementation of priority actions will support the feedback loop | PA Climate Impacts and Assessment Report |  | PA DEP | PA | update every 3 years
| Track public and local stakeholer opinion of actions as well as ecological response |  |  | GMU, Climate Change Communication Consortium
Management Approach 8: Increase Local Engagement
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Individual Partner Efforts Activities underway or proposed that support key action or performance target | Collective Effort Activity to be led by CBP or Climate Resiliency Work Group | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step)
Incorporate information regarding climate adaptation into the Management Strategy for the Local Leadership Outcome, as appropriate.
Engage Local governments and natural resource groups alongside the broader community.
Management Approach 9: Undertake Public and Stakeholder Engagement
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Individual Partner Efforts Activities underway or proposed that support key action or performance target | Collective Effort Activity to be led by CBP or Climate Resiliency Work Group | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step)
Conduct targeted conversations, focus groups and other appropriate mechanisms, with stakeholder groups that may help to establish and implement Adaptation Outcome priorities. |  | PA is currently conducting 14 listening sessions across PA to hear comments from citizens regarding the development of Pennsylvania's plan to comply with the Federal Clean Power Plan. DEP plans to submit a draft plan to EPA by September 2016 |  | PA DEP | PA | 2015-16
|  | PA Climate Change Advisory Committee |  | PA DEP | PA - statewide | ongoing
Engage stakeholders through existing community development, economic development, floodplain management, shoreline protection, hazard and flood mitigation, emergency management, and coastal zone management programs.
Management Approach 10: Foster a larger discussion on the linkage between climate impacts and diversity
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Individual Partner Efforts Activities underway or proposed that support key action or performance target | Collective Effort Activity to be led by CBP or Climate Resiliency Work Group | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step)
Ensure that a diverse group of local stakeholders are engaged in discussion related to climate change and the Chesapeake Bay. | Identify mechanisms that can increase community engagement and provide communities and diverse stakeholders with a voice and opportunity to engage in climate adaptation planning and policy decision-making processes for their communities | NPS to add an interpretive component to climate change vulnerability assessments being conducted for each park. |  | National Park Service
|  | MWCOG will help to connect local policymakers and public advisory committees with this type of information. | Collective effort in concert with Diversity Action Team | MWCOG |  | ongoing
| Explore effective formal and informal education tools to increase climate resilience literacy among multiple audiences in the Bay. | Maryland to add a "diversity climate change" filter to BMP targeting efforts |  | State of Maryland
| Undertake a pilot project with diverse communities vulnerable both physically and socially | GMU, Climate Change Communication Consortium - Proposed project
Management Approach 11: Conduct Targeted Education and Outreach
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Individual Partner Efforts Activities underway or proposed that support key action or performance target | Collective Effort Activity to be led by CBP or Climate Resiliency Work Group | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step)
Provide both practitioners (including consultants) and the general public the opportunity to learn about adaptation science, approaches, and demonstration projects and feel empowered to have a voice in the decisions being made in their communities. | Release a periodic “special issue” newsletter to disseminate adaptation-related information.
| Engage the Stewardship Work Group in support of climate outreach and education. | Chesapeake Bay NERRS Contribution to Climate Change (Stewardship) - NERRS to provide educational opportunities and training related to effects of climate change on human and estuarine systems to increase public awareness and foster behavior change. |  | Chesapeake Bay NERRS
| Develop broad Chesapeake Bay Program climate messaging, including information on how it integrates climate science into restoration efforts and impacts of climate on restoration work in progress. | DC-CUSP is working on forming a community of practice on climate change communication. http://www.cuspproject.org/cities/dc#.VfxZh5eVmpQ | Collective effort in collaboration wih many partners, including GMU Science Communication Program and Center for Climate Communcations and the MADE-CLEAR (MD-DE Climate Change Education Assessment and Research) | MADE-CLEAR (MD-DE Climate Change Education Assessment and Research)
| Collaborate with the NOAA Mid Atlantic Focus Area Coastal Storms Program to create and disseminate information materials. | In 2015, the NOAA Coastal Storms Program will be focusing on the Mid-Atlantic/Chesapeake Bay area and will have a coordinator working in the region. The Program is a nationwide effort to make communities safer by reducing the loss of life and negative impacts caused by coastal storms. Program results often include new data and predictive tools, new ways of keeping the public informed and enlightened, and new partnerships that strengthen existing resilience efforts. | Collective effort | NOAA Coastal Storms Program | Chesapeake Bay | 2015-2016
|  | PA is currently conducting 14 listening sessions across PA to hear comments from citizens regarding the development of Pennsylvania's plan to comply with the Federal Clean Power Plan. DEP plans to submit a draft plan to EPA by September 2016 |  | PA |  | 2015-16
Provide support for decision-makers and community leaders to engage on climate change adaptation planning efforts at multiple levels (county, city, state, federal) |  | MWCOG engages members on this topic.
|  | PA Climate Impacts and Assessment Report - engages researchers at PSU |  | PADEP
Test and develop new communication tools that are audience specific so that climate information is accessible and understandable across multiple audiences and communities. |  | DC-CUSP is working on forming a community of practice on climate change communication. http://www.cuspproject.org/cities/dc#.VfxZh5eVmpQ