## Monitoring & Assessment
Outcome: Monitoring and Assessment
Goal: Climate Resiliency
Outcome: Continually monitor and assess the trends and likely impacts of changing climatic and sea level conditions on the Chesapeake Bay ecosystem, including the effectiveness of restoration and protection policies, programs and projects.
Management Approach 1-3: Define Goals and Establish Baselines; Develop Conceptual Monitoring, Modeling and Assessment Model; and Prioritize Climate Impacts
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Timeframe (month/year) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Develop and implement a methodology to establish climate related goals and baselines for individual Chesapeake Bay Agreement Management Strategies. | Select two Management Strategies to conduct thorough documentation and evaluation. | 2016 CBP Funded Project | 2016-01-01
| Complete a Literature Review of existing ecosystem-based climate resiliency approaches, aids (e.g., tables, matrices) and processes or decision making products. | 2016 CBP Funded Project | 2016-05-01
| Compile existing climate change vulnerability research and data, including available assessment products and tools, specific to protected lands and wetlands within the Chesapeake Bay region. | 2016 CBP Funded Project | 2016-06-01
| Design a Climate Resiliency Analysis and Decision-Making Matrix for Protected Lands and Wetlands. | 2016 CBP Funded Project | 2016-07-01
| Facilitate in-person workshops with select Work Groups to: 1) complete Matrix Analysis process and revise, modify, prioritize and select management actions for integration into Management Strategies; and 2) to develop recommendations for augmenting existing Management Strategies through the “Adaptive Management” framework. | 2016 CBP Funded Project | 2017-07-01
| Refine matrix and recommend implementation process for applying matrix analysis and decision-making process to other Management Strategies. | 2016 CBP Funded Project | 2017-09-01
Develop approach to factor climate change considerations into the 2017 Chesapeake Bay TMDL Midpoint Assessment | Conduct a review of the CBP Approach to factor climate change considerations into the 2017 Chesapeake Bay TMDL Midpoint Assessment | Climate Resiliency Workgroup; CBP Modeling Workgroup; STAC | 2016-03-01
| Document approach utilized by CBP to factor climate change considerations into the 2017 Chesapeake Bay TMDL Midpoint Assessment | Climate Resiliency Workgroup; CBP Modeling Workgroup; STAC | 2016-06-01
Management Approach 4: Design Monitoring and Modeling Plan
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Timeframe (month/year) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Identify and evaluate existing monitoring data and models available within federal agencies, state partners, and academic partners, to explain the relationship of the future impact of climate to specific outcomes. | Work with 5-select work groups to determine current and future monitoring needs by geography, habitat type, and BMP. | STAR | 2017-12-01
| Work with 5-select work groups to Identify and evaluate the continuity of existing monitoring data and models | STAR | 2017-12-01
Catalogue monitoring and modeling gaps for 4 select CB Agreement Management Strategies | Outline gaps at work group or GIT level. | STAR | 2017-12-01
| Outline gaps for watershed-scale modeling efforts. | STAR | 2017-12-01
| Outline gaps for watershed scale monitoring effort, including gaps related to monitoring of non-climate stressors that could exacerbate climate impacts to Chesapeake Bay habitat or BMPs. | STAR | 2017-12-01
Explore gap filling measures or solutions | Explore the use of citizen-based monitoring networks. | STAR | 2017-12-01
| Identify and examine groups using new technology and assessment methods for tracking climate factors. | STAR | 2017-12-01
| Participate in regional climate forums for networking and identifying new partnership opportunities. | STAR | 2017-12-01
Develop a plan to fill identified gaps. | Identify costs associated with closing those gaps. | STAR | 2017-12-01
| Identify agencies/organizations through which commitments could be sought to fund or participate in closing those gaps. | STAR | 2017-12-01
| Identify geographical overlap in monitoring and modeling efforts to explore opportunities for cost saving efficiencies and integration of priorities to include climate factors. | STAR | 2017-12-01
Management Approach 5: Assess past and future trends in sea level, precipitation patterns, temperature and ecosystem response
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Timeframe (month/year) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Establish guidance on the application of climate change scenarios, projections and realizations for CBP assessments. | Evaluate applicability of international, national, regional and state climate scenarios, projections, forecasts and assessments for use in CBP assessments. | STAC Workshop | 2016-02-01
| Facilitate a workshop to develop process for establishing a recommended set of climate projections for use in Chesapeake Bay Program assessments. | STAC Workshop | 2016-02-01
Conduct a literature review and synthesis of latest scientific research on past and future climate change impacts on the Chesapeake Bay, as was done in the 2008 STAC report. | Compile and assess international, national, regional and state-level, including DE, MD, PA, WV, VA, NY, DC climate change assessments. | CRWG/ STAC Synthesis Team
| Synthesize latest scientific research on sea level and water level trends; precipitation and evapotranspiration; and temperature change in both air and water. | CRWG/ STAC Synthesis Team
| Synthesize latest scientific research on bay acidification and potential impact on Chesapeake Bay waters (e.g., findings of MD Task Force Report; UMD and SERC research, etc.) | CRWG/ STAC Synthesis Team
| Synthesize latest scientific research on ecosystem response. | CRWG/ STAC Synthesis Team
Management Approach 6: Develop a research agenda to improve understanding of climate impacts or fill critical data or research gaps
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Timeframe (month/year) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Examine individual management strategies and biennial work plans and outline list of research needs. | Conduct a cursory review and analysis of 29 individual management strategies to identify initial climate-related research needs. | Climate Resiliency Workgroup
| Conduct an assessment of research needs to support future policy dialog related to the integration of climate change considerations into the Water Quality Management Strategy. | Climate Resiliency Workgroup | 2016-06-01
| Conduct a more thorough assessment of research needs to support integration of climate change considerations into the Protected Lands and Wetlands Management Strategy. | 2016 CBP Funded Project | 2016-07-01
Compile a research agenda to improve understanding of climate impacts or fill critical data or research gaps. | Work with regional partners, academic institutions and other stakeholders to collaboratively define climate related science and research needs at the broader watershed-scale or within a defined geographic area. | Climate Resiliency Workgroup | 2017-12-01
| Work with NE and Appalachian Landscape Conservation Cooperative, the NE Climate Science Center and NE USDA Climate Hubs to identify collective research priorities. | Climate Resiliency Workgroup
Management Approach 1 (Adaptation): Compile and assess current adaptation efforts and lessons learned
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Timeframe (month/year) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Compile and assess lessons learned from past and ongoing adaptation planning and programmatic efforts within the Chesapeake Bay Watershed. | Compile and synthesize available data, tools and resources that can be used to support CB region vulnerability assessments. | Climate Resiliency Workgroup
| Develop need and format for information to be gathered and a methodology for updating list and synthesis on a continual basis. | Climate Resiliency Workgroup | 2016-06-01
| Informed by step above, work from Appendix B to compile an expanded list of current planning and programmatic efforts that support key elements of the Management Strategy. | Climate Resiliency Workgroup | 2016-12-01
Approach Targeted to Local Participation: Undertake public, stakeholder and local engagement
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Timeframe (month/year) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Increase availability and access to monitoring and assessment data. | Explore need, utility and format for a climate data and information portal and/or another form for dissemination. | Climate Resiliency Workgroup | 2016-06-01
Management Approach 7: Review progress and reassess implementation priorities
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Timeframe (month/year) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Review progress on a biennial basis. | Create process to evaluate progress toward the closing of gaps in baseline monitoring and gaps in assessment tools and scientific research. | Climate Resiliency Workgroup

## Adaptation
Outcome: Climate Adaptation
Goal: Climate Resiliency
Outcome: Continually pursue, design and construct restoration and protection projects to enhance the resiliency of the Bay and aquatic ecosystems from the impacts of coastal erosion, coastal flooding, more intense and more frequent storms and sea level rise.
Management Approach 3: Review and revise conservation, restoration and protection goals and objectives.
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Timeframe (month/year) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Develop process to revise or reconsider Watershed Agreement Management Strategies to accommodate anticipated climate-related changes or impacts. | Create a Climate Resiliency Analysis and Decision Making Matrix to enable the assessment of climate impacts on existing management goals and outcomes and the effect of climate change on the performance of specific management practices (BMPs). | 2016 CBP Funded Project | 2016-07-01
| Facilitate in-person workshops with Wetlands and Protected Lands Work to complete Matrix Analysis process and revise, modify, prioritize and select management actions for integration into Management Strategies; and 2) to develop recommendations for augmenting existing Management Strategies through the “Adaptive Management” framework. | 2016 CBP Funded Project | 2017-05-01
| Develop recommendations for refinement of matrix and a proposed implementation process to engage one-on-one with GITS and work groups to identify, assess, evaluate and revise (as necessary) all individual CB Agreement Management Strategies. | 2016 CBP Funded Project | 2017-09-01
Management Approach # 5: Increase the institutional capacity of the Chesapeake Bay Program to prepare for and respond to climate change.
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Timeframe (month/year) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Work with partners to host a “Chesapeake Bay Climate Adaptation Workshop" or offer adaptation related trainings at appropriate regional forums and conferences. | Participate in the Maryland Sea Grant: Climate Change Research Forums | Climate Resiliency Workgroup | 2016-06-01
| Participate in the NE Climate Preparedness Conference – Baltimore (April 4-5, 2016) | Climate Resiliency Workgroup | 2016-04-01
| Host a workshop on the role of natural infrastructure/living shorelines as part of adaptation/mitigation strategies for the built environment. | Climate Change Workgroup with MDSG, NWF, SAGE, Academic Community
Increase opportunities for formal and informal communication and the exchange of ideas among the Chesapeake Bay watershed’s existing “adaptation planning network.” | Develop a framework and list of organizations within the “Chesapeake Bay Adaptation Network.” | Climate Resiliency Workgroup
Explore mechanisms to encourage the integrationof climate change considerations in the design and implemenation of on the ground protectionand restoration efforts. | Track Department of Interior Metrics Expert Group (MEG) recommendations for measuring effects of ecological resilience projects to protect key features/ systems and some forms of grey infrastructure against effects of coastal storms and climate change effects (e.g., sea level rise, storm surge). | Climate Resiliency Workgroup
Identify and assess institutional barriers. | Work with the Protected Lands and Wetland work groups to develop list of policy, programmatic and regulatory enhancements that will increase capacity. | 2016 CBP Funded Project | 2017-12-01
Management Approach # 6: Implement Priority Adaptation Actions
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Timeframe (month/year) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Plan and implement targeted restoration and protection efforts that build community and ecosystem resilience within the Bay watershed. | Identify projects proposed or planned by CB partners, likely to be implemented within the next two years. | Climate Resiliency Workgroup
| Assess opportunities to modify planned project designs to accommodate for climate considerations, develop metrics for and/or monitor a specific projects performance over time. | Climate Resiliency Workgroup
Pursue implementation of “pilot projects” to test new and emerging design principles and implementation methodologies. | Participate in the SAGE Chesapeake Bay Pilot to develop “living” models of green/gray infrastructure for coastal community protection and improved resilience of natural resources; evaluate alternative SAGE project financing approaches; share information across federal, state, and local agencies, NGOs, academic institutions, and multiple business sectors (e.g., engineering, finance). | Climate Resiliency Workgroup
Local Participation Approach: Undertake Local, Public and Stakeholder Engagement & Conduct Targeted Education and Outreach
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Timeframe (month/year) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Share current efforts, including policy, tools, products, and scientific understanding with interested parties. | Work with CBP Communications Work Group to release a periodic newsletter to disseminate adaptation-related information. | Climate Resiliency Workgroup | 2016-03-01
Local Participation Approach: Foster a larger discussion on the linkage between climate impacts and diversity
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Timeframe (month/year) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Work with the Diversity Action Team to identify and pursue opportunities to create a strong linkage between the Climate Resiliency and Diversity Management Strategy. | Identify a Climate Resiliency Work Group member to serve on the Diversity Action Team. | Climate Resiliency Workgroup | 2016-01-01
Management Approach 7: Track adaptation action effectiveness and ecological response
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Timeframe (month/year) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Assess progress towards the full integration of climate resilience considerations into the Chesapeake Bay Program. | Develop a questionnaire or matrix to document programmatic baselines and monitor the status and progress towards incorporating climate factors into individual management strategies. | Climate Resiliency Workgroup | 2017-12-01
Investigate climate resilience indicators to assess adaptation action effectiveness and ecological response. | Review other climate indicator frameworks (USGRCP and US EPA Climate Change Indicators (http://www3.epa.gov/climatechange/science/indicators/) to assess suitability for application to CBP related activities. | Climate Resiliency Workgroup
| Work with STAR and STAC to recommend and establish performance metrics and/or indicators to assess Climate Resiliency Goal and Outcome implementation effectiveness, as well as ecological response. | Climate Resiliency Workgroup; STAR; STAC