## Monitoring & Assessment
Monitoring and Assessment Outcome: Continually monitor and assess the trends and likely impacts of changing climatic and sea level conditions on the Chesapeake Bay ecosystem, including the effectiveness of restoration and protection policies, programs and projects. |  |  |  | Complete
On track, progress ongoing
Some challenges or delay
Management Approach : Define Goals and Establish Baselines; Develop Conceptual Monitoring, Modeling and Assessment Model; and Prioritize Climate Impacts |  |  |  | No Action
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity (Partner(s) Responsible) | Timeline (completion date: month & year)
Develop and implement a methodology to establish climate related goals and baselines for individual Chesapeake Bay Agreement Management Strategies. | Complete a Literature Review of existing ecosystem-based climate resiliency approaches, aids (e.g., tables, matrices) and processes or decision making products. | Climate Resiliency Workgroup, Wetlands Workgroup, Chesapeake Conservation Partnership | 2016-05-01 | Climate Smart Habitat Restoration Workshop: SAV and Tidal Wetlands/Black Duck held in November, 2016
| Compile existing climate change vulnerability research and data, including available assessment products and tools, specific to SAV and tidal wetlands/Black Duck, within the Chesapeake Bay region. | Climate Resiliency Workgroup, Wetlands Workgroup, Chesapeake Conservation Partnership | 2016-06-01 | Climate Smart Habitat Restoration Workshop: SAV and Tidal Wetlands/Black Duck held in November, 2016
| Create a Climate Resiliency Analysis and Decision Making Matrix to enable the assessment of climate impacts on existing management goals and outcomes and the effect of climate change on the performance of specific management practices (BMPs). | Climate Resiliency Workgroup, Wetlands Workgroup, Chesapeake Conservation Partnership | 2016-07-01 | Progress ongoing (Lead: Tetra Tech)
| Conduct a review of approach to factor climate change considerations into the 2017 Chesapeake Bay TMDL Midpoint Assessment | Climate Resiliency Workgroup, CBP Modeling Workgroup, STAC | 2016-08-01 | Guiding Principles and Options for Addressing Climate Change Considerations in the Jurisdictions’ Phase III Watershed Implementation Plans
Management Approach: Design Monitoring and Modeling Plan
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Timeline (completion date: month & year)
Identify and evaluate the continuity of existing monitoring data and models within federal agencies, state partners, and academic partners, to explain climate factors of interest to the Bay Program Partnership (i.e., sea level rise, precipitation, temp) at the watershed scale. |  |  |  | N/A
Catalogue monitoring and modeling gaps for 4 select Chesapeake Bay Agreement Management Strategies | Work with 4-select Workgroups to determine current and future monitoring needs by geography, habitat type, and BMP and outline gaps at Workgroup or GIT level. | STAR | 2017-12-01 | Initial engagement letters sent to Forage fish, Black Duck, Stream health and Fish habitat Workgroups
| Outline gaps for watershed scale monitoring effort, including gaps related to monitoring of non-climate stressors that could exacerbate climate impacts to Chesapeake Bay habitat or BMPs. | STAR | 2017-12-01 | No action to date
Identify gap-filling solutions by expanding the Partnership to include identified ongoing or planned monitoring efforts of climate factors. | Identify opportunities to better integrate data collected by the NOAA Chesapeake Bay Sentinel Site Cooperative (CBSSC) with CBP monitoring efforts. | Climate Resiliency Workgroup, Chesapeake Bay Sentinel Site Cooperative (CBSSC) | 2017-03-01 | Progress ongoing
| Explore the use of citizen-based monitoring networks. | STAR, Alliance for the CB | 2017-12-01 | No action to date
Develop a plan to fill identified gaps. | Identify costs associated with closing monitoring gaps. | STAR; Trout Unlimited | 2017-12-01 | No action to date
| Identify agencies/organizations through which commitments could be sought to fund or participate in filling monitoring gaps. | STAR; Trout Unlimited | 2017-12-01 | No action to date
| Identify geographical overlap in monitoring and modeling efforts to explore opportunities for cost saving efficiencies and integration of priorities to include climate factors. | STAR | 2017-12-01 | No action to date
Management Approach: Assess past and future trends in sea level, precipitation patterns, temperature and ecosystem response
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Timeline (completion date: month & year)
Establish guidance of the application of climate change scenarios, projections and realizations for Chesapeake Bay Program assessments. | Facilitate a workshop to evaluate applicability of international, national, regional and state climate scenarios, projections, forecasts and assessments and to develop process for establishing a recommended set of climate projections for use in Chesapeake Bay Program assessments. | STAC | 2016-02-01 | Development of Climate Projections for Use in Chesapeake Bay Program Assessments
| **Convene a group of sea level rise researchers and resource experts to reach agreement on sea level rise estimates to apply to MPA modeling efforts; how to best approach simulating effects of sea level rise on living resources and wetlands; and the range of sea level rise scenarios to run. | Climate Resiliency Workgroup | 2016-08-01 | Recommendations on Incorporating Climate-Related Data Inputs and Assessments: Selection of Sea Level Rise Scenarios and Tidal Marsh Change Models
Conduct a literature review and synthesis of latest scientific research on past and future climate change impacts on the Chesapeake Bay, as was done in the 2008 Scientific and Technical Advisory Committee report. | Assess international, national, regional and state-level (DE, MD, PA, WV, VA, NY, DC) climate change assessments. | STAC, STAR, Climate Resiliency Workgroup, PA, MD, DE, DC | 2017-12-01 | No action to date
| Synthesize latest scientific research on sea level and water level trends; precipitation and evapotranspiration; and temperature change in both air and water | STAC, STAR | 2017-12-01 | Development of Climate Projections for Use in Chesapeake Bay Program Assessments
Gain a better understanding of past and future impact of ocean acidification on Chesapeake Bay waters. | Convene federal, state and regional experts along with academic partners to assess current knowledge surrounding ocean acidification trends within the Chesapeake Bay. | Climate Resiliency Workgroup; Fisheries GIT; Maryland Dept. of Natural Resources | 2017-12-01 | No action to date
Management Approach: Develop a research agenda to improve understanding of climate impacts or fill critical data or research gaps
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Timeline (completion date: month & year)
Compile a research agenda to improve understanding of climate impacts or fill critical data or research gaps. | Conduct a cursory review and analysis of 29 individual management strategies to initial climate-related research needs. | Climate Resiliency Workgroup | 2017-12-01 | Initial engagement with Workgroups through STAR and STAC
| Conduct an assessment of research needs to support future policy dialog related to the integration of climate change considerations into the Water Quality Management Strategy. | Climate Resiliency Workgroup | 2016-06-01 | Progress ongoing; Being conducted as part of Midpoint Assessment process
| Work with regional partners (e.g., LCC, Climate Hubs and Climate Science Centers), academic institutions and other stakeholders to collaboratively define climate related science and research needs at the broader watershed-scale or within a defined geographic area. | Climate Resiliency Workgroup, USFWS, NRCS, USFS, USDA NE Climate Hub, NFW, CBSSC, USGS | 2017-12-01 | No specific action to date
Undertake targeted research to improve understanding of climate impacts or fill critical data or research gaps. |  |  |  | N/A
Compile available data, tools and resources that can be used to support Chesapeake Bay watershed vulnerability assessments. |  |  |  | 1) Development of Climate Projections for Use in Chesapeake Bay Program Assessments; and 2) Climate Change Research and Adaptation in the Chesapeake Bay Watershed
Management Approach: Undertake public, stakeholder and local engagement
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Timeline (completion date: month & year)
Increase availability and access to monitoring and assessment data. |  |  |  | N/A
Management Approach: Review progress and reassess implementation priorities
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Timeline (completion date: month & year)
Review progress on a biennial basis. | Evaluate progress toward the closing of gaps in baseline monitoring and gaps in assessment tools and scientific research. | Climate Resiliency Workgroup | 2017-12-01 | No action to date
** Performance Target added after approval of CRWG Workplan

## Adaptation
Adaptation Outcome: Continually pursue, design and construct restoration and protection projects to enhance the resiliency of the Bay and aquatic ecosystems from the impacts of coastal erosion, coastal flooding, more intense and more frequent storms and sea level rise. |  |  |  | Complete
On track, progress ongoing
Some challenges or delay
Management Approach: Compile and assess current adaptation efforts and lessons learned. |  |  |  | No action
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Timeline (completion date: month & year)
Compile and assess lessons learned from past and ongoing adaptation planning and programmatic efforts within the Chesapeake Bay Watershed. | Develop need and format for information to be gathered and a methodology for updating list and synthesis on a continual basis. | Climate Resiliency Workgroup; State Signatories to provide information on plan updates and programmatic efforts | 2016-06-01 | Climate Change Research and Adaptation in the Chesapeake Bay Watershed
| Informed by step above, work from Appendix B to compile an expanded list of current planning and programmatic efforts that support key elements of the Management Strategy. | Climate Resiliency Workgroup | 2016-12-01 | Climate Change Research and Adaptation in the Chesapeake Bay Watershed
Management Approach: Review and revise conservation, restoration and protection goals and objectives.
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity (Partner(s) Responsible) | Timeline (completion date: month & year)
Develop process to revise or reconsider Watershed Agreement Management Strategies to accommodate anticipated climate-related changes or impacts. | Facilitate in-person workshops with Wetlands and Protected Lands Work to complete Matrix Analysis process and revise, modify, prioritize and select management actions for integration into Management Strategies; and 2) to develop recommendations for augmenting existing Management Strategies through the “Adaptive Management” framework. | Climate Resiliency Workgroup, Wetlands Workgroup, Chesapeake Conservation Partnership | 2017-05-01 | Climate Smart Habitat Restoration Workshop: SAV and Tidal Wetlands/Black Duck held in November, 2016
| Develop recommendations for refinement of matrix and a proposed implementation process to engage one-on-one with GITS and Workgroups to identify, assess, evaluate and revise (as necessary) all individual CB Agreement Management Strategies. | Climate Resiliency Workgroup | 2017-09-01 | On track, progress ongoing (Lead: Tetra Tech)
Management Approach: Increase the institutional capacity of the Chesapeake Bay Program to prepare for and respond to climate change.
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity (Partner(s) Responsible) | Timeline (completion date: month & year)
Increase opportunities for formal and informal communication and the exchange of ideas among the Chesapeake Bay watershed’s “adaptation planning network.” | Participate in the Maryland Sea Grant: Climate Change Research Forums | Maryland Sea Grant, Climate Resiliency Workgroup | 2016-09-01 | Maryland Sea Grant Forums have not been scheduled due to staffing changes
| Work with partners to host a “Chesapeake Bay Climate Adaptation Workshop" or offer adaptation related trainings at appropriate regional forums and conferences. | Climate Resiliency Workgroup | 2017-12-01 | Presentations at regional forums have been given but no action on hosting a regional workshop
Identify funding availability, needs and mechanisms. |  |  |  | N/A
Identify and assess institutional barriers. |  |  |  | N/A
Management Approach : Implement Priority Adaptation Actions
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity (Partner(s) Responsible) | Timeline (completion date: month & year)
Plan and implement targeted restoration and protection efforts that build community and ecosystem resilience within the Bay watershed. | Identify additional on-the-ground projects proposed or planned by CB partners, to be implemented within the next two years and beyond. | Climate Resiliency Workgroup | 2016-17 | No action
| Opportunistically, assess planned on-the-ground restoration projects, proposed by CB Partners, to evaluate whether project designs accommodate for climate change; and, where possible, develop metrics for and/or monitor a specific projects performance over time. | Climate Resiliency Workgroup | 2016-17 | No action
| Participate in the SAGE Chesapeake Bay Pilot to develop “living” models of green/gray infrastructure for coastal community protection and improved resilience of natural resources; evaluate alternative SAGE project financing approaches; share information across federal, state, and local agencies, NGOs, academic institutions, and multiple business sectors (e.g., engineering, finance). | CBP, Climate Resiliency Workgroup | 2016-17 | Participated in several SAGE Chesapake Bay Pilot meetings but need to determine status of implementation of pilot effort.
Management Approach: Undertake Local, Public and Stakeholder Engagement & Conduct Targeted Education and Outreach
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity (Partner(s) Responsible) | Timeline (completion date: month & year)
Share current efforts, including policy, tools, products, and scientific understanding with interested parties. | Work with CBP Communications Workgroup to release a periodic newsletter to disseminate adaptation-related information. | Climate Resiliency Workgroup | 2016-03-01 | Chesapeake Resiliency News released in Jan, March and August 2016
Test and develop new communication tools that are audience specific so that climate information is accessible and understandable across multiple audiences and communities. |  |  |  | N/A
Develop information products that can be used to inform community-led coastal resiliency planning processes. |  |  |  | N/A
Management Approach: Foster a larger discussion on the linkage between climate impacts and diversity
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity (Partner(s) Responsible) | Timeline (completion date: month & year)
Work with the Diversity Action Team to identify and pursue opportunities to create a strong linkage between the Climate Resiliency and Diversity Management Strategy. | Climate Resiliency Workgroup member to serve on the Diversity Action Team. | Climate Resiliency Workgroup | 2016-01-01 | CRWG Infocus Meeting (09/19/2016) on Diversity and Climate Change issues
Undertake targeted efforts to engage diverse stakeholders. |  |  |  | N/A
Management Approach: Track adaptation action effectiveness and ecological response
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity (Partner(s) Responsible) | Timeline (completion date: month & year)
Assess progress towards the full integration of climate resilience considerations into the Chesapeake Bay Program. | Develop a questionnaire or matrix to document programmatic baselines and monitor the status and progress towards incorporating climate factors into individual management strategies. | Climate Resiliency Workgroup | 2017-12-01 | Initial evaluation completed and presented to STAC and MB
Investigate climate resilience indicators to assess adaptation action effectiveness and ecological response. | Interface with NFWF/DOI, USGRCP and US EPA to review other climate indicator frameworks (DOI Metrics, USGRCP and US EPA Climate Change Indicators (http://www3.epa.gov/climatechange/science/indicators/) to assess suitability for application to CBP related activities. | USGS, FWS, Climate Resiliency Workgroup | 2017-12-01 | RFP Issued for Project: Development of Climate Change Indicators for the CBP
| Track Department of Interior Metrics Expert Group (MEG) recommendations for measuring effects of ecological resilience projects to protect key features/ systems and some forms of grey infrastructure against effects of coastal storms and climate change effects (e.g., sea level rise, storm surge). | Climate Resiliency Workgroup | 2017-12-01 | Presentation to CRWG on DOI Metrics (MEG) provided by Pete Murdoch, but no additional followup. Review of these metrics was included in scope of work for indicators project.
| Work with STAR and STAC to recommend and establish performance metrics and/or indicators to assess Climate Resiliency Goal and Outcome implementation effectiveness, as well as ecological response. | STAR, STAC | 2017-12-01 | RFP Issued for Project: Development of Climate Change Indicators for the CBP