## Monitoring & Assessment
Outcome: Monitoring and Assessment
Goal: Climate Resiliency
Outcome: Continually monitor and assess the trends and likely impacts of changing climatic and sea level conditions on the Chesapeake Bay ecosystem, including the effectiveness of restoration and protection policies, programs and projects.
Management Approach 1-3: Define Goals and Establish Baselines; Develop Conceptual Monitoring, Modeling and Assessment Model; and Prioritize Climate Impacts
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity (Partner(s) Responsible) | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Develop and implement a methodology to establish climate related goals and baselines for individual Chesapeake Bay Agreement Management Strategies. | Complete a Literature Review of existing ecosystem-based climate resiliency approaches, aids (e.g., tables, matrices) and processes or decision making products. | Climate Resiliency Workgroup, Wetlands Workgroup, Chesapeake Conservation Partnership | Watershed | 2016-05-01 | Lack of guidance | 40000 | 40000
| Compile existing climate change vulnerability research and data, including available assessment products and tools, specific to protected lands and wetlands within the Chesapeake Bay region. | Climate Resiliency Workgroup, Wetlands Workgroup, Chesapeake Conservation Partnership | Watershed | 2016-06-01 | Vulnerability of the watershed
| Create a Climate Resiliency Analysis and Decision Making Matrix to enable the assessment of climate impacts on existing management goals and outcomes and the effect of climate change on the performance of specific management practices (BMPs). | Climate Resiliency Workgroup, Wetlands Workgroup, Chesapeake Conservation Partnership | Watershed | 2016-07-01 | Cross-cutting programmatic gap
Inform approach to factor climate change considerations into the 2017 Chesapeake Bay TMDL Midpoint Assessment | Conduct a review of and document approach to factor climate change considerations into the 2017 Chesapeake Bay TMDL Midpoint Assessment | Climate Resiliency Workgroup, CBP Modeling Workgroup, STAC | Watershed | 2016-08-01 | Climate science | 15000 | 15000
Management Approach 4: Design Monitoring and Modeling Plan
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Identify and evaluate the continuity of existing monitoring data and models within federal agencies, state partners, and academic partners, to explain climate factors of interest to the Bay Program Partnership (i.e., sea level rise, precipitation, temp) at the watershed scale. | Work with its regional offices, states, tribes, river basin commissions and other entities to establish Regional Monitoring Networks (RMNs) for freshwater wadeable streams. | U.S. EPA | Watershed | 2016-2017 | Coordination of modeling | 200000 | $50,000 in FY15; FY16-17 Budget TBD
| Monitor a number of sites in the Susquehanna River watershed for thermal changes. | Susquehanna River Basin Commission | Susquehanna River watershed | 2016-2017 | Coordination of modeling | Staff time | Staff time
| Evaluate the capacity of CBIBS to contribute to climate science and the CBIB’s Data Enterprise to determine applicability for template for CBP climate data portal. | NCBO | Chesapeake Bay | 2016 | Complexity of monitoring program | Staff time | Staff time
| Incorporate RMN sites into the existing Water Quality Network (WQN). The WQN is a long-term monitoring program with approximately eleven long term continuous monitoring sites operated by USGS on large river systems. | PA DEP | Pennsylvania | 2016-2017 | Coordination of modeling | Staff time | Staff time
Catalogue monitoring and modeling gaps for 4 select CB Agreement Management Strategies | Work with 5-select Workgroups to determine current and future monitoring needs by geography, habitat type, and BMP and outline gaps at Workgroup or GIT level. | STAR | Watershed | 2017-12-01 | Coordination of modeling; Complexity of monitoring program | Staff time | Staff time
| Outline gaps for watershed scale monitoring effort, including gaps related to monitoring of non-climate stressors that could exacerbate climate impacts to Chesapeake Bay habitat or BMPs. | STAR | Watershed | 2017-12-01 | Non-climate related and multiple stressors | Staff time | Staff time
| Explore need for consistent bay-wide wetland monitoring in brackish and freshwater tidal and non-tidal wetlands. | EPA Region 3 | Watershed | TBD | Coordination of modeling; Complexity of monitoring program | Staff time | Staff time
Identify gap-filling solutions by expanding the Partnership to include identified ongoing or planned monitoring efforts of climate factors. | Identify opportunities to better integrate data collected by the NOAA Chesapeake Bay Sentinel Site Cooperative (CBSSC) with CBP monitoring efforts. | Chesapeake Bay Sentinel Site Cooperative (CBSSC) | Sites within the NOAA Chesapeake Bay Sentinel Site Cooperative (CBSSC) | 2017-03-01 | Coordination of modeling; Complexity of monitoring program | Potential $1K in travel funds for coordinator | Funding for site coordinator position is commited by Maryland Sea Grant and MD DNR through August 2017
| Explore the use of citizen-based monitoring networks. | STAR, Alliance for the CB | Watershed | 2017-12-01 | Coordination of modeling; Complexity of monitoring program | Staff time | Staff time
Develop a plan to fill identified gaps. | Identify costs associated with closing monitoring gaps. | STAR | Watershed | 2017-12-01 | Coordination of modeling; Complexity of monitoring program | Staff time | Staff time
| Identify agencies/organizations through which commitments could be sought to fund or participate in filling monitoring gaps. | STAR | Watershed | 2017-12-01 | Coordination of modeling; Complexity of monitoring program | Staff time | Staff time
| Identify geographical overlap in monitoring and modeling efforts to explore opportunities for cost saving efficiencies and integration of priorities to include climate factors. | STAR | Watershed | 2017-12-01 | Coordination of modeling; Complexity of monitoring program | Staff time | Staff time
Management Approach 5: Assess past and future trends in sea level, precipitation patterns, temperature and ecosystem response
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Establish guidance of the application of climate change scenarios, projections and realizations for CBP assessments. | Facilitate a workshop to evaluate applicability of international, national, regional and state climate scenarios, projections, forecasts and assessments and to develop process for establishing a recommended set of climate projections for use in Chesapeake Bay Program assessments. | STAC | Watershed | 2016-02-01 | Climate science | 9000 | $9000 ($7,000 STAC; $2,000 USGS)
Conduct a literature review and synthesis of latest scientific research on past and future climate change impacts on the Chesapeake Bay, as was done in the 2008 STAC report. | Compile and assess international, national, regional and state-level (DE, MD, PA, WV, VA, NY, DC) climate change assessments. | STAC, STAR, Climate Resiliency Workgroup, PA, MD, DE, DC | Watershed | 2017-12-01 | Vulnerability of the watershed | TBD | TBD
| Report on PA Climate Impacts and Assessment, a report that is required to be updated every 3 year. PSU researchers have been contracted to provide an assessment report to PA DEP. The most current report was updated in August 2015. | PA DEP | Pennsylvania | 2016-2017 | Vulnerability of the watershed | Staff time | Staff time
| Synthesize latest scientific research on sea level and water level trends; precipitation and evapotranspiration; and temperature change in both air and water. | STAC, STAR | Watershed | 2017-12-01 | Climate science | TBD | TBD
| Conduct research on bay acidification and potential impact on Chesapeake Bay waters | UMCES/CBL (NOAA Ocean Acidification Program) | Chesapeake Bay |  | Climate science | NOAA Ocean Acidification Program funded project | NOAA Ocean Acidification Program funded project
Management Approach 6: Develop a research agenda to improve understanding of climate impacts or fill critical data or research gaps
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Examine individual management strategies and biennial work plans and outline list of research needs. | Conduct a cursory review and analysis of 29 individual management strategies to identify initial climate-related research needs. | Climate Resiliency Workgroup | Watershed | 2017-12-01 | Scientific capabilities | Staff time | Staff time
| Conduct an assessment of research needs to support future policy dialog related to the integration of climate change considerations into the Water Quality Management Strategy. | Climate Resiliency Workgroup | Watershed | 2016-06-01 | Scientific capabilities | TBD | TBD
Compile a research agenda to improve understanding of climate impacts or fill critical data or research gaps. | Work with regional partners (e.g., LCC, Climate Hubs and Climate Science Centers), academic institutions and other stakeholders to collaboratively define climate related science and research needs at the broader watershed-scale or within a defined geographic area. | Climate Resiliency Workgroup,USFWS, NRCS, USFS, USDA NE Climate Hub, NFW, CBSSC | Watershed | 2017-12-01 | Scientific capabilities; Lack of collaboration | Staff time | Staff time
Undertake targeted research to improve understanding of climate impacts or fill critical data or research gaps. | Simulate the effects of the projected changes on the living resources of the Bay system through application of an integrative ecosystem modeling approach(es) (e.g., CAM). | NCBO | Chesapeake Bay | TBD | Vulnerability of the watershed | TBD | TBD
| Undertake the NSF Coastal SEES Project: Chesapeake Bay Sustainability: Implications of Changing Climate and Shifting Management Objectives | VIMS, NCBO CAM | Chesapeake Bay | Sep 2013 – August 2016 | Vulnerability of the watershed | 582500 | 582500
| Assess effects of climate change on flow, temperature, and water-quality in streams of the Bay watershed. Work will build off USGS analysis examining changes in flow and temperatures in streams. USGS will be working with fish biologists on implications for freshwater populations and will also be looking at potential approaches to assess effects on nutrient and sediment loads. | USGS, CBP Modeling Team | Watershed | 2016-2017 | Vulnerability of the watershed | 100000 | 100000
| Investigate the risk of flooding and salt water intrusion to state wildlife impoundments and ponds and consider how to support important wetland communities and related species. | State of Delaware | Nanticoke Watershed | 2018-09-01 | Vulnerability of the watershed | 102800 | 76800
| Conduct research on the mechanisms and potential migration path of wetlands and habitat conversion as water levels rise and salt tolerance lines move. | State of Delaware | Nanticoke Watershed | 2018-09-01 | Vulnerability of the watershed | 111900 | 78500
| Analyze available climate monitoring and climate sensitive data on extreme events to document past trends and impacts. Analyze climate model projections similarly to predict future. Use CB NERRS data in conjunction with other available data to tell specific stories about climate impacts on NERRS. Develop climate change chapter for Chesapeake Bay Ecosystem Atlas for use in formal and informal education. | Chesapeake Environmental Communications, MD and VA National Estuarine Research Reserves, University of Maryland Center for Environmental Science | Chesapeake Estuary | 2015-10-16 | Climate science | NOAA NCCOS funded project | NOAA NCCOS funded project
| Conduct an evaluation of existing data sets, long-term trends, projects and research studies at each Sentinel Site in the Chesapeake Bay Sentinel Site Cooperative (CBSSC), to include (but not limited to): sea level change, surface elevation change and wetland vegetation dynamics. | Chesapeake Bay Sentinel Site Cooperative (CBSSC) | Sentinel Sites included in the Chesapeake Bay Sentinel Site Cooperative (CBSSC) | 2016-12-01 | Climate science | Potential $1K in travel funds for coordinator. Evaluation dependent on partner cooperation. | Funding for site coordinator position is commited by Maryland Sea Grant and MD DNR through August 2017
| Analyze latest scientific data collected at MD CBNERRS sites (i.e., SETs, water quality, vegetation data) to gain a better understanding of what is happening at the reserve level and how that can be applied to the Bay as a whole. | Chesapeake Bay NERRS, CBSSC (Participating) | MD NERRS Sites | 2017-12-01 | Climate science | Currently investigating internal funds versus seeking extrernal funding; if seeking external funding, would be approximately $50,000 | 0
| Compile and synthesize existing Gulf and Atlantic Coast vulnerability/resilience information on ~30 priority coastal species and models that quantitatively link SLR and increased storm severity and frequency with system response, impacts to habitats and species, and restoration and management alternatives. | USFWS, Landscape Conservation Cooperatives | Watershed | Septemer 2016 | Climate Science | 120000 | $90K (LCC Region 5); $30K (LCC Region 4)
| Provide science on wetlands prioritization by (1) modeling marsh migration due to sea-level rise using monitoring data from near Blackwater National Wildlife Refuge and other coastal wetlands, (2) conducting research on the effects of sea-level rise, salinification, and watershed sediment loading on the resilience and services of tidal freshwater wetlands (along the Pamunkey and Mattaponi rivers), (3) providing forecasts of land development throughout the watershed to help assess potential wetland loss, and (4) better document long-term changes in wetlands due to climate variability. | USGS, CBSSC (Participating) | Watershed | 2016-2017 | Vulnerability of the watershed | 150000 | 150000
Adaptation Management Approach 1: Compile and assess current adaptation efforts and lessons learned
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Compile and synthesize available data, tools and resources that can be used to support CB region vulnerability assessments. | Develop a vulnerability assessment guidance document for NER parks based on lessons learned from completed and ongoing NER vulnerability assessments and the broader existing literature and resources applicable to coastal parks. | NPS Northeast Region collaborators at the University of Rhode Island | National Parks | Estimated winter 2016 | Vulnerability of the watershed; Lack of capacity | $30K | ? (NPS funded in FY14)
| Undertake a follow up vulnerability assessment building on that guidance for Colonial National Historical Park beginning in 2016. | National Park Service | National Parks | Estimated summer 2017 | Vulnerability of the watershed; Lack of capacity | $125K | ? (NPS funded in FY15)
Compile and assess lessons learned from past and ongoing adaptation planning and programmatic efforts within the Chesapeake Bay Watershed. | Develop need and format for information to be gathered and a methodology for updating list and synthesis on a continual basis. | Climate Resiliency Workgroup; State Signatories to provide information on plan updates and programmatic efforts | Watershed | 2016-06-01 | Institutional capacity; Lack of guidance | Staff time | Staff time
| Informed by step above, work from Appendix B to compile an expanded list of current planning and programmatic efforts that support key elements of the Management Strategy. | Climate Resiliency Workgroup | Watershed | 2016-12-01 | Institutional capacity; Lack of guidance | Staff time | Staff time
| The USACE Committee on Climate Preparedness and Resilience will release annually its Climate Change Adaptation Plan, which tracks climate preparedness and resilience through annual metrics that address external collaboration, improving knowledge about climate impacts and adaptation, progress assessing vulnerability, and development of policy and guidance. The 2015 CCAP is available online at http://www.corpsclimate.us/docs/USACE_Adaptation_Plan_30-JUN-2015_final_hires.pdf. | USACE | Watershed | Annually | Climate science; Lack of indicators
| Track local government and water utility climate adaptation efforts in the MWCOG region and develop recommendations for potentially replicating those efforts in other geographic areas (mainly urban/suburban landscapes). | MWCOG | MWCOG | 2016-12-01 | Facilitate stakeholder engagement | Staff time | Staff time
| Explore the development of a spatially explicit adaptation project/plan database for the Mid-Atlantic Region modeled after EPA Region 2 effort. | EPA Region 3 | EPA Region 3 | 2016-12-01 | Facilitate stakeholder engagement | Staff time | Staff time
Approach Targeted to Local Participation: Undertake public, stakeholder and local engagement
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Increase availability and access to monitoring and assessment data. | Explore need, utility and format for a climate data and information portal and/or another form for dissemination. | Climate Resiliency Workgroup | Watershed | 2016-06-01 | Lack of guidance; Facilitate stakeholder engagement | Staff time | Staff time
| Share and disseminate recently published a set of projections in temperature and precipitation for the DC metro area: http://green.dc.gov/publication/climate-projections-scenario-development. | District of Columbia | District of Columbia | Projections released September 2015, will inform adaptation plan to be complete mid 2016. | Lack of guidance; Facilitate stakeholder engagement
| Launch climate data portal to provide access to climate projections data (temperature and precipitation) based on downscaling analysis conducted in 2013. | Delaware | Delaware | TBD | Lack of guidance; Facilitate stakeholder engagement | Costs of developing data portal already covered. Costs to host technical outreach events is minimal. | N/A
| Develop the Virginia Coastal Adaptation Data Portal | State of Virginia, VIMS | Virginia | 2017-12-01 | Lack of guidance; Facilitate stakeholder engagement
| Disseminate information on CBP’s climate change activities to MWCOG region local governments and water utility staff and stakeholders through existing committees (e.g., LGAC) and websites, and share lessons learned with other metro regions. | MWCOG | MWCOG | 2017-05-01 | Lack of guidance; Facilitate stakeholder engagement | Staff time | Staff time
| PA DEP has created a “Climate Change” button on the Department’s webpage for the purpose of posting climate related data and links. Information pertaining to the Climate Change Advisory Committee, including the Climate Impacts and Assessment Report and the Climate Change Action Plan, will be published on this site. | PA DEP | Pennsylvania | 2016-2017 | Facilitate stakeholder engagement | Staff time | Staff time
Management Approach 7: Review progress and reassess implementation priorities
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Review progress on a biennial basis. | Create process to evaluate progress toward the closing of gaps in baseline monitoring and gaps in assessment tools and scientific research. | Climate Resiliency Workgroup | Watershed | 2017-12-01 | Lack of indicators | Staff time | Staff time

## Adaptation
Outcome: Climate Adaptation
Goal: Climate Resiliency
Outcome: Continually pursue, design and construct restoration and protection projects to enhance the resiliency of the Bay and aquatic ecosystems from the impacts of coastal erosion, coastal flooding, more intense and more frequent storms and sea level rise.
Management Approach 3: Review and revise conservation, restoration and protection goals and objectives.
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity (Partner(s) Responsible) | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Develop process to revise or reconsider Watershed Agreement Management Strategies to accommodate anticipated climate-related changes or impacts. | Facilitate in-person workshops with Wetlands and Protected Lands Work to complete Matrix Analysis process and revise, modify, prioritize and select management actions for integration into Management Strategies; and 2) to develop recommendations for augmenting existing Management Strategies through the “Adaptive Management” framework. | Climate Resiliency Workgroup, Wetlands Workgroup, Chesapeake Conservation Partnership | Watershed | 2017-05-01 | Cross-cutting programmatic gap | 40000 | 40000
| Develop recommendations for refinement of matrix and a proposed implementation process to engage one-on-one with GITS and Workgroups to identify, assess, evaluate and revise (as necessary) all individual CB Agreement Management Strategies. | Climate Resiliency Workgroup | Watershed | 2017-09-01 | Cross-cutting programmatic gap
Management Approach # 5: Increase the institutional capacity of the Chesapeake Bay Program to prepare for and respond to climate change.
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity (Partner(s) Responsible) | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Increase opportunities for formal and informal communication and the exchange of ideas among the Chesapeake Bay watershed’s “adaptation planning network.” | Participate in the Maryland Sea Grant: Climate Change Research Forums | Maryland Sea Grant, Clmate Resiliency Workgroup | Maryland Coastal Zone | 2016-06-01 | Facilitate stakeholder engagement | $2K | $2K
| Participate in the NE Climate Preparedness Conference – Baltimore (April 4-5, 2016) | EPA Region 3 | Watershed | 2016-04-01 | Facilitate stakeholder engagement | Staff Time | Staff Time
| Conduct a workshop on the role of natural infrastructure/living shorelines as part of adaptation/mitigation strategies for the built environment. | MDSG, NWF, MARCO | Chesapeake Bay Coastal States | 2017-12-01 | Facilitate stakeholder engagement | $40K | $10K (MDSG); MARCO/NWF $139K
| Work with partners to host a “Chesapeake Bay Climate Adaptation Workshop" or offer adaptation related trainings at appropriate regional forums and conferences. | Climate Resiliency Workgroup | Watershed | 2017-12-01 | Facilitate stakeholder engagement; Lack of collaboration; Lack of capacity | 15000 | 0
| Explore creation of a new Community of Practice around using “Green Infrastructure” for climate resiliency. | The Conservation Fund | CB Watershed and beyond | 2016-03-01 | Facilitate stakeholder engagement; Lack of collaboration; Lack of capacity | 50000 | 50000
Facilitate climate adaptation planning and project implementation guidance. | Develop a “Flood Avoidance and Design Guidance” document for Delaware state agencies, under Executive Order 41, to use in the development of state projects. | State of Delaware | Delaware | April 2016. Training and technical workshops to follow throughout 2016. | Lack of guidance | Cost of technical workshops is minimal. | N/A
| Conduct a Coastal Resiliency Assessment to identify conservation and restoration priorities based on shoreline and community exposure and social vulnerability to flooding, storm surge, sea level rise, and wave action. | Maryland Dept. of Natural Resources; The Nature Conservancy | Maryland Coastal Zone | 2016-03-01 | Institutional capacity; Linking science to implementation | 41000 | 41000
| Initiate project to apply EPA’s wetlands vulnerability framework to several areas within the Chesapeake Bay to understand how to apply climate change science to assess wetland vulnerability and the key factors that affect tidal and nontidal wetlands vulnerability to inform climate adaptation. | US EPA | Chesapeake Bay | Tentative Timeline (to be confirmed) : Application of wetlands vulnerability framework to non-tidal wetlands within the Chesapeake Bay (FY2016); Conceptual approach for wetlands vulnerability framework modified for application to tidal wetlands (FY2017) | Scientific capabilities; Linking science to implementation | 200000 | Approximately $100,000 in FY15; FY16-17 Budgets TBD
| Improve technical understanding for successful restoration projects. USGS activities include research to optimize the design of restored nontidal freshwater wetlands for water-quality benefits and an addition study of the water-quality benefits of floodplain restoration along the Pocomoke River. | USGS in partnership with USDA and TNC | Pocomoke River | 2016-17 | Scientific capabilities; Linking science to implementation | 100000 | 100000
| Participate in the Hampton Roads Adaptation Forum, a quarterly meeting to bring together stakeholder in the Hampton Roads region to advance sea level rise adaptation. | Virginia Sea Grant, ODU and Hampton Roads Planning District Commission | Hampton Roads | Ongoing | Facilitate stakeholder engagement; Linking science to implementation | Staff time | Staff time
| Develop wetland restoration priorities for climate risk reduction and resilience in the Mid-Atlantic region. | Mid Atlantic Regional Council on the Ocean (MARCO) | Chesapeake Bay Watershed | 2016-12-01 | Linking science to implementation | $99K | $99K
Explore mechanisms to encourage the integration of climate change considerations in the design and implementation of on-the ground "protection” and “restoration” efforts. | Explore applicability of EPA Climate Change and Storm water Design Guide for Chesapeake Bay specific practices, soils, and climate changes. If additional site specific information is needed, use expert elicitation methods to gain that information from across EPA and other Agencies. | US EPA | Chesapeake Bay Coastal States | STAC/CB Program proactive expert urban stormwater workshop – 2016 (Q4)/2017(Q1); Draft/final report 2017 | Scientific capabilities; Linking science to implementation; Lack of guidance | 50000 | 0
| Undertake planning project on use of green infrastructure to increase regional resiliency to coastal storms and climate change project supported by NFWF in central MD (parts of 7 counties + major cities) | The Conservation Fund, APA, USGS MD-DE-DC Water Science Center, Chesapeake Conservancy, NFWF | Maryland western Bay shore & Gunpowder, Patapsco, Patuxent watersheds | 2016-09-01 | Scientific capabilities; Linking science to implementation; Lack of guidance | 775000 | 775000
| Implement major activities included in Choptank Habitat Focus Area Implementation Plan, focused on the concentrate of resources within the Choptank watershed to improve the decision-making and resilience of coastal communities by improving the delivery of NOAA’s habitat and climate science. | NCBO | Choptank Watershed | 2016-2017 | Linking science to implementation; Stakeholder engagement; Vulnerability of the watershed | 50000 | 50000
Identify funding availability, needs and mechanisms. | Review, update, and prioritize the recommendations of VA's 2008 Climate Change Action Plan and identify sources of revenue to fund the implementation. One recommendation in from the Commission is a green infrastructure bank of resilience projects and clean energy investments. | VA Climate Change and Resiliency Update Commission | Virginia | The final report of the Commission was delivered to the Governor on September 20, 2015. Timeline for the prioritization of recommendations and implementation of activites TBD. | Institutional capacity
| Integrate resiliency into the state’s Working Waterfronts Program. DNR to offer Working Waterfronts Enhancement Grants to local governments to support revitalization of working waterfront communities and economies. Maryland will seek projects that consider natural resource conservation and/or restoration, potential flooding, storm surge impacts, and MD’s Climate Change and Coast Smart Construction Infrastructure Siting and Design Guidelines. | Maryland Dept. of Natural Resources | Maryland Coastal Zone | Grants to be awarded in January 2016. Projects to be completed by December 31, 2016. | Institutional capacity | Funding 2 projects, total of $110,000 | 110000
| Pennsylvania’s TreeVitalize program is a public-private partnership to help restore tree cover, educate citizens about planting trees as an act of caring for our environment, and build capacity among local governments to understand, protect and restore their urban trees. The program is administered through PA Department of Conservation and Natural Resources. TreeVitalize is a funding mechanism that is included in the Chesapeake Bay Program Urban Tree Canopy’s Biennial Work plan. | PA DCNR Bureau of Forestry and PSU Extension | Pennsylvania | 2016-17 | Institutional capacity | 500000 | 250000
Identify and assess institutional barriers. | Explore opportunities to form new partnerships with entities such as the Sea Grant Law Clinic, the William and Mary’s Coastal Law and Policy Center or Georgetown’s Climate Center, to support projects to conduct targeted policy, legal and regulatory analyses. | Maryland and Virginia Sea Grant programs, National Sea Grant Law Clinic | Watershed | 2016-17 | Regulatory constraints | $20K cost depends on analyses identified. Could partner with Univ Maryland Extension law program if related to agricultural issues | MDSG can commit $5-$10K for seed money for projects
Management Approach # 6: Implement Priority Adaptation Actions
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity (Partner(s) Responsible) | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Plan and implement targeted restoration and protection efforts that build community and ecosystem resilience within the Bay watershed. | Implement the Urban and Community Forestry Initiative. The draft plan seeks to utilize the planting and maintenance of trees in urban and community settings to increase carbon storage and to reduce residential, commercial, and institutional energy use for heating and cooling purposes. Targets in this plan are set for 2030, but funding is limited, and DCNR is currently seeking private partners to help with implementation of the plan. Project scoping will occur over the next two years. | Pennsylvania | Pennsylvania | 2016-17 | Institutional capacity | Staff time | Staff time
| Plan, design and pursue construction of 7 on-the-ground resiliency projects in the State of Maryland, (Arundel on the Bay (AA CO), Annapolis Maritime Museum (AA CO) Flag Pond (Calvert Co), Cambridge Beach (Dorchester CO), Ellis Road (St. Mary’s CO), Livie Property (St. Mary’s CO) and Conquest Wildlife Preserve (QA CO). | Maryland DNR | Maryland Coastal Zone | 2016-17 | Adaptation | $1.65M | $1.65M
| Project partners to remove the 34-foot high by 220-foot long, state-owned Bloede Dam in the Patapsco Valley State Park (Ilchester, MD). In 2016-2017, major construction activities include removal of the Bloede Dam, relocation of a 42-inch sanitary sewer line, relocation of a 12-inch sanitary sewer line connection at Bonnie Road, replacement of the Grist Mill Trail and placement of stone along a portion of the riverbank for infrastructure protection. | NOAA, MDNR, American Rivers, and USFWS | Patapsko Valley State Park | 2016-17 | Adaptation | $3.6M | $3.6M
| Elevate & restore failing salt marsh site within Blackwater NWR with locally obtained materials to: 1) Extract eroded marsh material from Blackwater River and 2) elevate target tidal marsh to 30 cm NAVD 88 (for ideal veg. productivity) | USFWS, The Conservation Fund, Audubon MD-DC, USACE, National Fish & Wildlife Foundation | Blackwater NWR (Dorchester Co., MD) | Sept. 2016 | Adaptation | $2.5M | $2.5M
| Determine source, solution, of increased ponding at Farm Creek Marsh to 1) assess cause of surface water ponding on tidal marsh; and 2) design tidal exchange network to remediate | Audubon MD-DC, USGS Water Science Center MD-DC-DE, The Conservation Fund, MD DNR | Dorchester Co., MD (Fishing Bay) | Sept. 2016 | Adaptation | $250-300,000 | $250-300,000
| The Water Resources Development Act of 2007 authorized the expansion of the Paul S. Sarbanes Ecosystem Restoration Project at Poplar Island. Construction for the expansion is anticipated to begin in fiscal year 2017, depending on funding and regulatory permitting schedules. The expansion project would restore an additional 575 acres of remote island habitat. Adaptive management considerations as part of planned design and construction actions will address sea level rise of each new wetland cell in accordance with USACE policy guidance Engineer Regulation 1100-2-8162, dated December 31, 2013. | USACE | Maryland | 2017-2043 | Adaptation
| USACE, Baltimore District is assisting the U.S. Army Aberdeen Proving Grounds with ecosystem restoration on Poole's Island in the northern Chesapeake Bay. USACE, Philadelphia District will provide dredged materials from the Chesapeake and Delaware Canal dredging project for beneficial use as part of the project. The project will include monitoring actions related to sea level change and its impacts. | USACE | Maryland | 2017-2020 | Adaptation
| Identify additional projects proposed or planned by CB partners, likely to be implemented within the next two years. | Climate Resiliency Workgroup | Watershed | 2016-17 | Adaptation | Staff Time | Staff Time
| Assess opportunities to modify planned project designs to accommodate for climate considerations, develop metrics for and/or monitor a specific projects performance over time. | Climate Resiliency Workgroup | Watershed | 2016-17 | Adaptation | Staff Time | Staff Time
Pursue implementation of “pilot projects” to test new and emerging design principles and implementation methodologies. | Participate in the SAGE Chesapeake Bay Pilot to develop “living” models of green/gray infrastructure for coastal community protection and improved resilience of natural resources; evaluate alternative SAGE project financing approaches; share information across federal, state, and local agencies, NGOs, academic institutions, and multiple business sectors (e.g., engineering, finance). | CBP, Climate Resiliency Workgroup | Chesapeake Bay Coastal States | 2016-17 | Lack of guidance; Regulatory constraints; Lack of collaboration; Linking science to implementation | Unknown | Mostly in-kind technical support at present
Local Participation Approach: Undertake Local, Public and Stakeholder Engagement & Conduct Targeted Education and Outreach
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity (Partner(s) Responsible) | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Share current efforts, including policy, tools, products, and scientific understanding with interested parties. | Work with CBP Communications Workgroup to release a periodic newsletter to disseminate adaptation-related information. | Climate Resiliency Workgroup | Watershed | 2016-03-01 | Stakeholder engagement | Staff Time | Staff Time
| Connect local policymakers and public advisory committees with information on climate change-related activities. | MWCOG | MWCOG | 2017-11-01 | Cross-cutting programmatic gap; Stakeholder engagement | Staff Time | Staff Time
| PA DEP, in coordination with the PA Climate Change Advisory Committee, is currently drafting a Climate Change Action Plan, which will include climate change adaptation strategies. A 60-day public comment period for the draft plan will begin in November 2015. This plan was drafted with input from and endorsed by the PA Climate Change Advisory Committee. | PA DEP | Pennsylvania | 2016-2017 | Stakeholder engagement | Staff time | Staff time
Test and develop new communication tools that are audience specific so that climate information is accessible and understandable across multiple audiences and communities. | Undertake the Exploration to Explanation, Education to Conservation project, which will use emerging technology to explore and communicate coastal resiliency as sea levels rise and address green infrastructure solutions to climate change impacts specific to coastal areas. | Maryland DNR, MADE CLEAR | Coastal Maryland and Delaware | 2016-06-01 | Linking science to implementation | $XX
| Support UMD project 'Integrated geospatial, cultural, and social assessment of coastal resilience to Climate Change'. | UMD, MDNR, MDSG | Deale Island, Somerset County, MD | 2/2016 - 1/2018 | Stakeholder engagement | $100K | MDSG anticipates support at $140K over two years. Other partner support TBD
Develop information products that can be used to inform community-led coastal resiliency planning processes. | Support application of Town of Oxford’s vulnerability assessment result in community-led adaptation planning and engagement efforts. | NCCOS | Oxford, MD | 2016-01-01 | Vulnerability of the watershed; Stakeholder engagement | $208, 000 | $208, 000
| Data collection, indicator refinement, analysis and development of interpretive data products for second integrated vulnerability assessment. | NCCOS | Choptank Watershed | 2017-12-01 | Vulnerability of the watershed; Stakeholder engagement | 127000 | 127000
Local Participation Approach: Foster a larger discussion on the linkage between climate impacts and diversity
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity (Partner(s) Responsible) | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Work with the Diversity Action Team to identify and pursue opportunities to create a strong linkage between the Climate Resiliency and Diversity Management Strategy. | Climate Resiliency Workgroup member to serve on the Diversity Action Team. | Climate Resiliency Workgroup | Watershed | 2016-01-01 | Cross-cutting programmatic gap; Stakeholder engagement | Staff Time | Staff Time
Undertake targeted efforts to engage diverse stakeholders. | Use EJSCREEN to help prioritize new public access sites and target communities that might be in areas vulnerable to climate change impacts. | State of Maryland | Watershed | Ongoing | Cross-cutting programmatic gap; Stakeholder engagement | Staff Time | Staff Time
| Add an interpretive component to climate change vulnerability assessments being conducted for each park. | NPS | National Parks within Watershed | Ongoing | Cross-cutting programmatic gap; Stakeholder engagement | Varies by project, estimate $5-25K each | NPS projects over $100K require an Interpretive Component, others are not necessarily funded
| Participate on Greater Baltimore Wilderness Coalition Equity work group. | Greater Baltimore Wilderness Coalition, Climate Resiliency Workgroup; CBP Diversity Communications and Outreach Coordinator | Greater Baltimore Project Boundary (central MD - 7 counties, 3 major cities) | November 2015 -December 2017 (and beyond) | Cross-cutting programmatic gap; Stakeholder engagement | $15K/ year | $15K/ year
| Community partnership-building in three socially vulnerable communities in Maryland to survey residents' risk perceptions, and climate and energy policy preferences. | GMU, MDSG Extension, JHU, City of Baltimore | Baltimore MD, Cambridge MD. Proposed Prince George's County | Sept. 2015-Aug. 2016 | Cross-cutting programmatic gap; Stakeholder engagement | 35 | TBD
| The District will release a draft climate adaptation plan for public comment in early 2016. Through targeted outreach to the communities identified as most vulnerable, the District will seek to facilitate a discussion about climate change and resilience with underserved communities. | District of Columbia | District of Columbia | Early-mid 2016 | Cross-cutting programmatic gap; Stakeholder engagement
Management Approach 7: Track adaptation action effectiveness and ecological response
Key Action (Description of work/project) | Performance Target(s) (Incremental steps to achieve Key Action) | Participating Entity (Partner(s) Responsible) | Geographic Location | Timeline (completion date: month & year) | Factors Influencing and/or Gap | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner
Assess progress towards the full integration of climate resilience considerations into the Chesapeake Bay Program. | Develop a questionnaire or matrix to document programmatic baselines and monitor the status and progress towards incorporating climate factors into individual management strategies. | Climate Resiliency Workgroup | Watershed | 2017-12-01 | Cross-cutting programmatic gap; Lack of indicators | Staff Time | Staff Time
Investigate climate resilience indicators to assess adaptation action effectiveness and ecological response. | Review other climate indicator frameworks (DOI Metrics, USGRCP and US EPA Climate Change Indicators (http://www3.epa.gov/climatechange/science/indicators/) to assess suitability for application to CBP related activities. | Climate Resiliency Workgroup | Watershed | 2017-12-01 | Lack of indicators | Staff Time | Staff Time
| Track Department of Interior Metrics Expert Group (MEG) recommendations for measuring effects of ecological resilience projects to protect key features/ systems and some forms of grey infrastructure against effects of coastal storms and climate change effects (e.g., sea level rise, storm surge). | Climate Resiliency Workgroup | Chesapeake Bay Coastal States | 2017-12-01 | Lack of indicators | Staff Time | Staff Time
| Explore applications of the Chesapeake Atlantis Model as a tool to integrate available scientific information on the biology, habitats (physical and water column), and physical drivers (climate effects), which could be used to visualize outcomes with regard to the living resources- related management decisions. | NCBO | Chesapeake Bay Coastal States | TBD | Linking science to implementation; Lack of indicators | TBD | TBD
| Work with UMCES, IAN to identify lessons learned through the development process for the Climate Resilience Index (2015). | UMCES, IAN, STAR Workgroup | Chesapeake Bay Coastal States | 2017-12-01 | Lack of indicators | Staff Time | Staff Time
| Work with STAR and STAC to recommend and establish performance metrics and/or indicators to assess Climate Resiliency Goal and Outcome implementation effectiveness, as well as ecological response. | STAR, STAC | Watershed | 2017-12-01 | Lack of indicators | Staff Time | Staff Time