## RFB Workplan
Outcome: Riparian Forest Buffer
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Management Approach 1: RFB Leadership
Meet with RFB leadership within each state to develop a coordinated, riparian forest buffer (RFB) strategy to boost enrollment | Hold 3-4 meetings/year | State RFB Lead | 2017-12-01 | staff | n/a | Staff resources, funding
| Develop Action Plan |  | 2016-01-01 | staff | n/a
Appoint a leadership-field liaison/coordinate RFB activity in state
|  |  | 2016-01-01 | staff | n/a
Pilot Projects to Inform Leadership | Coordinate with Sustainable Ag community | MD DNR Forest Service | 2016-07-01 | existing staff | existing
| Development of a flexible buffer program with innovative tools and programs to fill niches not met by traditional buffer programs | Upper Susquehanna Coalition | 2016-07-01 | 300000 | 300000 | Project funded by NFWF Chesapeake Bay Stewardship Fund Innovative Nutrient and Sediment Reduction Grants (INSRG)
| Host a Statewide RFB summit, led by leadership team | PA DCNR, MD CREP Committee | 2016-07-01
Management Approach 2: RFB Enhancements
Coordinate with allied practices, especially streambank fencing, streambank stabilization and/or transitional woodland practice |  |  | Jan. 2016
Increase financial assistance
Program adjustments in RFB cost-share practices (i.e., CREP) per state task force reports
Recognize partnership potential with NGOs |  |  | Jan. 2016 | n/a - staff | n/a | Staff resources
Management Approach 3: RFB Technical Assistance
Increase staffing levels to provide more technical assistance | [5 empty] | Staff resources, funding
Expand partnerships to address technical assistance needs |  |  | Oct. 2015 | n/a - staff | n/a
Management Approach 4: RFB Outreach and Increasing New Enrollment
Address programmatic design/delivery that create barriers to new enrollment | Secure funding to process CRP/CREP new contracts that wish to enroll | DNREC, DE FSA/NRCS | 2016-01-01 | n/a - staff | DNREC | The Delaware CREP Program has a programmatic freeze until funding shortfalls are addressed. Shortfalls are approximately: $500,000 for 2015, $500,000 for 2016, and $300,000 for 2017 for current enrollments. Work-arounds are needed for new enrollees.
|  |  | Oct. 2015 | n/a - staff
Execute Regional Outreach Strategy for 2016 |  |  | 2016-05-01 | 180000 | 180000 | funding provided in FY2015 by FSA
Share local case studies of successful buffers; consider LandCare model |  | MD DNR Forest Service
Management Approach 5: Improve Establishment/Maintenance/Verification
Improve tracking and reporting | Utilize GIS, CAST, and other tools
Analyze efforts to recommend efficiencies
Follow RFB Verification Protocol | Conduct Initial RFB Training in new verification protocol |  | 2015-01-17
Increase annual maintenance payments | Increase annual maintenance payments from $5/acre to $10/acre | State, FSA | 2015-12-17
Increase establishment period | Expand the RFB establishment period from 2 years to 3-4 years | State, FSA | 2017-12-01
Cost share for invasive plant control | Create cost share for herbicide spraying to increase tree survival rates | State, FSA | 2015-12-17
Evaluation of Buffer Effectiveness/Tree Planting Success | Complete evaluation of tree planting mortality/success for three years after initial planting and secure additional planting stock to correct planting failures | State, FSA | 2015-12-17 |  |  | FSA and ERS project
Management Approach 6: Improve Re-enrollment
Provide targeted outreach to CREP participants in the last 1-2 years of contract | Send postcards to expiring contract holders and follow-up with phone calls | FS, State FSA, ACB
Provide TA/maintainance funding to help participants resolve compliance issues
Encourage participants with re-enrolling RFBs to include upgrades, such as increased acres and/or alternative water, stream crossings, fencing
Management Approach 7: Improve Targeting of RFB
Maintain current levels of RFB credit in portions of the state within the CB watershed
Fund trials for function-based incentives |  | MDA
Utilize CREP targeting tool
Increase MPL soil rental rates
Management Approach 8: Ramp-up conservation of RFB easement programs
Increase participation with the Agriculture Conservation Partnership Program (ACEP) | determine opportunities for CREP participants to transition enrollments to NRCS ACEP easement programs | NRCS, FSA |  |  |  | staff resources
Protect RFBs under ACEP easements | outreach to participants with expiring contracts | NRCS, FSA
Management Approach 9: Focus on non-ag RFB
Reduce mowing
Identify and connect with major non-ag. land owners | Target locations through GIS analysis
Work with federal land managers to promote RFB
Prioritize state-owned properties for RFB
Promote upland reforestation
Pursue options for aggreagating small landowners planting and management | Prettyboy analysis; Baltimore County Example contracts
Coordinate with MS4 permits | Meeting to assess options, needs | SRCC
| Develop examples of buffers & SWM | CWP