## (Goal Name) Workplan
Draft 2-Year Workplan (Dec 1, 2015) | [5 empty] | implement State RFB Plans
Riparian Forest Buffer Outcome
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Participating Entity Identify responsible partner for each step. | Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Management Approach 1: RFB Leadership
Meet with RFB leadership within each state to develop a coordinated, riparian forest buffer (RFB) strategy to boost enrollment | a) State Lead for RFB activities is appointed and helps coordinate work at all levels--from state leadership to field | State Lead | Baywide | 2016-07-01 | Stafftime
| b) Host a watershedwide 2-day RFB Summit | USFS, FSA, ACB | Baywide | 2016-03-01 | 10K
| c) Pursue opportunities for state leadership to express need/RFB is a priority practice | State Lead | Baywide | 2017-12-01 | Stafftime
| d) Establish a RFB Leadership Team in PA | DCNR and DEP | Pennsylvania | 2016-02-01 | Stafftime
| e) Host a statewide RFB summit | PA DCNR, MD CREP Committee | Pennsylvania | 2016-12-01 | Stafftime
States augment CREP program for RFB using additional funding from FSA | Increase acres enrolled in Chesapeake Bay CREPS, CP22 (RFB) | FSA, State Leads | NY, WV, DE, VA | 2017-12-01 | 4 million | 4 million | Funding (~1 million/state) will mostly go out as incentives for participating in CREP
Work to access additional financial assistance to augment programs for RFB | a) Increase acres enrolled in Chesapeake Bay CREPS, CP22 (RFB). Continue to assess available financial assistance as needed to encourage landowner interest in CREP and implementing conservation practice | FSA | Baywide | 2017-12-01
| b) Make non-federal match available as new opportunities present for federal funding | State |  | 2017-12-01
Coordinate and support State Leads and other partners in achieving RFB goals | Work with each state to help accomplish actions in 2-year workplan | USFS, FWG | Baywide | 2017-12-01 | 500K | 500K
Pilot Projects to Inform Leadership | a) Coordinate with Sustainable Ag community | MD DNR Forest Service | Maryland | 2016-07-01 | Stafftime
| b) Develop a flexible buffer program with innovative tools and programs to fill niches not met by traditional buffer programs | Upper Susquehanna Coalition, NFWF | Upper Susquehanna | 2016-07-01 | 300000 | 300000
Management Approach 2: RFB Enhancements
Look broadly to plan for new buffers and align related projects/funding | a) Coordinate with allied ag practices in NY especially streambank fencing, streambank stabilization and/or transitional woodland practice using AgNPS | NY NRCS and FSA, USC | New York | 2017-01-01 | $$
| b) Seek more opportunities to engage landowners about opportunities for RFB | State Leads | Baywide | 2017-12-01 | Stafftime
| c) Incorporate RFBs into planning efforts, e.g., the State Planning Board, county comprehensive plans, and local zoning ordinances | State Leads | Pennsylvania | 2017-12-01 | Stafftime
| d) Work with other programs and agencies that do preservation, restoration, etc. to improve overlap with RFB | State Leads | Baywide | 2017-12-01 | Stafftime
Accelerate RFB implementation through NFWF's 2015 Regional Conservation Partnership Program (RCPP) project award, "Comprehensive Watershed-Scale Restoration in Dairy and Livestock Landscapes of the Chesapeake Bay". | a) Utilize NFWF grant funding and technical and financial assistance 21:22 to increase implementation of RFB and C21 of existing cost-share funding | Stroud Water Research Center, Trout Unlimited, Chesapeake Bay Foundation, Alliance for the Chesapeake Bay, Bradford County (PA) Conservation District | Baywide | 2017-12-01 | $$
| b) Support local USDA NRCS and FSA staff, SWCDs, and NGOs in collaborating and prioritizing RCPP funding to enhance RFB CREP implementation at the local level |  |  |  | $$
Program adjustments in RFB cost-share practices (i.e., CREP) per state task force reports | Work with FSA to approve CREP amendments and make practice adjustments | State leads | Baywide | 2017-12-01 | Stafftime
Apply the Healthy Streams Farm Stewardship Program | a) Identify projects in conjunction with SWCD and ag consultants b) Conduct farmer and conservation professional workshops on the Program c) Help landowner with agreements and assist them with plantings | Alliance for the Bay | Maryland | 2017-12-01
Pilot voluntarily purchase of nutrient credits by businesses to pay for the installation of forest buffers | a) Work with partners like Businesses for the Bay to information out to businesses | PENNvest | Pennsylvania | 2017-12-01
b) Make purchases and establish RFB
Pursue a state/privately-funded RFB program | a) Test methods for flexibility in buffer administration and management | DCNR, DEP | Statewide
| b) Pilot sites showcasing different approaches including maintenance needs | DCNR, DEP | Priority watersheds
| c) Incorporate agroforestry practices into the RFB program | PA DCNR | TBD
Management Approach 3: RFB Technical Assistance
Increase staffing levels to provide more technical assistance | Hire 8 additional field personnel through grant from FSA | FSA, FS, ACB, State forestry in MD, PA, VA, WV | MD, PA, WV, VA | 2017-12-01 | 560K | 560K
Improve tracking and spending of TA funding provided by FSA | a) FSA provides TA funding for CRP/CREP to USFS and NRCS | State Leads | Baywide | 2017-12-01 | 4 M | 4 M | Funding includes TA on all CRP/CREP not just RFB
| b) Track and suggest improvements in spending as needed |  |  |  | Stafftime
Increase effectiveness of landowner education on RFB establishment and maintenance | a) Identify successful programs and begin expanding them in your state | State Leads | Baywide | 2016-06-01 | Stafftime
| b) Reach out to local groups with interest in RFB such as SWCDs, NGOs, Land Trusts, | State Leads | Baywide | 2016-04-01 | Stafftime
| c) Support PACD outreach efforts in creating a clearinghouse of informational materials | DCNR, DEP, PACD | Pennsylvania | 2017-12-01 | Stafftime
| d) Enhance collaboration among organizations to better understand farmers' needs | State Leads | Pennsylvania | 2017-12-01 | Stafftime
| e) Technical Service Providers receive training on RFB outreach through grant from FSA | USFS, ACB | Baywide | 2016-12-01 | 35K
| f) NRCS employees receive >3 trainings per year | NRCS | Baywide | 2017-12-01 | Stafftime
| g) Determine how best to engage SWCDs | USFS, ACB | Baywide | 2017-12-01 | Stafftime
Pilot strategies to reinforce incentives for producers to install and maintain riparian forest buffers | Work with a SWCD to pilot higher priority for EQIP when CREP buffer is used | NRCS, SWCD | TBD | 2017-12-01 | Stafftime
Expand partnerships to address technical assistance needs | Identify potential new partners and establish working agreements | State Leads | Baywide | 2016-01-01 | Stafftime
Use Regional Conservation Partnership Program projects to increase RFB enrollment | a) Conduct workshops with NRCS and conservation districts to market the opportunity b) Work with partners to identify projects and sign-up for RCPP c) Work with partners to provide technical assistance for planning and implementation | Alliance for the Bay | MD and PA | 2017-12-01 | $$ | $$ | funded, but more RFB opportunities are needed
Technical Assistance provided by NYS DEC Forester | Provide forestry support on EQIP and CREP projects | NYS DEC, USFS | Tioga and Broome Counties | 2017-12-01 | 120K/yr | 120K/yr | Joint Chief's funding through 2017
Management Approach 4: RFB Outreach and Increasing New Enrollment
Address programmatic design/delivery that are barriers to new enrollment | Work with decision-makers to secure state cost-share funding to process CRP/CREP new contracts | DNREC, DE FSA/NRCS | Delaware | 2016-01-01 | Stafftime |  | The Delaware CREP Program has a programmatic freeze until funding shortfalls are addressed. Shortfalls are approximately: $500,000 for 2015, $500,000 for 2016, and $300,000 for 2017 for current enrollments. Work-arounds are needed for new enrollees.
Execute Outreach Strategy for 2016 | Improve outreach of RFB: webinar education series, information packets, posters, displays, forum, support for re-enrollment | USFS, FSA, ACB | Baywide | 2016-12-01 | 184000 | 184K | funded
Improve outreach and education to landowners on RFB | a) Technical Service Providers receive training on RFB outreach through grant from FSA | USFS, ACB | Baywide | 2016-12-01 | 35K |  | Also see line 49
| b) NRCS employees receive >3 trainings per year | NRCS | Baywide | 2017-12-01 | Stafftime
| c) Determine how best to engage SWCD | USFS, ACB | Baywide | 2017-12-01 | Stafftime
Seek liaisons (leaders, early adopters) within farming communities | a) Reach out to dairy, horse, and poultry farmers, and others | Dept of Ag | Baywide | 2016-12-01 | Stafftime
| b) Reach out to plain sect community | PA CREP partners | Priority watersheds | 2016-12-31 | Stafftime
Increase MPL soil rental rates where feasible | Work with FSA to make adjustments in CREP agreements, as needed | State Leads | As needed | 2017-12-01 | Stafftime
Share local case studies of successful buffers-- how to integrate with better overall environmental health (e.g., LandCare model) | Reports on case studies and how LandCare model could be used | State Leads | MD | 2017-12-01 | Stafftime
Management Approach 5: Improve Establishment/Maintenance/Verification
Improve tracking and reporting of RFB implementation | a) Utilize GIS, CAST, and other tools | State Leads | Baywide | 2017-12-01 | Stafftime
| b) Analyze efficiencies and quantify benefits of RFB | FSA, USFS, ARS, PennState |  | 2017-12-01
| c) Track progress through reports and maps | DEP, DCNR |  | 2016-12-31
Survey recent NFWF grantees to determine extent of RFB vs. grassed buffer implementation | Develop, implement, and analyze survey of NFWF grantees to determine likelihood of RFBs going in on grants that don't specify type of riparian buffer being used | NFWF, USFS | Baywide | 2016-12-01 | Stafftime
Strengthen inter-organizational operations, including reporting, cross-training, and Verification for RFB BMP | a) States work internally with partners | State Leads | Baywide | 2017-12-01 | Stafftime
| b) Work with other Workgroups and Goal Teams to integrate RFB into planning | FWG/USFS | Baywide | 2017-12-01 | Stafftime
| c) Work with Ag Workgroup on improving Verification procedures for RFB | FWG/USFS | Baywide | 2016-12-31
Evaluate State RFB BMP Verification Protocol | Work with states to examine how RFB verification is working | USFS | Baywide | 2017-12-01 | Stafftime
Work with FSA to see about increasing annual maintenance payments | Annual maintenance payments increase (e.g., from $5/acre to $10/acre) where feasible | State leads, ACB, USFS | Baywide | 2016-12-01 | Stafftime
Work with FSA to see about increasing establishment period | Expand the RFB establishment period from 2 years to 3-4 years (already happened in PA) | State Lead | Baywide | 2017-12-01 | Stafftime
Work with FSA to make cost share available for weed suppression during RFB establishment | Determine level of invasive plant control cost-share that is part of extended establishment | State, FSA | Baywide | 2016-12-01 | Stafftime
Put maintenance tips in conservation plans, contracts, and landowner info | a) Produce information on common maintenance needs/issues for website/handbook | USFS, ACB | Baywide | 2017-01-01 | 12K | 12K | Part of FSA Outreach grant
| b) Distribute handbook to contract holders through SWCD and field offices | USFS, ACB |  | 2017-01-01 |  |  | Part of FSA Outreach grant
Evaluation of Buffer Effectiveness/Tree Planting Success | Complete evaluation of tree planting mortality/success for three years after initial planting and secure additional planting stock to correct planting failures | State lead | Baywide | 2017-12-01 | Stafftime
Management Approach 6: Improve Re-enrollment
Provide targeted outreach to CREP participants in the last 1-2 years of contract | a) Send postcards to expiring contract holders and follow-up with phone calls | FS, State FSA, ACB | Baywide | 2017-12-01 | 3K
| b) Provide maintainance crews to assist landowners with successful RFB | USFWS, CBF | Maryland | 2017-12-01 | $$
| c) Encourage TSPs re-enrolling RFBs to include upgrades, such as increased acres and/or alternative water, stream crossings, fencing | State Leads | Baywide | 2017-12-01 | Stafftime
Provide contact information for expriring contract holders to State Leads | Information provided to each state annually | FSA | Baywide | 2017-12-01 | Stafftime
Management Approach 7: Improve Targeting of RFB
Fund trials for function-based incentives | Perform work on NFWF grant | MDA | Maryland | 2017-12-01 | $$ |  | NFWF funded
Utilize CREP targeting tool developed by FWG | Make maps of high-priority areas for reforestation | State Leads | As needed | 2017-12-01 | Stafftime
Incorporate other WQ, brook trout and demographic targeting tools for RFB | a) Utilize tools to identify and implement RFB restoration opportunities considering climate change | VA, TNC | Baywide | 2017-12-01 | Stafftime
| b) Analyze for effectiveness |  |  | 2017-12-01 | Stafftime
Use high-resolution land cover data to map RFB and train partners on how to use the new data for prioritizing their work | a) Pilot method in James to target areas for new RFB | Chesapeake Conservancy, James River Assoc, NFWF, SWCDs | James River watershed | 2016-09-01 | $$
| b) Work with the SWCDs, JRA and others to independently incorporate the new high-resolution data into their planning and ranking frameworks |  |  | 2017-12-01 | $$
Management Approach 8: Ramp-up conservation of RFB easement programs
Increase participation with the Agriculture Conservation Partnership Program (ACEP) | Determine opportunities for CREP participants to transition enrollments to NRCS ACEP easement programs | NRCS | Baywide | 2017-12-01 | Stafftime
Improve easement language for RFB | Suggest acceptable language standards for RFB easements | FWG | Baywide | 2016-12-01 | Stafftime
Management Approach 9: Focus on non-ag RFB
Programs to reduce mowing | # State/County-level programs | State Leads | Baywide | 2017-12-31
| a) Work with federal land managers to promote RFB | USFS | Baywide | 2017-12-01 | Stafftime
| b) Target locations through GIS analysis | PA, MD, VA | Golf courses, schools, public lands etc | 2016-12-31 | Stafftime
Work with local groups to expand tree planting programs | Successful programs such as Turf to Trees, Backyard Buffers, and CLIPS (Baltimore Co)--meet with LGAC, local leadership group, and others to determine how best to do this | FWG | Baywide | 2017-12-01 | Stafftime |  | Consistent funding source-- Where is overlap with TC Strategy
Coordinate with MS4 permits | Meeting to assess options, needs | SRCC | Baywide | 2017-12-01 |  |  | Overlap with TC Strategy
| Develop examples of buffers & SWM | CWP | As appropriate | 2016-12-01
Increase CBIG funding for RFB establishmenton urban lands | Assign 1-2 additional no-ag buffer projects to CREP foresters | WVDOF | Priority watersheds | 2017-12-01 | $$
Open Field Initiative targeting areas for tree planting that are otherwise abandoned | Identify and contact landowners | VDOF | Central Virginia | 2017-12-01 | $$