## Schedule
Deliverable | Jurisdictional Schedule | FF Schedule | Notes for FFWG Consideration | Based on the notes what actions are there here that we could set a deliverable/schedule?
All Phase 6 data inputs due (except land use) September 30, 2016 | 2016-12-31 | 2016-11-01 | FF inputs included property boundary information, historical BMPs from 1985 and SY16 Progress BMPs.
Rolling local review of the Phase 6 land use data | October-early Nov 2016 | Decision on AG land uses may be requested by the WQGIT during their F2F on 12/19/2016 | There is currently an outstanding issue related to Agricultural land use assignment on federal lands and facilities. USGS via the federal facilities editor tool requested federal facility contacts input four low vegetation land use classes (mixed open, turf, pasture and crop). The FFWG recently discovered that ag land uses were not currently coded for federal lands and facilities. A small group of interested FFWG met to discuss possible options for considering ag land uses on federal lands and facilities (three options). EPA and VA have discenting views.
Final Phase 6 land use dataset due | 2016-12-01 |  | See note above from Row 4.
EPA releases draft3 expectations for Phase III WIPs | 2017-01-01 | 2017-03-15 | Federal agencies may wish to comment on these expectations. Due date is dependent on EPA's timeline for when they would like comments back. Estimated due date for federal response. Reponses: funneled up to Jim Edward
Final calibration of Phase 6 Model | January – March 2017 |  | Would need to get presentation from Jeff Sweeny to provide results of progress input deck of Federal agencies. Not sure what input FFWG would need to provide here; looking to jurisdictions for guidance. | Gary Shenk / Lew Linker to provide input possibly.
Final recommendations on approaches for local area targets | 2017-03-01 | What is the schedule for moving the decisions up the partnership? | FFWG continues to participate. FFWG may want to put forth a position on the topic. If so, now is the time to do that prior to the WQGIT decision to support the recommendations document. | Final recommendations final 12/9; presented at the WQGIT 12/19
Partnership fatal-flaw review of final Phase 6 Model | March-May 2017 |  | See note from Row 7.
EPA releases final expectations for Phase III WIPs | 2017-04-01 | FF guidedance by March 2018 | Once final expectations are released, the FFWG could take on developing a Federal WIP guidance document that could incorporate some of the expectations that may impact them. | FF Guidance can provide the discussion on what should be included in Phase III WIPs as it relates to FF. Discuss Federal Phase III WIP Participation Document.
Release of final Phase 6 Model | 2017-06-01
EPA releases draft4 Phase III WIP Planning Targets | 2017-06-01 |  | Need to work with jurisdictions in determining impacts and possible revisions for FF targets and development of local area planning goals.
EPA releases final Phase III WIP Planning Targets | 2017-12-01 |  | Once Planning Targets are final can begin to understand changes and continue to work with jurisdictions in determining revisions for FF targets and development of local area planning goals. | BayFAST; new or current revised Targets to submitt scenarios for planning 2025. Convert it to a reporting tool. Maybe after the first of the year, we can get to talking with BayFAST developers for enhancements.
Draft Phase III WIPs due to EPA | 2018-08-01 | 2018-06-01 | Any input needed from federal facility contacts? Federal agencies need to review WIPs to understand changes from Phase II and possible impacts to increases in implementation requirements. | Inputs to jurisdictions based on the guidance for WIP 3. Narrative content and planning scenarios.
EPA feedback on draft Phase III WIPs | 2018-10-01 |  | FFWG review feedback from EPA on each jurisdiction to determin if there are any impacts.
Final Phase III WIPs due to EPA | 2018-12-01 |  | Roll-out

## Comments
Agency | Comment / Questions | Response / Proposed Change or Addition to Schedule
NPS | The Phase 6 model will be released 6/2017, how soon after that will it be loaded into BayFast? | Recommend discussing with BayFAST development team, their schedule and incorporating changes to all of the planning and scenario tools. | Revise Schedule to incorporate BayFAST revisions
NPS | EPA releases the final Phase III WIP Planning Targets 12/2017 – are these the new Federal Facility Targets? Are these expected to be included in the 2018-2019 Milestone Plans, if so when are those due? Or are the 2018-2019 Milestone Plan still due 11/1/2017? | No, the Phase III WIP Planning Targets are released to the jurisdictions and are for the major state river basins. These values will inform additional strategies for inclusion in Phase III WIPs. Between the time the Jurisdictions are provided the planning targets, they will need to develop local area planning goals below the major state river basin and federal facility targets. Those stakeholders would need need to provide their input for implementation through 2025. All between 12/17 and 5/18. | Revise schedule and include milestone reporting and progress reporting deadlines. The milestone reporting schedule is out of sync. Not sure if all of the 18/19 milestones (regardless of whether you are a federa or state agency) will be based off 5.3.2 or the draft Phase III WIP Planning Targets. The partnership needs to figure this out and federal agencies will need to determine if jurisdictions will be taking the draft planning targets and determining draft local area planning goals and federal facility targets since the 18/19 milestones are still due on 11/1/17.
NPS | Is the 2017 BMP reporting still due 10/1/2017? Or have we pulled all BMP reporting forward as we did this year? And please remind me what that new date is, thank you. | It is my understanding that progress reporting data for BMP implementation is due on 10/1/2017
VDEQ | The Task Force's final recommendations on Local Planning Goals are on the 12/19 WQGIT agenda for decision.
VDEQ | EPA is releasing Draft Expectation in 1/2017, I would suggest building the FF Guidance from that then making any needed adjustments when the Final Expectations are released in 4/2017. Either way, I think the FF Guidance should be on the street before the end of 2017.
VDEQ | VA, and I suspect other jurisdictions, will need the FF WIP 3 input by April/May 2018 (Same as for local partners). By June 2018 we will be beginning the internal review of the completed document to ensure submission to EPA and release for public comment by August 2018. The date could slide toward mid-May if we are getting a single set of WIP inputs for all FFs and would need to shift toward early April if the inputs are from each FF individually.