## Sheet1
GIT | GIT Needs from STAR | Timeline
Climate Resiliency | 4 workgroups for Climate monitoring | 2017-12-01
| Outline Gaps for Climate Monitoring | 2017-12-01
| Explore Citizen monitoring for climate | TBD
| ID Costs for climate monitoring gaps | 2017-12-01
| ID agencies for monitoring gaps | 2017-12-01
| ID overlap in monitoring and modeling efforts | 2017-12-01
| Assess multi-scale climate assessments | 2017-12-01
| synthesize research on sea level, precip, temp trends | 2017-12-01
| Assess climate change influence on flow, temp, WQ in streams | 2016-2017
| Develop climate indicators | 2017-12-01
Ocean Acidification
Sustainable Fisheries | ID healthy habitat criteria | 2017-06-01
| ID spatial tools and datasets to map ranges and stressors | 2017-06-01
| Convert fish and habitat survey data to spatial datasets | 2017-12-01
| Explore options for monitoring programs to cover range of species | Early-Mid 2016
| Determine feasibility of phytoplankton and zooplankton monitoring | Mid 2016
| Develop shallow water monitoring survey proposal for gaps | Mid 2016
Forage fish indicator
Pair WQ data with living resources data
Improved fish habitat maps
Oyster indicator development
Shoreline indicator development
Updating blue crab stock assessment
Oyster monitoring
Habitat | Expand USC wetland mapping model | 2017
| Wetland Acres reporting to NEIEN | Ongoing
| QA/QC of wetland data | Ongoing
| Input for indicator development beyond Chessie BIBI | 2017
| support for reporting progress for Chessie BIBI | ongoing
| interaction with Healthy Watershed GIT tracking current status of streams | 2017
| Assist with incorporation of new indicator | 2017
| Funding for Aerial surveys | 2017-03-01
| Improve SAV component of shallow water model | 2017
| ID climate changes threats and SLR to SAV | 2017
| Assist with economic value assesssments of SAV | 2017
| Assist with ID of brook trout locations for reporting in patch layer | 2017
| funding for brook trout monitoring | Ongoing
| New Indicator (3-5 year occupancy census) | Ongoing
| Development of habitat-based indicator | 2017
Water Quality | WQ Criteria Attainment patterns summary | June, 2016
| Update in patterns in WQ standards attainment DO, clarity/SAV and chlorophyll | December, 2016
| Publish WQ Criteria Tech Addendum | December, 2016
| Implement new process to quantify trends in tidal WQ parameters | Annually in 2016/2017
| WQ results attained from 2 of 6 high flow events for mid point assessment | 2017
| Monitor high flow events at Conowingo | On/before May 30, 2016
| Conowingo impacts on WQ monitoring plans | On/before May 30, 2016
| 125 sites of nutrient and sediment samples | 2016-2017
| Update loads and Trends USGS | 2016-2017
| USGS to update reporting/communicating of loads to Bay | 2016
| expand on BEI report for add'l monitoring needs | 2016-2017
Incorporate Citizen Science Monitoring for WQ standards
develop targeted shallow water monitoring strategy
| Test watershed factors influencing WQ trends in tidal waters | 2016-2017
| Release report/communication of nitrogen sources | 2016-2017
Compare observed and expected trends in watershed
Improve knowledge of sed and N sources
Use WQ data to assess PA's progress
WQ functions of wetlands
Improve understanding of tidal water response to load changes
| Develop land cover dataset | 2016
Enhance watershed and SPARROW model
Examine Susquehanna reservoirs' impact on N and sed transport
Assess N and sed response to management practices
| Incorporate BMP efficiencies and land cover/use | Oct. 2015 - October 2016
| Conduct STAC peer reviews | Winter/Spring 2016
| Run scenarios and modeling tools | January 2016 - September 2016
Healthy Watersheds | Compile existing Climate change vulnerability data/tools | 2017-12-01
| Work with CRWG to refine Climate Decision Matrix | 2017-12-01
| Review findings from NAC Comprehensive study | 2017-12-01
| Review/incorporate findings from TNC study | 2017-12-01
| Review/incorporate findings from USGS Shale Gas Development study | 2017-12-01
Review/incorporate findings from Habitat and Resiliency TNC study
Use NALCC's map layers to ID conservation opportunities
| compile/publish bi-annual CBP Lands dataset | Bi-annually (last dataset Spring 2016)
| Track and refine tracking process for protected lands data | ongoing
| Overlay data with Healthy Watersheds and other partners for progress | ongoing
| Determine current and future monitoring needs | 2017-12-01
Form a cross-GIT tracking workgroup
Monitor progress of land use to use in tracking framework
Note on B2: CRCStaffers: Work with 4-select Workgroups to determine current and future monitoring needs by geography, habitat type, and BMP and outline gaps at Wokrgroup or GIT level.
Note on B3: CRCStaffers: Outline gaps for watershed scale monitoring effort, including gaps related to monitoring of non-climate stressors that could exacerbate climate impacts to Chesapeake Bay habitat or BMPs.
Note on B4: CRCStaffers: Explore the use of citizen-based monitoring networks.
Note on B5: CRCStaffers: Identify costs associated with closing monitoring gaps.
Note on B6: CRCStaffers: Identify agencies/organizations through which commitments could be sought to fund or participate in filling monitoring gaps.
Note on B7: CRCStaffers: Identify geographical overlap in monitoring and modeling efforts to explore opportunities for cost saving efficiencies and integration of priorities to include climate factors.
Note on B8: CRCStaffers: Assess international, national, regional and state-level (DE, MD, PA, WV, VA, NY, DC) climate change assessments.
Note on B9: CRCStaffers: Synthesize latest scientific research on sea level and water level trends; precipitation and evapotranspiration; and temperature change in both air and water
Note on B10: CRCStaffers: Assess effects of climate change on flow, temperature, and waterquality in streams of the Bay watershed. Work will build off USGS analysis examining changes in flow and temperatures in streams. USGS will be working with fish biologists on implications for freshwater populations and will also be looking at potential approaches to assess effects on nutrient and sediment loads. (listed under Modeling workgroup)
Note on B11: CRCStaffers: Work with STAR and STAC to recommend and establish performance metrics and/or indicators to assess Climate Resiliency Goal and Outcome implementation
Note on B12: CRCStaffers: Ocean Acidification: discussed at Dec 2016 STAR meeting to be added as potential STAC workshop or STAR meeting focus
Note on B13: CRCStaffers: Use the priority species habitat stressor analysis from management approach 1 to identify healthy habitat criteria for species.
Note on B14: CRCStaffers: Identify spatial tools and datasets that can be utilized to map the seasonal ranges of priority species habitats and stressors identified under management approaches 1 and 2.
Note on B15: CRCStaffers: Convert existing fish and habitat survey data for priority species to spatial datasets where needed.
Note on B16: CRCStaffers: Explore options to modify existing monitoring programs that will reduce costs and cover a range of species. This is captured in an undergraduate project by Jeremy Carton (exploring benthic and pelagic sampling gear for use in citizen science projects) and in the FY16 GIT-funded Citizen Science project which features a similar pilot study, which will be informed by Jeremy’s project to gauge the feasibility of introducing forage sampling into a Chesapeake Bay-wide citizen monitoring effort.
Note on B17: CRCStaffers: Work with partners to evaluate the feasibility of restarting phytoplankton and zooplankton monitoring. Had a discussion on the feasibility and need of restarting phytoplankton and zooplankton monitoring with Forage Action Team at September Quarterly meeting.
Note on B18: CRCStaffers: Develop a proposal for shallow-water monitoring survey(s) that address identified gaps
Note on B20: CRCStaffers: Provided at Dec STAR 2016 meeting. PT Comment: Need more direction here.
Note on B21: CRCStaffers: Develop improved fish habitat maps (convene a meeting in which STAR, GIS, and fish habitat team members develop these maps using recent data sources) STAR can maybe start that conversation. It was discussed at Dec 1 STAR meting that this might be the first step to focus on.
Note on B22: CRCStaffers: Discussed at Dec STAR 2016 meeting
Note on B23: CRCStaffers: Discussed at Dec 2016 STAR meeting
Note on B24: CRCStaffers: Discussed at Dec 2016 STAR meeting as a need, although the workgroup is looking outside CBP to address
Note on B25: CRCStaffers: Discussed at Dec 2016 STAR meeting as a need, although the workgroup is looking outside CBP to address
Note on B26: CRCStaffers: Not in Workplan: Expand Upper Susquehanna Coalition predictive wetland mapping model from Chesapeake portion of PA to entire watershed.
Note on B27: CRCStaffers: Consistent reporting of wetland acres (including enhanced) from states to NEIEN
Note on B28: CRCStaffers: QA/QC of wetland data (Jackie Johnson used to do this; HGIT has lost but needs support of one of the science contractors for this and other data)
Note on B29: CRCStaffers: Advice on indicator (metric) development beyond Chessie BIBI to support tracking and reporting. Include reconciliation of scale issues between Bay-wide metric (BIBI) and response of stream health and function due to restoration projects
Note on B30: CRCStaffers: Support to determine and report progress for Chessie BIBI (see Key Action 3 in Biennial Workplan) (Note: this is currently not funded but a necessary step to report on recommendations from ICRPB. See Key Actions 1 (Update and refine the Bay basin wide (Chessie BIBI) for streams, and 2 (Establish 2008 baseline and approach for determining future trends %change).
Note on B31: CRCStaffers: Interaction with Watershed GIT for tracking current status of streams.
Note on B32: CRCStaffers: Assist in applying the new method and incorporation to the Bay Program indicators.
Note on B33: CRCStaffers: Continued funding for aerial surveys (consider whether needs to be annual)
Note on B34: CRCStaffers: Not in Workplan
Note on B35: CRCStaffers: Not in workplan: Characterize threats posed to SAV by climate change and sea level rise
Note on B36: CRCStaffers: Not in workplan: Assist with economic value assessments of Chesapeake Bay SAV
Note on B37: CRCStaffers: Not in workplan: Assistance with the identification of Brook Trout focus locations within CBW for annual reporting using EBTJV’s Patch Layer (Due Dec. 2016) Brook Trout Indicator will be EBTJV's 3-5 year state populated Occupancy Census. Annual reporting will bein the form of locations of BT work focus in the CBW on EBTJV's Patch Layer
Note on B38: CRCStaffers: Continued funding for brook trout monitoring (summer of 2017 and beyond)
Note on B40: CRCStaffers: Not in workplan: Assistance with development of a habitat-based indicator (to be based on results of habitat prioritization map that was recently delivered)
Note on B41: CRCStaffers: Summarize patterns in water-quality criteria attainment over time in tidal waters from 1985-2014
Note on B42: CRCStaffers: Provide an update describing temporal and regional patterns in water quality standards attainment of dissolved oxygen, water clarity/SAV and chlorophyll.
Note on B43: CRCStaffers: Publish a new Ambient Water Quality Criteria Technical Addendum that provides updated guidance on water quality standards attainment assessment methods for the tidal bay jurisdictions
Note on B44: CRCStaffers: Implement new process for quantifying trends in tidal water-quality parameters. The new process incorporates advances in methods to provide more information on trends in water-quality patterns over time.
Note on B45: CRCStaffers: Water quality results attained from 2 of the 6 high flow events assessed in April 2015 will be submitted to the CBP to be included in the 2017 CB Mid Point Assessment
Note on B46: CRCStaffers: Monitor any high flow event of greater than 100,000 cfs at Conowingo Dam occurring before May 30, 2016
Note on B47: CRCStaffers: Develop alternative monitoring plans to gather sufficient information to inform Conowingo impacts on Bay water quality standards now that it has reached "dynamic equilibrium" in the event than less that 6 high flow events occur before May 30, 2016
Note on B48: CRCStaffers: The partners in the network will collect nutrient and sediment samples from over 125 sites throughout the watershed.
Note on B49: CRCStaffers: The USGS will work with the partners to compile quality assure the information to update loads and trends.
Note on B50: CRCStaffers: USGS will completely update the reporting of loads to the Bay and trends of nutrients and sediment loads in the watershed; revised products will be prepared to communicate these results.
Note on B51: CRCStaffers: Expand upon the water quality-focused Building Environmental Intelligence report to a new process to address additional monitoring needs associated with the 2014 Chesapeake Bay Agreement. Integrate the role of Citizen Science to address gaps in water quality-related monitoring and assessment needs. Work with partners and Management Board to consider and attempt to implement recommendations.
Note on B52: CRCStaffers: Coordinate and integrate Citizens Monitoring effort funded by the Chesapeake Bay Program. Develop high quality citizens monitoring programs to assess water quality standards. Target areas where implementation will potentially show progress.
Note on B53: CRCStaffers: Develop strategy to target shallow water monitoring program with limited resources. Incorporate all spatially and temporally intensive monitoring results into Bay water quality standards attainment.
Note on B54: CRCStaffers: Test watershed factors influencing water-quality trends in tidal waters.
Note on B55: CRCStaffers: Release of a report and communication products regarding nitrogen sources and transport processes in smaller agricultural and urban watersheds.
Note on B56: CRCStaffers: Compare observed and expected trends in the watershed and relation to management actions.
Note on B57: CRCStaffers: Improve knowledge of sediment and nitrogen sources and residence times.
Note on B58: CRCStaffers: Utilize empirical, historical and current water quality data to assess Pennsylvania's progress towards meeting goals.
Note on B59: CRCStaffers: Improve knowledge of the water-quality functions of created and restored nontidal wetlands.
Note on B60: CRCStaffers: Support efforts to improve the understanding of tidal water response to changes in watershed loads.
Note on B61: CRCStaffers: Develop a new land-cover data set for the CBP watershed model.
Note on B62: CRCStaffers: Enhance the CBP watershed model using USGS measured loads for calibration as well as SPARROW model, groundwater models and other science findings.
Note on B63: CRCStaffers: Examine the impact of Susquehanna reservoirs on changes in nutrient and sediment transport to Chesapeake Bay.
Note on B64: CRCStaffers: Better utilize monitoring data to assess progress and explain observed changes in nutrients and sediment in response to management practices.
Note on B65: CRCStaffers: Incorporate data inputs, such as BMP efficiencies and land use/land cover
Note on B66: CRCStaffers: Regarding MA3 KA4. Release beta and final version of the Phase 6 Watershed Model
Note on B67: CRCStaffers: Regarding MA3 KA4. Release beta and final version of the Phase 6 Watershed Model
Note on B68: CRCStaffers: Compile existing climate change vulnerability research and data, including available assessment products and tools.
Note on B69: CRCStaffers: Work with Climate Resiliency workgroup to refine Climate Resiliency Analysis Decision Making matrix and recommend implementation process for applying matrix analysis and decision-making process to other Management Strategies such as the Healhty Watersheds Management Strategy.
Note on B70: CRCStaffers: Review and incorporate findings from the North Atlantic Coast Comprehensive Study: resilient Adaptation to Increasing Risk. This refers to Appendix A, Egnineering.
Note on B74: CRCStaffers: Incorporate the North Atlantic Landscape Conservation Cooperative work which identified RCOA's (Resource Conservation Opportunity Areas). Hs work is a roll-up of map layers that include climate resiliency information as well a development and other stressor information, to help managers hone in on the areas of greatest conservation (and restoration) opportunities for terrestrial and aquatic wildlife habitat. (see northatlanticlcc.org under "projects".)
Note on B75: CRCStaffers: Compile and publish bi-annaul Chesapeake Bay Protected Lands Dataset: Compile primirary source datasets from authorative partners.
Note on B76: CRCStaffers: Work towards continually tracking and refine/improve tracking process for protected lands data.
Note on B77: CRCStaffers: Overlay data with Healthy Watersheds and other partner conservation goals above to report on progress.
Note on B78: CRCStaffers: Work with STAR to determine current and future monitoring needs by geography, habitat type, and BMP and outline gaps at Workgroup or GIT level.
Note on B79: CRCStaffers: Form a cross-GIT tracking workgroup to work on : healthy watershed metrics, analyses of plans/protocol for determining status of each watershed in succeeding years, assessments of watershed protection priority, and exploring a method to track "marginally" healthy waters and watersheds
Note on B80: CRCStaffers: Monitor Progress of key actions related to high resolution imagery processing and work with LUWG to determine how data can be incorporated into a healthy waters and watershed tracking frmework.