## (Climate Resiliency) Workplan
Outcome: Monitoring and Assessment
Goal: Climate Resiliency
Outcome: Continually monitor and assess the trends and likely impacts of changing climatic and sea leel conditions on the Chesapeake Bay ecosystem, including the effectiveness of restoration and protection policies, programs and projects
Long term Target: ...by 2025
2 year Target: ...by 2016
Management Approach 1: Define Goals and Establish Baselines
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. | Current Efforts Activities underway or proposed that could support key action | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Establish baselines for the monitoring, modeling, and assessment of different aspects of climate change | Develop methodogy and assessment tool (i.e., matrix) to analyze climate related factors for each Management Strategy | [7 empty] | Funding Proposal Ideas for Discussion
| Develop a process for coordination with and among individual GITs, the larger research community and stakeholders to identify the linkages of climate to each outcome and evaluate whether those linkages are well understood or need further research. | [8 empty] | MA#1/AD#3
| Perform analysis using methodoligy and process developed above. | [8 empty] | MA#2
| Identify climate related factors, metrics and/or indicators for all Management Strategies | [8 empty] | MA#3/AD#2
Conduct an evaluation of existing data, research, studies, tools, as they relate to climate and the needs for select management strategies. | Select several (<3) Management Strategies to conduct thorough documentation and evaluation
Management Approach 3: Prioritize climate impacts
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. |  | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Perform a consultative prioritization to determine which of the gaps are most critical to outcome attainment. | Select and document priorities
Management Approach 4: Design monitoring and modeling plan
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. |  | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Determine if the monitoring data being collected and the tools that are available can answer answer assessment tool questions | Evaluate existing monitoring data and available assessment tools to determine if they are adequate to fully explain the relationship of the future impact of climate on the outcome. |  | Climate Work Group In coordination with GITs
Define likely current and future monitoring needs by geography, habitat type, and BMP
Develop an integrated monitoring and assessment plan, including necessary forecast and/or projection models, for priority aspects of climate change. | Develop a monitoring plan and research agenda for the prioritized gaps that have been identified in terms of assessment tools, scientific understanding, and baseline monitoring.
Identify costs associated with closing those gaps
Identify agencies/organizations through which commitments could be sought to achieve long-term monitoring.
Management Approach 5: Assess Trends and Conduct Assessments
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. |  | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Assess trends and document observed changes in sea level, precipitation patterns, bay temperature, and the ecosystem responses. |  | MD's Bay Acidification Task Force addressed how changing Bay chemistry negatively impacts Maryland’s coast and shellfish industry. The Task Force studied and assessed water quality in Maryland’s Chesapeake and coastal bays, and reviewed ocean acidification studies and findings from other states. The group presented recommendations for monitoring and addressing acidification, and its effects on Maryland’s commercial fishery and aquaculture industry in January, 2015. | Work Group; Federal Agencies and State Agencies; Academic Partners
Chesapeake Bay Climate Sensitivity Assessment: using weather, water, biological, and climate data from a variety of sources and a state of the art biophysical model (the Chesapeake Bay Ecological Prediction System) to address the needs and goals of the Chesapeake Bay NERRS, the Chesapeake Bay Program, and NOAA’s Chesapeake Bay Sentinel Site Cooperative. http://coastalscience.noaa.gov/about/centers/col
Chesapeake Bay NERRS can contribute to scientific understanding of climate change and monitor ecosystem changes. NERR's could assess climate change impacts on human and estuarine ecosystem communities, vulnerability of these communities, and their capacity for adaptation and mitigation.
In 2011, NOAA selected the Chesapeake Bay as one of five initial regional Sentinel Site Cooperatives to demonstrate the value of using a place-based approach to address issues of local, regional and national significance. The Coop provides integrated observations across a host of environmental monitoring programs within the Bay area. The goal of the cooperative is to provide information to Chesapeake Bay communities and managers who need to address challenges such as storm flooding, long term, local sea level rise, barrier island movement, degraded water quality, and wetland loss.
Coastal SEES: Chesapeake Bay Sustainability: Implications Of Changing Climate And Shifting Management Objectives - A National Science Foundation funded collaborative project lead by VIMS that aims to develop an advanced modeling framework that integrates the physical, biogeochemical, and human components needed to simulate and select climate change adaptation strategies that will support a sustainable system. The National Science Foundation - Science, Engineering and Education for Sustainability (SEES) Program provides a funding mechanism to advance science, engineering, and education to inform the societal actions needed for environmental and economic sustainability and sustainable human well-being.
Management Approach 6: Develop a Research Agenda
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. |  | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Compile list of data and research needs. | Catalog current data, research, studies and tools for select Mgmt. Strategies | Landscape Conservation Cooperatives are partnerships between federal agencies, states, tribes, non-governmental organizations, universities, and other entities to collaboratively define science needs and jointly address broad-scale conservation issues, such as climate change in a defined geographic area. | Climate Work Group; Select Work Groups; STAC
Conduct a gap analysis for select Mgmt. Strategies using the catalog of data, research and tools
Conduct a review of existing data and research needs assessment and status of implementation and identify outstanding needs and prioirties related to CB Management Strategy Goals and Outcomes
Conduct targeted research to improve understanding of cliimate impacts or fill critical data or research gaps. | Evaluate climate change mitigation and adaptation benefits of water quality BMPs for forest, ag and urban sectors
Identify climate "hot spot" areas that threaten the bay and local communities or infrastructure for monitoring
Management Approach 7: Reassess priorities and revise goals
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. |  | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Review progress on a biennial basis, with particular emphasis on evaluating progress toward the closing of gaps in baseline monitoring and gaps in assessment tools and scientific research. | Re-prioritize gaps that remain in monitoring and scientific understanding.
Management Approach 8: Undertake Public, Stakeholder and Local Engagement
Key Action** Description of work/project. Define each major action step on its own row. Identify specific program that will be used to achieve action. | Performance Target(s) Identify incremental steps to achieve Key Action. |  | Participating Entity Identify responsible partner for each step. | Geographic Location | Timeline Identify completion date (month & year) for each step) | Estimated Project Cost Best estimate of total project cost (needed) | Available funding by Partner | Factors Influencing and/or Gap Identify related factor or gap in Management Strategy
Increase availability and access to monitoring and assessment data to support stakeholder discussions on the socioeconomic impacts of climate change on the Bay. | Collaborate with stakeholders in the development of data synthesis products for their use.
Develop climate data and information portal
Participate in 3-5 regional climate workshops or public events to increase awareness