## MBM-MTM Elements and Timeline
Main Bay Model (MBM) Tasks and Timelines
January 3, 2022
Calendar Year |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027
Calendar Quarter |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Project Year |  | 2022 Q1: Year 1; 2023 Q1: Year 2; 2024 Q1: Year 3; 2025 Q1: Year 4; 2026 Q1: Year 5; 2027 Q1: Year 6
Task 1. Initial MBM-MTM Development (2022 – 2023) | Task 1 | bar: 2022 Q1 to 2023 Q4
1-1. Kick-off MBM meeting, with follow-up CBPO Quarterly meetings (Q1-Q2: 2022). | Task 1.1 | bar: 2022 Q1 to 2022 Q2
1-2. Integrate the latest ICM changes into MBM (Q1-Q2: 2022). | Task 1.2 | bar: 2022 Q1 to 2022 Q2
1-3. Revise the current MBM mesh as needed to achieve best scale-performance tradeoffs (Q1-Q3: 2022). | Task 1.3 | bar: 2022 Q1 to 2022 Q3
1-4. Revise MBM mesh to account for channels in MBM and MTMs (Q1-Q2: 2022) | Task 1.4 | bar: 2022 Q1 to 2022 Q2
1-5. Performance tuning of MBM to achieve 1991-2000 simulation in one day (Q1-Q3: 2022). | Task 1.5 | bar: 2022 Q1 to 2022 Q3
1-6. Work with watershed, airshed, hydrological modeling group's inputs (All Qs: 2022-2023). | Task 1.6 | bar: 2022 Q1 to 2023 Q4
1-7. Develop boundaries of MBM, WSM, and tidal wetlands (Q1: 2022). | Task 1.7 | bar: 2022 Q1
1-8. Quantify how boundaries of MBM, WSM, and tidal wetlands will change with SLR (Q2: 2022). | Task 1.8 | bar: 2022 Q2
1-9. Develop SAV simulation approach: explicit beds or bounded seed in every mesh (All Qs: 2023). | Task 1.9 | bar: 2023 Q1 to 2023 Q4
1-10. Establish MBM-MTM boundary interfaces for all MTMs (All Qs:2022). | Task 1.10 | bar: 2022 Q1 to 2022 Q4
1-11. Develop MTM grids in anticipation of MTM teams (All Qs: 2022). | Task 1.11 | bar: 2022 Q1 to 2022 Q4
1-12. CBP decision makers to finalize 5 MTMs (Q2-Q3: 2022). | Task 1.12 | bar: 2022 Q3 to 2022 Q4
1-13. Link with initial P7 WSM hydrology (Q4: 2022, Q1: 2023). | Task 1.13 | bar: 2022 Q4 to 2023 Q1
1-14. Link with initial P7 WSM sediment load estimates (1Q-Q2: 2023). | Task 1.14 | bar: 2023 Q1 to 2023 Q2
1-15. Link with initial P7 WSM nutrient load estimates (3Q-Q4: 2023). | Task 1.15 | bar: 2023 Q3 to 2023 Q4
1-16. Expand temporal domain of MBM to focus on 1991-200 and other key years (All Qs: 2022-2023). | Task 1.16 | bar: 2022 Q1 to 2023 Q4
1-17. Initial work to improve shallow water dynamics in MBM (All Qs: 2022-2023). | Task 1.17 | bar: 2022 Q1 to 2023 Q4
1-18. Initial work to improve shallow water dynamics in MTMs (All Qs: 2023). | Task 1.18 | bar: 2023 Q1 to 2023 Q4
1-18. Initial work on basic living resource linkages of refined chlorophyll, wetlands, & SAV (All Qs: 2022-2023). | Task 1.19 | bar: 2022 Q1 to 2023 Q4
1-19. Initial work on potential linkage to higher trophic levels MBM & MTMs (All Qs: 2023). | Task 1.20 | bar: 2023 Q1 to 2023 Q4
1-20. Initial work of using MBM and MTMs to better resolve CBP problem segments (All Qs: 2023). | Task 1.21 | bar: 2023 Q1 to 2023 Q4
1-21. Initial work on examining CC influence on phenology MBM & MTM (All Qs: 2023). | Task 1.22 | bar: 2023 Q1 to 2023 Q4
Task 2 Interim MBM and MTM Development (2023 – 2024) | Task 2 | bar: 2023 Q1 to 2024 Q4
2-1. Initiate MTM activities (Q1-Q2: 2023). | Task 2.1 | bar: 2023 Q2 to 2023 Q3
2-2. Kick-off joint meetings of MBM and MTM Teams with Mod WG (Q1-Q2: 2023) | Task 2.2 | bar: 2023 Q1 to 2023 Q2
2-3. Conduct full initial calibration and verification of hydrodynamic and WQ model output (Q3-Q4: 2024). | Task 2.3 | bar: 2024 Q3 to 2024 Q4
2-4. Address important knowledge gaps in ICM (All Qs: 2024). | Task 2.4 | bar: 2023 Q1 to 2024 Q4
2-5. Begin completion of work to improve shallow water dynamics in MBM (All Qs: 2024). | Task 2.5 | bar: 2023 Q3 to 2024 Q4
2-6. Begin completion of work to improve shallow water dynamics in MTMs (All Qs: 2024). | Task 2.6 | bar: 2023 Q3 to 2024 Q4
2-7. Completion of work on basic living resource linkages of refined chlorophyll, wetland, and SAV simulation and potential linkage to higher trophic levels (All Qs: 2024). | Task 2.7 | bar: 2023 Q4 to 2024 Q4
2-8. Completion of work using MBM and MTMs to better resolve CBP problem segments (All Qs: 2024). | Task 2.8 | bar: 2024 Q1 to 2024 Q4
2-9. Completion of work examining CC influence on SAV, shallow water, & phenology of CC watershed loads and tidal Bay processing (All Qs: 2024). | Task 2.9 | bar: 2024 Q1 to 2024 Q4
2-10. Improve nutrient speciation simulation by better tracking the watershed to tidal Bay and the tidal water to sediment exchanges of the different nutrient species (Q3-Q4: 2023 & Q1-Q2: 2024). | Task 2.10 | bar: 2023 Q3 to 2024 Q2
Task 3 Final MBM and MTM Development (2005) | Task 3 | bar: 2025 Q1 to 2025 Q4
3-1. Provide a fully operational MBM that meets the needs of CBP (Q2-Q3: 2025). | Task 3.1 | bar: 2025 Q2 to 2025 Q3
3-2. Finish documentation on the software package in a report that will include detailed documentation on model structure, major code changes, validation and calibration procedure and usage (Q4: 2025). | Task 3.2 | bar: 2025 Q4
3-3. Demonstrate feasibility and utility of using a state of the science UG model to better estimate Chesapeake WQ standards in shallow open waters under 2035 and future climate change conditions (All Qs: 2025). | Task 3.3 | bar: 2025 Q1 to 2025 Q4
3-4. Transfer the software package to CBPO for operational testing, and work with CBPO personnel to test the model package under operational settings and resolve any issues that may arise (Q3-Q4: 2025). | Task 3.4 | bar: 2025 Q3 to 2025 Q4
3-5. All MBM and MTMs fully operational (Q4: 2025). | Task 3.5 | bar: 2025 Q4
3-6. Conduct full review of al MBM and MTMs with CBP technical and management groups and with STAC (All Qs: 2026). | Task 3.6 | bar: 2026 Q1 to 2026 Q4
3-7. Review all recent studies related to Bay WQ processes and work with CBP and Mod-WG to identify key missing processes and update the code to address knowledge gaps as they are filled (All Qs: 2025). | Task 3.7 | bar: 2025 Q1 to 2025 Q4
3-8. Provide estuarine models, analysis tools, and initial scoping scenarios, final code version and other materials to CBPO for testing (Q3-Q4: 2025). | Task 3.8 | bar: 2025 Q3 to 2025 Q4
3-9. Finalize work to improve shallow water dynamics in MBM (Q1-Q2: 2025). | Task 3.9 | bar: 2025 Q1 to 2025 Q2
3-10. Finalize work to improve shallow water dynamics in MTMs (Q1-Q2: 2025). | Task 3.10 | bar: 2025 Q1 to 2025 Q2
3-11. Finalize work on basic living resource linkages of refined chlorophyll, wetland, and SAV simulation and potential linkage to higher trophic levels (All Qs: 2025). | Task 3.11 | bar: 2025 Q1 to 2025 Q4
3-12. Finalize work using MBM and MTMs to better resolve CBP problem segments (Q1-Q2: 2025). | Task 3.12 | bar: 2025 Q1 to 2025 Q2
3-13. Finalize work examining CC influence on SAV, shallow water, and phenology of CC watershed loads and tidal Bay processing (Q1-Q2: 2025). | Task 3.13 | bar: 2025 Q1 to 2025 Q2
Task 4. MBM and MTM Review (2006) and Application (2007) | Task 4 | bar: 2026 Q1 to 2027 Q4
4-1. Provide final estuarine models, analysis tools, model documentation and other materials to CBPO (Q1:2026). | Task 4.1 | bar: 2026 Q1
4-2. Improve the CBP management decisions through the successful application of developing quantitative assessments of climate change in the Chesapeake main-Bay and in ultra-local tidal waters, as directed by CBP managers with detailed estimates for how to respond to 2035 climate change challenge (All Qs: 2027). | Task 4.2 | bar: 2027 Q1 to 2027 Q4
4-3. Provide initial (2026) and final (2027) scoping scenarios, analyses, and other materials to support Chesapeake protection and restoration efforts and address the needs and requirements of CBP decision makers and managers for responding to climate change in the Chesapeake (All Qs: 2026 & 2027). | Task 4.3 | bar: 2026 Q1 to 2027 Q4
4-4. Develop user-friendly interfaces with model software and technical transfer training so that a variety of stakeholders can have full access and know how to use to pre- and post-processing, visualization, and scenario tools (All Qs: 2026). | Task 4.4 | bar: 2026 Q1 to 2026 Q4
4-5. Develop and apply 2035 CC and all other management MBM and MTM scenarios as determined by CBP decision makers (Q3, Q4: 2026 & all Qs; 2027). | Task 4.5 | bar: 2026 Q1 to 2027 Q4
4-6. Document the findings and recommendations in the final report (All Qs 2026). | Task 4.6 | bar: 2026 Q1 to 2026 Q4
4-7. Provide final TMDL scenario simulation results to address the needs and requirements of CBP decision makers and managers for responding to climate change in the Chesapeake, tributaries, and in ultra-local areas as requested. (Q3, Q4: 2027). | Task 4.7 | bar: 2027 Q3 to 2027 Q4
Task 5. Continuous Activities | Task 5
5-1. Support the Modeling Workgroup, WQGIT, and other technical and management/policy CBP groups as needed (All Qs: 2022-2027). | Task 5.1
5-2. Host a dedicated web site for the new Main Bay Model (MBM) (All Qs: 2022 2027 with final deliverable Q3 2027). | Task 5.2
5-3. Submit annual reports with detailed documentation on model structure, major code changes, validation, and calibration procedure and usage (Q4 each year: 2022-2027). | Task 5.3 | bar: 2022 Q4; 2023 Q4; 2024 Q4; 2025 Q4; 2026 Q4; 2027 Q4
5-4. Disseminate research findings & experiences via 1-2 journal papers/year (All Qs: 2022-2027). | Task 5.4
5-5. Coordination/collaboration meetings among MBM and MTM Teams (All Qs: 2023-2027 coincident with CBP Modeling Quarterlies). | Task 5.5
Task 1. Initial MBM-MTM Development (2022 – 2023)
1-1. Kick-off MBM meeting with follow-up CBPO Quarterly meetings to decide tasks to be completed, priority model activities and improvements, and finalize the schedule for progress reporting (Q1-Q2: 2022).
1-2. Integrate the latest ICM changes into MBM (Q1-Q2: 2022).
1-3. Revise the current MBM mesh to achieve best scale and performance tradeoffs (Q1-Q2: 2022).
1-4. Revise MBM mesh to account for channels in MBM and MTMs (Q1-Q2: 2022).
1-5. Performance tuning of MBM to achieve 1991-2000 simulation in one day (Q1-Q3: 2022).
1-6. Work with watershed, airshed, hydrological modeling groups to ensure the coupling, scale, and the interface mechanisms are properly executed, including climate change (CC) input information (All Qs: 2022-2023).
1-7. Develop boundaries of MBM, WSM, and tidal wetlands (Q1: 2022).
1-8. Quantify how boundaries of MBM, WSM, and tidal wetlands will change with SLR (Q2: 2022).
1-9. Develop SAV simulation approach of explicit beds or bounded seed in every mesh (All Qs: 2022-2023).
1-10. Establish MBM-MTM boundary interfaces for all MTMs (All Qs:2022).
1-11. Develop MTM grids in anticipation of MTM teams (All Qs: 2022).
1-12. CBP decision makers to finalize 5 MTMs (Q2-Q3: 2022).
1-13. Link with initial P7 WSM hydrology (4Q: 2022, Q1:2023).
1-14. Link with initial P7 WSM sediment load estimates (1Q-Q2: 2023).
1-15. Link with initial P7 WSM nutrient load estimates (Q3-Q4: 2023).
1-16. Expand temporal domain of MBM to focus on 1991-200, 1993-1995, recent years for good calibration data, and the full 1985-present for coastal eutrophication research (All Qs: 2022-2023).
1-17. Initial work to improve shallow water dynamics in MBM (All Qs: 2022-2023).
1-18. Initial work to improve shallow water dynamics in MTMs (All Qs: 2023).
1-18. Initial work on basic living resource linkages of refined chlorophyll, wetlands, & SAV for MBM & MTM (All Qs: 2022).
1-19. Initial work on potential linkage to higher trophic levels MBM & MTMs (All Qs: 2023).
1-20. Initial work of using MBM and MTMs to better resolve CBP problem segments (All Qs: 2023).
1-21. Initial work on examining CC influence on SAV, shallow water, and phenology of CC watershed loads and tidal Bay processing MBM & MTM (All Qs: 2023).
Task 2 Interim MBM and MTM Development (2023 – 2024)
2-1. Initiate MTM activities (Q1-Q2: 2023).
2-2. Kick-off joint meetings of MBM and MTM Teams with Mod WG (Q1-Q2: 2023)
2-3. Conduct full initial calibration and verification of hydrodynamic and WQ model output (Q3-Q4:2024).
2-4. Address important knowledge gaps in ICM (All Qs: 2024).
2-5. Begin completion of work to improve shallow water dynamics in MBM (All Qs: 2024).
2-6. Begin completion of work to improve shallow water dynamics in MTMs (All Qs: 2024).
2-7. Begin completion of work on basic living resource linkages of refined chlorophyll, wetland, and SAV simulation and potential linkage to higher trophic levels (All Qs: 2024).
2-8. Begin completion of work using MBM and MTMs to better resolve CBP problem segments (All Qs: 2024).
2-9. Begin completion of work examining CC influence on SAV, shallow water, and phenology of CC watershed loads and tidal Bay processing (All Qs: 2024).
2-10. Improve nutrient speciation simulation by better tracking the watershed to tidal Bay and the tidal water to sediment exchanges of the different nutrient species (Q3-Q4: 2023 & Q1-Q2: 2024).
Task 3 Final MBM and MTM Development (2005)
3-1. Provide a fully operational MBM that meets the needs of CBP (Q2-Q3: 2025).
3-2. Finish documentation on the software package in a report that will include detailed documentation on model structure, major code changes, validation and calibration procedure and usage (Q4: 2025).
3-3. Demonstrate feasibility and utility of using a state of the science UG model to better estimate Chesapeake WQ standards in shallow open waters under 2035 and future climate change conditions (All Qs: 2025).
3-4. Transfer the software package to CBPO for operational testing, and work with CBPO personnel to test the model package under operational settings and resolve any issues that may arise (Q3-Q4: 2025).
3-5. All MBM and MTMs fully operational (Q4: 2025).
3-6. Conduct full review of al MBM and MTMs with CBP technical and management groups and with STAC (All Qs: 2026).
3-7. Review all recent studies related to Bay WQ processes and work with CBP and Mod-WG to identify key missing processes and update the code to address knowledge gaps as they are filled (All Qs: 2025).
3-8. Provide estuarine models, analysis tools, and initial scoping scenarios, final code version and other materials to CBPO for testing (Q3-Q4: 2025).
3-9. Finalize work to improve shallow water dynamics in MBM (Q1-Q2: 2025).
3-10. Finalize work to improve shallow water dynamics in MTMs (Q1-Q2: 2025).
3-11. Finalize work on basic living resource linkages of refined chlorophyll, wetland, and SAV simulation and potential linkage to higher trophic levels (All Qs: 2025).
3-12. Finalize work using MBM and MTMs to better resolve CBP problem segments (Q1-Q2: 2025).
3-13. Finalize work examining CC influence on SAV, shallow water, and phenology of CC watershed loads and tidal Bay processing (Q1-Q2: 2025).
Task 4. MBM and MTM Review (2006) and Application (2007)
4-1. Provide final estuarine models, analysis tools, model documentation and other materials to CBPO (Q1:2026).
4-2. Improve the CBP management decisions through the successful application of developing quantitative assessments of climate change in the Chesapeake main-Bay and in ultra-local tidal waters, as directed by CBP managers with detailed estimates for how to respond to 2035 climate change challenge (All Qs: 2027).
4-3. Provide initial (2026) and final (2027) scoping scenarios, analyses, and other materials to support Chesapeake protection and restoration efforts and address the needs and requirements of CBP decision makers and managers for responding to climate change in the Chesapeake (All Qs: 2026 & 2027).
4-4. Develop user-friendly interfaces with model software and technical transfer training so that a variety of stakeholders can have full access and know how to use to pre- and post-processing, visualization, and scenario tools (All Qs: 2026).
4-5. Develop and apply 2035 CC and all other management MBM and MTM scenarios as determined by CBP decision makers (Q3, Q4: 2026 & all Qs; 2027).
4-6. Document the findings and recommendations in the final report (Yr 6: 2027).
4-7. Provide final TMDL scenario simulation results to address the needs and requirements of CBP decision makers and managers for responding to climate change in the Chesapeake, tributaries, and in ultra-local areas as requested. (Q3, Q4: 2027).
Task 5. Continuous Activities
5-1. Support the Modeling Workgroup, WQGIT, and other technical and management/policy CBP groups as needed (All Qs: 2022-2027).
5-2. Host a dedicated web site for the new Main Bay Model (MBM) (All Qs: 2022 2027 with final deliverable Q3 2027).
5-3. Submit annual reports with detailed documentation on model structure, major code changes, validation, and calibration procedure and usage (Q4 each year: 2022-2027).
5-4. Disseminate research findings & experiences via 1-2 journal papers/year (All Qs: 2022-2027).
5-5. Coordination/collaboration meetings among MBM and MTM Teams (All Qs: 2023-2027 coincident with CBP Modeling Quarterlies).

## Interum MBM-MTM Development
Main Bay Model (MBM) Tasks and Timelines
January 2, 2022
Calendar Year |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027
Calendar Quarter |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Project Year |  | 2022 Q1: Year 1; 2023 Q1: Year 2; 2024 Q1: Year 3; 2025 Q1: Year 4; 2026 Q1: Year 5; 2027 Q1: Year 6
Task 2 Interim MBM and MTM Development (2023 – 2024) | Task 2 | bar: 2024 Q1 to 2025 Q4
2-1. Initiate MTM activities (Q1-Q2: 2023). | Task 2.1 | bar: 2022 Q1 to 2022 Q2; 2024 Q2 to 2024 Q3
2-2. Kick-off joint meetings of MBM and MTM Teams with Mod WG (Q1-Q2: 2023) | Task 2.2 | bar: 2022 Q1 to 2022 Q2; 2024 Q1 to 2024 Q2
2-3. Conduct full initial calibration and verification of hydrodynamic and WQ model output (Q3-Q4: 2024). | Task 2.3 | bar: 2022 Q1 to 2022 Q3; 2025 Q3 to 2025 Q4
2-4. Address important knowledge gaps in ICM (All Qs: 2024). | Task 2.4 | bar: 2022 Q1 to 2022 Q2; 2024 Q1 to 2025 Q4
2-5. Begin completion of work to improve shallow water dynamics in MBM (All Qs: 2024). | Task 2.5 | bar: 2022 Q1 to 2022 Q3; 2024 Q3 to 2025 Q4
2-6. Begin completion of work to improve shallow water dynamics in MTMs (All Qs: 2024). | Task 2.6 | bar: 2022 Q1 to 2023 Q4; 2024 Q3 to 2025 Q4
2-7. Completion of work on basic living resource linkages of refined chlorophyll, wetland, and SAV simulation and potential linkage to higher trophic levels (All Qs: 2024). | Task 2.7 | bar: 2022 Q1; 2024 Q4 to 2025 Q4
2-8. Completion of work using MBM and MTMs to better resolve CBP problem segments (All Qs: 2024). | Task 2.8 | bar: 2022 Q2; 2025 Q1 to 2025 Q4
2-9. Completion of work examining CC influence on SAV, shallow water, & phenology of CC watershed loads and tidal Bay processing (All Qs: 2024). | Task 2.9 | bar: 2023 Q1 to 2023 Q4; 2025 Q1 to 2025 Q4
Task 2 Interim MBM and MTM Development (2023 – 2024)
2-1. Initiate MTM activities (Q1-Q2: 2023).
2-2. Kick-off joint meetings of MBM and MTM Teams with Mod WG (Q1-Q2: 2023)
2-3. Conduct full initial calibration and verification of hydrodynamic and WQ model output (Q3-Q4:2024).
2-4. Address important knowledge gaps in ICM (All Qs: 2024).
2-5. Begin completion of work to improve shallow water dynamics in MBM (All Qs: 2024).
2-6. Begin completion of work to improve shallow water dynamics in MTMs (All Qs: 2024).
2-7. Begin completion of work on basic living resource linkages of refined chlorophyll, wetland, and SAV simulation and potential linkage to higher trophic levels (All Qs: 2024).
2-8. Begin completion of work using MBM and MTMs to better resolve CBP problem segments (All Qs: 2024).
2-9. Begin completion of work examining CC influence on SAV, shallow water, and phenology of CC watershed loads and tidal Bay processing (All Qs: 2024).