## MPA Critical Path Forward
MPA Priority | Partnership Lead(s) | Major Deliverable(s) | Start & End Dates | Factors/Information Affecting Priority | Action/Decision for Workgroup | Action/Decision for WQGIT | Action/Decision for MB, PSC, and EPA
Timeline for establishing EPA's expectations for Phase III WIPs | EPA with input from Partnership | Refine decision-support tools, as appropriate, to enhance the evaluation of progress and crediting of actions on the ground | Start: October 2012 / End: October 2015 | Ongoing and formalized as priority since Oct 2012; From March 2015, all major Partnership decisions are made on changes to scenario builder processing and data. Scenario Builder final modifications begin. | All decisions in data inputs finalized prior to Oct 20, 2015 | All decisions in data inputs finalized prior to Oct 20, 2015
|  | EPA presents preliminary expectations and seeks initial input from Partnership on expectations for Phase III WIPs | Start: October 2013 / End: October 2016 | EPA solicits initial feedback from jurisdictions starting in October 2013; solicits feedback from Partnership. | Summer 2016 | Fall/October 2016 | EPA initiates discussions about Phase III WIP expectations with the jurisdctions in December 2013; present initial expectations to the MB in December 2016 and to the PSC in Feb/March 2017.
|  | EPA presents updated expectations and seeks input from Partnership on expectations for Phase III WIPs | Start: October 2013 / End: October 2016 | Test any refinements and, to the extent possible, assess model certainty and scope for using modeling tools within the WIP and milestone process. |  | March/April 2017 | EPA briefs the MB in March/April 2017 and the PSC in May 2017 on updated Phase III WIP expectations.
|  | Based on input from the Partnership, EPA provides expectations for scope and content of Phase III WIPs | Start: October 2013 / End: October 2016 | Review feedback from Partnership and modeling results that might impact the establishment of local area targets |  |  | EPA sends letter to PSC on final expectations for Phase III WIPs.
|  | Make any final modifications in response to Step 7 testing and set Phase III WIP planning targets | Continuous, estimated completion by December 2017 | All Phase 6 models are final. The Partnership decision making process begins in Dec 2016 to discuss how these models will be used in Phase III WIP process. | Input solicited early 2016 | Input solicited early 2016 | Based on feedback from the Partnership, EPA sets and releases Phase III WIP Planning Targets in December 2017
|  | Develop 2018-2019 Milestones | Evaluation begins January 2018 through March 2018 | Milestones will be developed and evaluated on Phase 6 modeling tools; December 2017 - milestones due from jurisdictions |  |  | EPA evaluation of milestones complete in early 2018
|  | Develop draft and final Phase III WIPs based on criteria for scope and content that may vary across jurisdictions due to implementation progress | Timeline is set by jurisdiction for the development of the Phase III WIPs | WIPs based on new modeling information, implementation progress to date, and possible local area targets |  |  | Jurisdictions submit draft PhIII WIPs by June 2018 and final PhIII WIPs by December 2018
|  | Evaluate progress through 2017 and attainment of the “60% by 2017” goal | Start: December 2017 / End: March 2018 | Jurisdictions submit progress in December 2017; CBPO/EPA uses Phase 5.3.2 modeling tools to evaluate progress across the jurisdiction as a whole. |  |  | EPA finalizes evaluations by March 2018; EPA presents evaluations to MB and PSC in Spring 2018
Develop new LULC categories and associated loading rates | Land Use Workgroup | Explore backcasting & forecasting options for 2025 | Start: June 2013 / End: September 2014 | For potential use in the Phase III WIPs | Approve use of 2025 projections for Phase III WIPs; Fall 2014 | Approve use of 2025 projections for Phase III WIPs; Winter 2014/Spring 2015 | Brief MB on projections for Phase III WIPs; Spring 2014
|  | Assign unique loading rates to potential new LULC classes | Start: November 2013 / End: January 2015 | Coordinate closely with Watershed Technical and Sector Workgroups and convene expert panels as needed. Informs final set of LULC classes to be used in the Phase 6 suite of models | Approve loading rates - October 2014 | Approve loading rates - January 2015
|  | Review results of applying new data/methods to CBP models and compare with local models | Start: August 2014 / End: November 2014 | Will need to backcast land use over calibration period for the Watershed Model and forecasting land use to 2017. | Review Results: December 2014
|  | Finalize land use dataset and submit to WQGIT for approval | Start: January 2015 / End: August 2015 | Dataset needs to be approved and incorporated into WSM by Oct 20, 2015. | Dataset for LUWG review Summer 2015 | Approve land use dataset; August 2015 | Brief MB on new land use datasets; Fall 2015