## Sheet1
Midpoint Assessment Deliverable | PSC-Approved Schedule | Notes
Release of Draft Phase III WIP Planning Targets | 2017-12-22 | 7-week difference
Partnership’s Review of Phase III WIP Planning Targets | December 22, 2017 – May 11, 2018 | WQGIT requested at least 4 months to review draft planning targets – WQGIT-approved (March 13, 2017).
EPA releases final Phase III WIP expectations document | Early January 2018 | Reflects final policy decisions from the October and December PSC meeting on Conowingo, climate change, and accounting for growth
Jurisdictions submit 2018-2019 milestones and final 2016-2017 milestones report | 2018-01-15 | No changes are recommended at this time. Jurisdictions are encouraged to solicit input from their local partners on milestone commitments in the September – October timeframe
Jurisdictions have opportunity to update milestone commitments based on EPA feedback and 2017 Progress results | January 15, 2018 – March 2018
Any proposed changes to the draft Phase III WIP Planning Targets including special case requests due to the Chesapeake Bay Program Office | 2018-04-20 | Identification of changes and special case requests will occur on a rolling basis throughout the 4-month review period. Final requests and changes should be submitted to the CBPO by no later than April 20, 2018
PSC Meeting - Approval of final Phase III WIP Planning Targets with special cases | mid May 2018 | Allows for the 4-month review of the draft Phase III WIP planning targets.
Release of Final Phase III WIP Planning Targets | 2018-05-25 | Jurisdictions are encouraged to engage their local partners in the development of local planning goals, if not before
EPA completes assessment of “60% by 2017 goal” using the Phase 5.3.2 suite of modeling tools | March/April 2018 | Jurisdictions’ progress data due December 1, 2017
Jurisdictions work with local partners to develop local planning goals | Throughout 2018 | Timing may vary across the jurisdictions
Draft Phase III WIPs posted on jurisdictions’ websites for partner and public stakeholder review | 2019-03-01 | Still maintains 9 months between final Phase III WIP planning targets and deadline for draft Phase III WIPs
Partners and public stakeholders’ feedback on draft Phase III WIPs due to jurisdictions | 2019-04-26 | Still allows for a 2-month Partnership review of draft Phase III WIPs
Final Phase III WIPs posted on jurisdictions’ websites | 2019-06-28 | Still follows Partnership recommendation to allow one year between when final Phase III WIP planning targets are released and when final Phase III WIPs are complete