## Slide 1
CBP Biennial Strategy Review System
Meetings Details (DRAFT) October 12, 2016 (DRAFT)

## Slide 2
The Timeline
Date | Action
August 2, 2016 | Present draft options to GIT 6. Solicit input for revisions.
August 30, 2016 | Present revised draft options to GIT Chairs. Present during GIT Chairs meeting, have Chairs review and comment.
September 6, 2016 | GIT 6 members review comments from GIT Chairs and modify options as needed.
September 14, 2016 | STAC members review and comment.
September 15, 2016 | Present revised draft options to the Management Board for review and discussion.
October 18, 2016 | Revise and edit the draft Strategy Review System to incorporate Management Board suggestions at full-day GIT6 meeting.
November 1, 2016 | GIT 6 continues development of strategy review system at monthly meeting.
December 6, 2016 | GIT 6 continues development of strategy review system at monthly meeting.
November 17, 2016 | Present recommended draft to the Management Board, as time permits.
December 2016 | Present final draft of Strategy Review System to Management Board for approval and implementation.

## Slide 3
Biennial Strategy Review Meetings
2-Day Biennial Review
EC
PSC
Biennial Review Meeting – High-level retrospective program-wide review to celebrate our successes and identify important stories. Discuss developments in environmental (monitoring, science) and economic (available resources) conditions, and results of program evaluations (e.g., Independent Evaluator). Identify science needs and future focus for GIT Progress meetings, and summarize recommendations to be reported to the PSC.
Principals’ Staff Committee – Provide input on any significant shifts in strategy and approval of changes, with public input, resulting from the Biennial Review to prepare for PSC report on implementation progress to the Executive Council.
Executive Council – Concurrence and partner commitment to significant strategy shifts and discussion and approval of changes, if necessary.
Goal Implementation Teams Progress Sessions – Review management strategy and work plan progress highlighting successes, challenges and obstacles. Provide rationale for any planned shifts in strategies and workplans. Receive input and problem solving support from Management Board, including Advisory Committee chairs.
Interim Management Board Meetings – As needed, follow-up on issues identified in GIT Progress Sessions, new issues related to challenges or strategy shifts, other business.
GIT Progress MB Sessions
Time-sensitive Topics

## Slide 4
Quarterly GIT Progress Meeting*
Who: Management Board, GIT Chairs, subject matter experts
GIT Progress Sessions
*Time-sensitive Topics
Objectives | Outputs
*Time-sensitive Topics: Discussion of time-sensitive or ongoing MB business on an as-needed basis. | Timely input and action on needed business.
Highlight GIT successes, identify challenges and delays, and support issue resolution Focus on cross-GIT collaboration and discuss opportunities for multi-outcome benefit Review resource needs and options to address deficits Prospective work planning: identify needed changes | Decisions on needed adaptations to Strategies and Work Plans Better understanding of work efforts related to GIT outcomes Identify opportunities for collaborative work Resolution of policy or programmatic concerns
Example Guiding Questions for Progress Portion on Agenda Has completed work produced expected results? How have changing conditions impacted your ability to meet your work plan commitments or impacted your strategy? What have we learned? Does it necessitate any changes to work plan and/or management strategy approaches? Are adequate resources available to complete GIT work plans? | 
*To be updated after November 1 GIT6 meeting with revised Objectives, Inputs, Outputs, and Guiding Questions (from “SRS Meeting Descriptions” document)

## Slide 5
Interim Management Board Meetings
Who: GIT Chairs, STAR, Management Board, Advisory Committees
Monthly Meetings
*
Objectives | Outputs
*Time-sensitive Topics: Discussion of time-sensitive GIT issues or challenges related to strategy or work plan on an as-needed basis. | Input and decisions into time-sensitive strategy or work plan shifts.
Discuss cross-program topics, e.g., monitoring, resources, stakeholder topics, governance, etc. Provide opportunity for MB input and guidance Showcase innovations and best practices Follow-up on issues and actions from previous meetings, as needed. | Resolution of policy or programmatic concerns Information exchange.
Example Guiding Questions for Time-sensitive Portion of the Agenda What is the strategy or work plan challenge or issue? How have you tried to solve this issue? What are the options and your recommended solution? | 

## Slide 6
Biennial Review Meetings*
Who: GITs, STAR, Management Board, Advisory Committees
2-Day Biennial Review
Objectives | Outputs
High-level retrospective program-wide review to celebrate our successes. Discuss developments in environmental and economic conditions. Discuss results of program evaluations. Build on Progress meetings to identify collaborative gains and cross-program needs. Provide PSC with information needed to complete strategy implementation report to EC. | Important *success* stories and *lessons learned* to share with others. Focus for GIT Progress Meetings based on understanding changing conditions. Emerging science needs to be factored into prospective work planning at GIT Progress meetings. Information to be provided to the PSC for use in reporting to the EC. Shared actions to address roadblocks.
Guiding Questions Have program evaluations identified needed changes? What opportunities exist to improve collaborative work? Do changing conditions warrant GIT re-evaluation of strategy and work plans? | 
*To be updated after November 1 GIT6 meeting with revised Objectives, Inputs, Outputs, and Guiding Questions (from “SRS Meeting Descriptions” document)

## Slide 7
Principals Staff Committee Meetings
Who: PSC, GIT Chairs, Management Board reps, Advisory Committees
PSC
Objectives | Outputs
Discuss developments in environmental and economic conditions. Discuss results of program evaluations. Discuss policy related impacts and options. Review of high-level retrospective program-wide progress to celebrate our successes and support completion of strategy implementation report to EC. | Understanding of how developments in environmental and economic conditions impact strategy implementation Understanding of emerging science needs Support for any needed revised policies Preparation for EC meeting.
Guiding Questions Have program evaluations identified needed changes? What opportunities exist to improve collaborative work? | 

## Slide 8
Executive Council Meetings
Who: EC, PSC, MB Chair, GIT Chairs, Advisory Committees
EC
Objectives | Outputs
High-level retrospective program-wide review to celebrate our successes Discuss new directions in strategy, if needed Discuss additional revisions, if needed Received Advisory Committee reports and recommendations. | Important *success* stories and *lessons learned* to share with others Direction for the program for the coming year.
Guiding Questions Have program evaluations identified needed programmatic or policy changes? What opportunities exist to improve collaborative work across our jurisdictions? Do changing conditions warrant re-evaluation of goals? | 

## Slide 9
Decision Governance Model

## Slide 10
Management Board recommends to PSC whether changes, additions, deletions are needed (p. 3).
PSC recommends, Executive Council decision (p. 3).
Make correction.
No elevation necessary.
        Are there corrections to the MS that will improve achievement of the outcome?
GIT proposes changes.
          Are modifications to the Goal necessary?
No
Yes
Yes
No
Are the Workplan actions being completed as expected?
Can barriers be removed by GIT or Workgroup action?
Elevation to Management
Board necessary. 3, 4
      Seeing expected outcome/indicator/
      measure improvement?
Yes
No elevation necessary. 2
No 1
Yes
No
Yes
No
PSC moves forward with modification of outcome, with public input. Modification published on web (p 3).
          Are modifications to the Outcome necessary?
Yes
No
        1 Review Management Strategy (p. 15) assumptions, factors, and approaches to determine if changes need to be made to Management Strategy approaches, factors influencing, monitoring, etc.
        2 Workplan updated with next biennial actions; signatories update participation (p. 3).
        3 Either at Biennial Review or at “special emphasis” slot in regular Management Board meeting (depending on urgency and critical path).
4 Management Board Action: identify other GITs/Workgroups/Advisory Committees that would help resolve barrier(s), identify action(s) a signatory can take, elevate to PSC, etc.
= GIT decision; MB informed
= MB decision; PSC informed
= PSC decision; EC informed
= EC decision