## Table 1
Biennial Strategy Review System: Logic Table and Work Plan
Instructions: The following Logic Table should be used to articulate, document, and examine the reasoning behind your work toward an Outcome. Your reasoning—or logic—should be based on the Partnership’s adaptive management decision framework. This table allows you to indicate the status of your management actions and denote which actions have or will play the biggest role in making progress.
Some Management Strategies and Work Plans will not immediately or easily fit into this analytical format. However, all GITs should complete columns one through four to bring consistency to and heighten the utility of these guiding documents. The remaining columns are recommended for those who are able to complete them. If you have any questions as you are completing this table, please contact SRS Team Coordinator Laura Free (free.laura@epa.gov).
The instructions below should be used to complete the table. An example table is available on the GIT 6 webpage under “Projects and Resources”.
1. For the first round of strategic review (2017-2018): Use your existing Work Plan actions to complete the Work Plan Actions section first. Make sure to number each of the actions under a high-level Management Approach, as these numbers will provide a link between the work plan and the logic table above it. Use color to indicate the status of your actions: a green row indicates an action has been completed or is moving forward as planned; a yellow row indicates an action has encountered minor obstacles; and a red row indicates an action has not been taken or has encountered a serious barrier. 2. Required: In the column labeled Factor, list the significant factors (both positive and negative) that will or could affect your progress toward an Outcome. The most effective method to ensure logic flow is to list all your factors and then complete each row for each factor. Consult our Guide to Influencing Factors (Appendix B of the Quarterly Progress Meeting Guide on the GIT 6 webpage under “Projects and Resources”) to ensure your list is reasonably comprehensive and has considered human and natural systems. Include any factors that were not mentioned in your original Management Strategy or Work Plan but should be addressed in any revised course of action. If an unmanageable factor significantly impacts your outcome (e.g., climate change), you might choose to list it here and describe how you are tracking (but not managing) that factor. 3. Required: In the column labeled Current Efforts, use keywords to describe existing programs or current efforts that other organizations are taking that happen to support your work to manage an influencing factor but would take place even without the influence or coordination of the Chesapeake Bay Program. You may also include current efforts by the Chesapeake Bay Program. Many of these current efforts may already be identified in your Management Strategy; you may choose to link the keywords used in this table to your Management Strategy document for additional context. You may also choose to include some of these efforts as actions in your work plan; if you do, please include the action’s number and hyperlink. 4. Required: In the column labeled Gap, list any existing gap(s) left by those programs that may already be in place to address an influencing factor. These gaps should help determine the actions that should be taken by the Chesapeake Bay Program through the collective efforts of Goal Implementation Teams, Workgroups, and internal support teams like STAR, or the actions that should be taken by individual partners to support our collective work (e.g., a presentation of scientific findings by a federal agency to a Chesapeake Bay Program workgroup). These gaps may already be listed in your Management Strategy. 5. Required: In the column labeled Actions, list the number that corresponds to the action(s) you are taking to fill identified gaps in managing influencing factors. Include on a separate line those approaches and/or actions that may not be linked to an influencing factor. To help identify the action number, you may also include a few key words. Emphasize critical actions in bold. 6. Optional: In the column labeled Metric, describe any metric(s) or observation(s) that will be used to determine whether your management actions have achieved the intended result. 7. Optional: In the column labeled Expected Response and Application, briefly describe the expected effects and future application of your management actions. Include the timing and magnitude of any expected changes, whether these changes have occurred, and how these changes will influence your next steps 8. Optional: In the column labeled Learn/Adapt, describe what you learned from taking an action and how this lesson will impact your work plan or Management Strategy going forward.
Toxics Policy and Prevention Logic Table and Work Plan
Primary Users: Goal Implementation Teams, Workgroups, and Management Board ¦ Secondary Audience: Interested Internal or External Parties Primary Purpose: To assist partners in thinking through the relationships between their actions and specific factors, existing programs and gaps (either new or identified in their Management Strategies) and to help workgroups and Goal Implementation Teams prepare to present significant findings related to these actions and/or factors, existing programs and gaps to the Management Board. ¦ Secondary Purpose: To enable those who are not familiar with a workgroup to understand and trace the logic driving its actions. Reminder: As you complete the table below, keep in mind that removing actions, adapting actions, or adding new actions may require you to adjust the high-level Management Approaches outlined in your Management Strategy (to ensure these approaches continue to represent the collection of actions below them). Long-term Target: Continually improve practices and controls that reduce and prevent the effects of toxic contaminants below levels that harm aquatic systems and humans. Build on existing programs to reduce the amount and effects of PCBs in the Bay and watershed. Use research findings to evaluate the implementation of additional policies, programs and practices for other contaminants that need to be further reduced or eliminated. Two-year Target: Completion of performance targets related to key actions
KEY: Use the following colors to indicate whether a Metric and Expected Response have been identified.
Metric |  | Specific metrics have not been identified
Metrics have been identified
Expected Response |  | No timeline for progress for this action has been specified
Timeline has been specified
Factor |  |  | Current Efforts |  | Gap |  |  | Actions (critical in bold) |  |  | Metrics | Expected Response and Application | Learn/Adapt
What is impacting our ability |  |  | What current efforts are |  | What further efforts or |  |  | What actions are |  |  | Optional: Do | Optional: What | Optional: What did
to achieve our outcome? |  |  | addressing this factor? |  | information are needed |  |  | essential to achieve |  |  | we have a | effects do we expect | we learn from taking
[5 empty] | to fully address this |  |  | our outcome? |  |  | measure of | to see as a result of | this action? How will
[5 empty] | factor? | [5 empty] | progress? | this action, when, | this lesson impact
[11 empty] | How do we | and what is the | our work?
[11 empty] | know if we | anticipated
[11 empty] | have achieved | application of these
[11 empty] | the intended | changes?
result?
Broad geographic extent and |  |  | PCB Story Map and tidal |  | Continued jurisdictional |  |  | Build on
distribution of PCBs |  |  | impairments indicator |  | monitoring programs |  |  | jurisdictional
|  |  | map to communicate |  | for PCBs, including fish |  |  | monitoring programs
|  |  | extent of PCB |  | tissue sampling. |  |  | to coordinate
|  |  | impairments. |  |  |  |  | watershed-wide
monitoring and
tracking of PCB
impairments.
Political will to modify |  |  | Progress in |  | Ongoing GIT funded |  |  | PCB Consortium to
regulatory programs and/or |  |  | implementation of local |  | project to study |  |  | support progress on
create voluntary programs |  |  | TMDLs, some progress on |  | feasibility of voluntary |  |  | regulatory and
|  |  | multi-state TMDL |  | PCB removal program(s) |  |  | voluntary programs
|  |  | development |  |  |  |  | in multiple
jurisdictions
High cost of remedies: in- |  |  | Ongoing academic |  | Complete and release |  |  | PCB Consortium to
stream sediment |  |  | studies; WWTP PCB |  | PCB trackdown study |  |  | share information in
remediation; waste water |  |  | removal GIT funded study |  | and PMP guide. |  |  | order to reduce high
PCB source trackdown | [7 empty] | cost of management
studies; electrical equipment | [7 empty] | approaches, and
replacements; stormwater | [7 empty] | consider more
controls; contaminated site | [7 empty] | approaches to
remediation | [7 empty] | prevent release of
PCBs
Variety of sources and |  |  | Reports from CSN to |  | Further information |  |  | PCB consortium to
pathways for PCBs entering |  |  | better understand variety |  | needed on extent of |  |  | share lessons
the environment that |  |  | of sources and pathways |  | atmospheric deposition |  |  | learned on
necessitate a wide-range of |  |  | for toxic contaminants, |  | of PCBs in the Bay |  |  | management
very different management |  |  | including PCBs; |  | Watershed; better |  |  | approaches and best
responses (e.g., primary |  |  | Development of fact |  | understand PCB |  |  | practices to
Factor |  |  | Current Efforts |  | Gap |  |  | Actions (critical in bold) |  |  | Metrics | Expected Response and Application | Learn/Adapt
What is impacting our ability |  |  | What current efforts are |  | What further efforts or |  |  | What actions are |  |  | Optional: Do | Optional: What | Optional: What did
to achieve our outcome? |  |  | addressing this factor? |  | information are needed |  |  | essential to achieve |  |  | we have a | effects do we expect | we learn from taking
[5 empty] | to fully address this |  |  | our outcome? |  |  | measure of | to see as a result of | this action? How will
[5 empty] | factor? | [5 empty] | progress? | this action, when, | this lesson impact
[11 empty] | How do we | and what is the | our work?
[11 empty] | know if we | anticipated
[11 empty] | have achieved | application of these
[11 empty] | the intended | changes?
result?
sources such as electrical |  |  | sheet to communicate |  | removal rates and |  |  | implement PCB
equipment, secondary |  |  | multiple benefits of |  | efficiencies through |  |  | reductions through
sources such as wastewater |  |  | nutrient and sediment |  | nonpoint source |  |  | TMDLs, MS4 permits,
treatment by-products, and |  |  | management practices |  | management practices |  |  | and NPDES permits.
pathways such as |  |  | for toxic contaminants |  | for nutrient and
stormwater runoff |  |  |  |  | sediment reduction.
contaminated by air
deposition or contaminated
sites)
Need to shift paradigm to |  |  | No current efforts |  | Track potential new |  |  | Develop approaches
acknowledge that there are |  |  |  |  | sources of PCB |  |  | for understanding all
ongoing sources of PCBs (i.e., |  |  |  |  | production, for example |  |  | sources of PCBs in
PCBs are not static “legacy” |  |  |  |  | ink and dye |  |  | the watershed.
contaminants) |  |  |  |  | manufacturing
industries.
Knowledge gaps on relative |  |  | No current efforts |  | Large scale synthesis |  |  | PCB consortium
sizes of PCB sources |  |  |  |  | and mass balance |  |  | could address this
[5 empty] | analysis of PCB sources |  |  | knowledge gap (with
[5 empty] | in the watershed |  |  | resources, e.g GIT
funding)
WORK PLAN ACTIONS | [13 empty] | 2020 SRS REVIEW: STATUS OF WORKPLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
Management Approach 1: Regulatory Approaches | [13 empty] | Management Approach 1: Regulatory Approaches
|  |  |  | 1.1.1 Continue statewide |  |  | PA DEP |  |  | 149 samples collected in 2019. Not all are in the Susquehanna drainage (i.e. Chesapeake Bay drainage). Lab analysis to be conducted when PA DEP lab re-opens. |  |  |  | Samples to be analyzed at PA DEP lab once it re-opens. | Ongoing with activities planned. Approximately 100 sites are planned to be sampled for fish tissue statewide in PA in 2020.
fish tissue sampling for
PCBs in at least 100 sites.
Not all are in the
Susquehanna Drainage.
These are rotated to new
locations every year.
| Continue jurisdictional |  |  | 1.1.2 Estuarine probabilistic monitoring which includes a list of PCB congeners in sediment | [5 empty] | On-going |  |  |  | On-going. Probabilistic study performed each year since 2001 in small tidal tributaries and embayments of the CB. A list of 21 PCB congeners is part of analysis. | Completed and additional activities already planned (i.e., 2020 field season).
monitoring programs for
1.1 | PCB occurrence to assess need for new local TMDLs
and progress related to
reducing PCB loads.
VA DEQ
|  |  |  | 1.1.3 Monitor all main stem tributaries to Bay listed as impaired. Fish PCB monitoring used on an as needed basis to monitor status; | [5 empty] | On-going |  |  |  | On-going. Annual Fish Tissue Monitoring Program | On-going with Activities planned. Fish tissue monitoring for PCBs occurs annually using a rotating basin approach.
|  |  |  | 1.1.4 TMDL source investigation studies included where PCB | [5 empty] | 2020-2022 |  |  |  | On-going; PCB monitoring effort for the non-tidal James River has been completed. | Completed and additional activities to be planned. Monitoring for the non-tidal James River has been completed. Future PCB monitoring will take place within PCB fish consumption impairments that require a TMDL which includes the Rappahannock and York Rivers. Field studies will be planned and implemented for these two Chesapeake Bay tributaries.
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
TMDL being developed. Includes sediment monitoring and low-level water column samples.
|  |  |  | 1.1.5 Conduct a PCB monitoring survey on pre and post-ENR WWTPs in Maryland to determine if there is an increase in removal efficiency from the ENR treatment technology. Conduct a second round of sampling on the two plants that are pre-ENR once the upgrade goes online. |  |  | MDE |  |  | The final round of sampling remains on hold as the Back River and Cox Creek WWTPs ENR treatment processes have not been completed. The contract has been extended through December 2018. |  |  |  | Final round of sampling and analysis has been completed for WWTPs which have upgraded their ENR treatment processes (Back River and Cox Creek). Data has been provided by the lab. Results indicate an increase in removal efficiency for WWTPs that have incorporated ENR treatment processes however sample size is insufficient to demonstrate statistically significant difference between pre and post ENR treatment. Data has been incorporated in TetraTech study. Contract has closed. | Completed and can be removed
|  |  |  | 1.1.6 Continue annual PCB monitoring in support of PCB TMDL development. Monitoring includes collection of water column (non-tidal/tidal), sediment and fish tissue samples for PCB analysis to support the development of water quality models in establishing PCB TMDLs. | [5 empty] | Attempts to collaborate with other jurisdictions unsuccessful. The lower Sus River TMDL will depend on what happens with the Conowingo Dam. (Lower Sus includes all waters below the Conowingo Dam). 2019-- TMDL will be in place for PCBs for both lower Sus and Conowingo pool. Datasets that trigger changes in listings will be shared with the TCW. Have not seen a declining trend in Hg in young of the year but trends in Hg appear to be declining in Potomac main stem in older fish. |  |  |  | PCB monitoring has been completed to support the development of PCB TMDLs to address impairment listings in the Conowingo Pool, Lower Susquehanna River, and non-tidal Potomac PCB TMDL. Additional PCB monitoringin support of PCB TMDL development is not currently planned for the near future. PCB fish tissue analysis continues in support of fish consumption advisories which will also support PCB impairment listing reassessment. | Ongoing with activities planned
1.1.7 Conduct toxic contaminant monitoring for the tidal waters of
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
Aberdeen Proving Grounds (APG).
|  |  |  | 1.1.8 Conduct an analysis of Bay-wide PCB concentration data to improve our understanding of PCB dynamics through-out the Bay mainstem and the influence of loadings from the Susquehanna River and C&D Canal. The project will also focus on approaches for developing a PCB TMDL to address the main stem segment listing in MD's portion of the Bay. |  |  | MDE & VIMS |  |  | The study has been completed and a draft is currently undergoing review. It is anticipated that the report will be available in March 2019 |  |  |  | The study has been completed and remains in draft format with the contract closed. The study was inconclusive in improving our understanding of PCB dynamics within the Chesapeake Bay due to limited availability of observed PCB concentration data within the estuary and major tributaries. The findings of the study will not benefit MDE in the development of PCB TMDLs to address the main stem segment of the Bay. | Completed and can be removed
|  |  |  | 1.1.9 Continue annual PCB fish tissue monitoring for MDE’s Fish Consumption Advisory Program to assign state- wide fish consumption advisories. The program also provides fish tissue data for MDE’s Environmental Assessments and Standards (EASP) and TMDL Programs to support Integrated |  |  | MDE |  |  | Toxics data for fish tissue collected on 2016 is available for early 2018. fish tissue sampling was conducted in 2017 at 25 stations (56 composites) to support the consumption advisory program, IR assessment, and TMDL development needs. Fish composite samples are being analyzed by UMBC and UMCES for PCBs, Hg, and chlordane. It is anticipated that the data results will be available in winter 2018. |  |  |  | Fish tissue sampling was conducted in 2018 (21 stations/79 composites) and 2019 (17 stations/46 composites) to support the consumption advisory program, IR assessment, and TMDL development needs. Fish composite samples are analyzed by UMBC and UMCES for PCBs, Hg, and heptachlor epoxide. Data results are available for the 2018 collection and is anticipated the data results for the 2019 collection will be available winter 2020. | Ongoing with activities planned
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
Report listing assessment and TMDL development.
|  |  |  | 1.1.10 Conduct fish tissue study. |  |  | DOEE (WQD- ESA) |  |  | Fish tissue study was initiated July 2017. Expected completion in July 2018. |  |  |  |  | Completed and additional activities planned - The fish tissue study for 2018 and 19 was summarized in the draft report in April 2020. The report is in internal review before it is finalized and posted on the DOEE web site. In FY 2020, DOEE entered into an MOU with US Fish and Wildlife Service to conduct a fish tissue study. The project is expected to be completed in FY 2021.
|  |  |  | 1.1.11 Complete toxics monitoring on sediments in the Anacostia. | [10 empty] | Remedial Investigation, Feasibility Report and Proposed Plan reports were completed and posted on the DOEE web site on December 27, 2019 for public review and comments. Close to 850 public comments were received on the Proposed Plan and supporting documents. DOEE is addressing these public comments with a plan to produce an Interim Record of Decision (ROD) with a section dedicated to Responsiveness Summary. The interim ROD is scheduled to be posted on the DOEE web site by September 30, 2020
|  |  |  | 1.1.12 Approximately every five years, West Virginia performs a statewide fish tissue assessment to inform both fish consumption advisory and 303(d) listing processes. Mercury and PCBs will be analyzed. |  |  | WV
|  |  |  | 1.1.13 Develop a QAPP to describe objectives, monitoring procedures and laboratory methods to be used to characterize toxics in the Delaware portion of the Chesapeake Bay drainage. |  |  | DE DNREC |  |  | Completd and sumbitted to CBP on July 26, 2017. |  |  |  |  | Completed and can be removed
|  |  |  | 1.1.14 Compile existing toxics data within the Delaware portion of the Chesapeake Bay drainage. | [5 empty] | Completd and sumbitted to CBP on July 26, 2017. |  |  |  |  | Completed and can be removed
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
|  |  |  | 1.1.15 Collect up-to-date | [5 empty] | Fieldwork completed, per the approved QAPP, in Fall 2017 and Fall 2018. |  |  |  |  | Completed with additional activities planned. Results will be incorporated into Summary Report (in preparation). Anticipate completion by the end of 2020.
toxics data on surface
water, surface sediment
and biota within the
Delaware portion of the
Chesapeake Bay
drainage.
|  |  |  | 1.1.16 Collect deep | [5 empty] | Fieldwork completed in Fall 2017. |  |  |  |  | Completed with additional activities planned. Results will be incorporated into Summary Report (in preparation). Anticipate completion by the end of 2020.
sediment cores from a
depositional area in the
tidal Nanticoke River.
Radio-date and analyze
for contaminants to
provide pollution history.
|  |  |  | 1.1.17 Create priority list | [5 empty] | Not Completed |  |  |  |  | Ongoing with activities planned. Results will be incorporated into Summary Report (in preparation). Anticipate completion by the end of 2020.
for sources in need of
clean-up and restoration.
|  |  |  | 1.2.1 Potomac River PCB |  |  | VA DEQ |  |  | On-going. |  |  |  | On-going process | On-going with future activities needed. A timeline to complete PMP implementation for PCBs is not applicable. Several Individual permits and Stormwater Industrial permits have been identified as requiring PMPs and are at different stages of implementation. MS4s have submitted Action Plans.
implementation includes
| Continue local TMDL |  |  | point sources and MS4s.
| implementation utilizing |  |  | Point sources that exceed
| to the extent possible the |  |  | WLAs will submit PMPs.
outputs of this strategy
1.2 | including data |  |  | 1.2.2 Tidal | [5 empty] | On-going |  |  |  | TMDL under development and is scheduled for completion in 2022. | On-going with future activities needed. Additional point source monitoring will occur once the tidal James River PCB TMDL is in place; PMPs will be required at applicable facilities.
| compilations, results of |  |  | James/Elizabeth Rivers –
| enhanced monitoring, |  |  | point sources that have
| guidance documents and |  |  | not screened effluents
| local-level input |  |  | using the low-level
method will be required
to do so. Facilities that
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
|  |  |  | have screened their effluents and exceed their WLA will be required to submit PMPs. | [5 empty] | Stormwater General Permits. Facility effluents with existing loads that exceed WLAs will be asked to develop PMPs.
|  |  |  | 1.2.3 Phase 1 MS4’s which have been assigned a WLA within a PCB TMDL requiring a PCB load reduction are required to develop a PCB Implementation Plan within one year of an approved TMDL. |  |  | MD MS4’s |  |  | Phase 1 MS4 Implementation Plans have been developed by Anne Arundel County for the Baltimore Harbor, Baltimore County for the Bird/Gunpowder River, and Harford County for the Bush River in 2015-2017. Counties that have submitted plans are currently developing monitoring programs to support PCB TMDL implementation. |  |  |  | Phase 1 MS4 Implementation Plans have been developed by Anne Arundel County, Montogomery County, and Howard County for the Patuxent River in 2018. Counties that have submitted plans are currently developing monitoring programs to support PCB TMDL implementation. | Ongoing with activities planned
|  |  |  | 1.2.4 Finalize the District Consolidated TMDL Implementation Plan, and incorporate elements into District’s next MS4 Permit. |  |  | DOEE, DDOT, DGS, and Federal Landholders |  |  | The TMDL IP was finalized in August 2016; 5 year milestones from the IP have been used to inform the performance metrics in each draft of the District's next MS4 permit, which is expected to be finalized in early 2018. |  |  |  |  | Completed and can be removed - DC's new MS4 permit went into effect in June of 2018.
|  |  |  | 1.2.5 Implement stormwater BMPs and green infrastructure to meet TMDL IP’s first set of 5-year milestones. | [5 empty] | Ongoing. DOEE is actively working to compile finalized collection of BMPs. |  |  |  |  | Completed and additional activities to be planned - DOEE is continuously working to implement and document BMPs to meet the required targets of the MS4 permit.
1.3 | Determine consistent implementation measures to use throughout the Bay watershed for tracking |  |  | 1.3.1 Develop maps to track locations where PCB TMDLs are active, under |  |  | CBP GIS team and Bay watershed |  | Entire Watershed | information as of calendar year 2017) |  |  |  | Completed. Outreach to jurisdictional partners was conducted and updates to the previous map have been incorporated (reflects current | Activity completed and requires update for each round of updated integrated assessment reports from the states.
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
| local TMDL development and implementation progress. |  |  | development, and needed. |  |  | jurisdiction GIS leads
|  |  |  | 1.3.2 Assess available information on identified management action implementation and determine next steps (e.g. status of npdes permits with regards to inclusion of PMP; MS4 action plans to ID potential IDDE connections to PMPs) |  |  | TCW and Bay watershed jurisdictions’ TMDL programs | [6 empty] | NPDES Permits and PMPs: Outcome was a memo on incorporating PMP approaches but not numeric effluent limitations. Follow up is needed to examine memo.
1.4 | Determine whether the jurisdictions compile existing PCB outfall monitoring data for NPDES dischargers and assist with development of systems to compile all available information from governmental and academic organizations. This inventory will help determine whether there is a need for additional monitoring requirements to support TMDL |  |  | 1.4.1 Reasonable potential analysis during permit reviews should include PCBs, but is focused on industrial permits. |  |  | PA |  |  | See next blocks. |  |  |  | Unsure if any progress made on ID of potential IDDE connection to PMPs. Will consider inclusion as a separate item for next workplan. | Ongoing with activities planned. There is a reasonable potential analysis done when reviewing permit renewal applications and it is limited to 3 samples collected for the application, typically. We do not have any electronic system to compile PCB results submitted with applications. If reasonable potential to exceed WQS is determined for PCBs, or when other criteria we use for monitoring applies, then we will get DMR data for PCBs electronically.
|  |  |  | 1.4.2 Virginia has an Access Database used to store PCB data obtained from a wide array of matrices (sediment, water, effluent, etc.). The database structure, obtained from DRBC, was designed specific to |  |  | VA |  |  | Ongoing. All PCB data generated using method 1668 are uploaded to the DB |  |  |  | On-going | Ongoing with future activites planned.
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
| development and implementation. |  |  | storing data analyzed and reported using method 1668 including 209 PCB congeners (aka DRBC protocol).
1.6 | Assess the information that is available and forthcoming (e.g., the characterization of Anacostia river sediments by DC Department of Energy and Environment) that describes the most highly contaminated in- stream sediments in the watershed to engage the jurisdictions and federal regulators to explore the feasibility of additional remedial actions such as capping and/or dredging. |  |  | 1.6.1 Develop a final Remedial Investigation Report (RI Report) based on the 700 samples already collected along the 9-mile tidal portion of Anacostia River between FY14 and end of FY15. |  |  | DOEE and federal partners |  |  | DOEE has completed all field activities for the Anacostia River sediment monitoring project. DOEE contractor has submitted a draft RI report to the Agency and is currently under review. Release of the RI report for public comment will be in early 2018. DOEE has held multiple meting engaging the public on the project, and providing updated during 2017. |  |  |  |  | Completed and additional activities to be planned - DOEE released its Phase 1 Remedial Investigation (Phase I RI Report) for public comment on March 2016 and Final Draft Remedial Investigation (RI Report) for comment in March of 2018. Since then, DOEE completed the next "step" in the Anacostia River Sedment Project (ARSP) with the release of the Focused Feasibility Study, "Proposed Plan", and other supporting documents for public comment in December of 2019. The Proposed Plan outlines the the early actions DC will take to remediate contaminant "hotspots" (i.e., early action areas) in the river. The comment period for these latest documents closed on March 2, 2020. DOEE will issue an Interim Record of Decision (Interim ROD) by Sept 30, 2020 that will specify the early actions DOEE will take in remediating (e.g., removing / amending / capping) the early action areas. Once these early actions are completed, additional sampling and analysis, as described in a Performance Monitoring Plan, will determine if the early remedial actions have had their desired effects and if additional steps should be taken to achieve a fishable/swimmable Anacostia River.
|  |  |  | 1.6.2 Study brown bullhead tumors in tidal Potomac River and Anacostia River between 2014-2016, establish trends, if any, and to determine whether or not any established trends are local or regional; ). |  |  | DOEE and FWS |  |  | FWS has completed the brown bullhead catfish study and DOEE is awaiting a draft to the final report for this 3rd round of data collection. |  |  |  |  | Completed and can be removed - FWS has completed the brown bullhead catfish study and DOEE has posted the report on the DOEE web site. The fact sheet can be found here: https://www.chesapeakebay.net/channel_files/27647/bullhead_fact_sheet_2018.pdf
|  |  |  | 1.6.3 Install gauging and sampling stations in NW Branch, NE Branch and Lower Beaver dam Creek. Sampling storms by |  |  | DOEE and USGS |  |  | DOEE in contract with USGS continues to collect water- quality samples for both lowflow and stormflow samples at NE Branch, NW Branch, Beaverdam Creek |  |  |  |  | Ongoing with activities planned - DOEE in contract with USGS has completed collecting water- quality samples for both lowflow and stormflow samples at NE Branch, NW Branch, Beaverdam Creek. USGS produced the Scientific Investigation report to document the study findings. The report can be found both on the DOEE web site as well as USGS using the link here: https://doi.org/10.3133/sir20195092 . A Phase II tributary study is planned to begin in summer 2020.
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
|  |  |  | collecting sediment | [5 empty] | (BDC), Hickey Run, and Watts Branch; and 4 smaller non-
|  |  |  | samples using innovative | [5 empty] | gaged tributaries that flow through Washington, D.C. --
|  |  |  | USGS tested methods to | [5 empty] | Nash Run, Ft. DuPont, Pope’s Branch, and Ft. Stanton;
calculate loads for six
episodes.
|  |  |  | 1.6.4 Collect data to |  |  | DOEE and
|  |  |  | identify sources and |  |  | USGS
characterize
contributions from those
sources, including CSOs,
MS4 outfalls, streams,
and upstream
contributions.
1.7 | The EPA Region 3 SEMD |  |  | 1.7.1 Ongoing tracking in |  |  | EPA SEMD |  |  | FY20/21 |  |  |  | Ongoing. Tracking is ongoing in the CB watershed. SEMD continues to add layers to the GIS desktop tool. | Ongoing with activities planned.
| Site Assessment program |  |  | SEMS of work in Ches.
| will continue to track sites |  |  | Bay Watershed Site
| that are being evaluated |  |  | assessment decision
| in the Chesapeake Bay |  |  | forms have been updated
| Watershed. Additionally, |  |  | to include checkbox on
| a GIS desktop tool has been |  |  | whether site is in Ches.
| developed to assist HSCD |  |  | Bay Watershed, and/or
| in identifying potential |  |  | priority areas (Baltimore
| land sources of |  |  | Harbor, Anacostia,
| contamination in the |  |  | Elizabeth River)
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
| watershed. This project is not limited to PCBs, but any type of contamination that could be migrating from CERCLA sites and affecting the watershed. The GIS tool will help to identify potential CERCLA sites and their proximity to environmentally sensitive areas and receptors to better focus on priority site evaluations. EJ SCREEN has been added as a layer to help identify the location of such sites in areas with diverse populations. |  |  | Site Assessment Mapper (SAM) GIS tool is completed and ready for use – EJScreen is a data layer in SAM |  |  | EPA SEMD
|  |  |  | 1.7.2 Provide information to TCW for potential GIS mapping on CERCLA NPL sites in the watershed that may be undergoing PCB remediation. |  |  | EPA SEMD |  |  | FY21 |  |  |  | Anticipated FY21 | Ongoing with future activities needed.
1.8 | The SEMD Site Assessment Program will conduct work share meetings with our State counterparts once per year to determine who will be the lead agency for further investigation of |  |  | 1.8.1 During yearly workshare meeting, TCW workplan will be a discussion point at the meetings and will use the initiative in the prioritization of sites to be evaluated in the State Cooperative Agreement |  |  | EPA SEMD, State Site Assessment Counterparts |  |  | Ongoing |  |  |  | Ongoing | Ongoing with activities planned
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
| any potential PCBs or mercury sites that are on the active sites list. |  |  | 1.8.2 Also, EPA SEMD and states will determine if sites identified may be better addressed under State VCP or other State programs. |  |  | EPA SEMD, State Site Assessment Counterparts |  |  | Ongoing |  |  |  | Ongoing | Ongoing with activities planned.
1.9 | If there are potential land sources that other programs have found, HSCD may be able to investigate those potential sources through coordination with the appropriate authority. |  |  | 1.9.1 Obtain information on PCB or mercury hotspot areas within the watershed and try to correlate CERCLA sites or other sites. |  |  | EPA SEMD, TCW, TSCA |  |  | Ongoing |  |  |  | Coordination with other programs is not occurring | Ongoing with future activities needed. SEMD to reach out to other groups to gather additional PCB/mercury data and map in conjunction with known CERCLA sites.
|  |  |  | 1.9.2 Discuss potential PCB sources with TCW and TSCA | [9 empty] | Coordination with other programs is not occurring | Ongoing with future activities needed. SEMD to reach out to other groups to determine if there are land sources to be investigated.
|  |  |  | 1.9.3 Use information and data generated from other programs to pre-screen and prioritize sites to determine whether further assessment is needed under Superfund. |  |  | EPA SEMD | [6 empty] | Minimal progress until sites are identified. | Ongoing with future activities needed. Once sites are identified, SEMD can screen and prioritize.
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
1.1 | The EPA R3 NPDES Permits Branch will continue to address PCBs through the CWA framework. Where waters have been identified as impaired and a local TMDL has been established creating WLA for point sources, the NPDES Permitting program will ensure that permits are consistent with the TMDL. The NPDES Permitting Program will draft and review permits with a |  |  | 1.10.1 The NPDES Permitting Program will draft permits with a focus on ensuring that PCB WLAs are clear and enforceable and consistent with the TMDL. |  |  | EPA R3 NPDES Permits Branch |  |  | Ongoing
|  |  |  | 1.10.2 The NPDES Permitting Program will review permits developed by the jurisdictions with a focus on ensuring that PCB WLAs are clear and enforceable and consistent with the TMDL. | [5 empty] | Ongoing
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
| focus on ensuring that |  |  | 1.10.3 The NPDES | [5 empty] | Ongoing
| PCB WLAs are clear and |  |  | Enforcement Program,
| enforceable. The NPDES |  |  | through state oversight
| Enforcement Program, |  |  | and its independent
| through state oversight |  |  | compliance monitoring
| and its independent |  |  | and enforcement
| compliance monitoring |  |  | authorities, will ensure
| and enforcement |  |  | that permit requirements
| authorities, will ensure |  |  | are met. If a permittee is
| that permit requirements |  |  | in non-compliance with
| are met. If a permittee is |  |  | its compliance
| in non-compliance with |  |  | obligations, EPA will take
| its compliance |  |  | timely and appropriate
| obligations, EPA will take |  |  | action, including
| timely and appropriate |  |  | exercising its
| action, including |  |  | enforcement authority, to
| exercising its |  |  | ensure that the permittee
| enforcement authority, to |  |  | returns to compliance in
| ensure that the permittee |  |  | an expeditious manner.
returns to compliance in
an expeditious manner.
1.11 | The EPA R3 Land and |  |  | 1.11.1 In 2016 and 2017, |  |  | EPA Region 3 |  |  | There were 2 inspections at Aberdeen and Delmarva
| Chemicals (LCD) Toxics |  |  | the EPA R3 LCD Toxics |  |  | Land and |  |  | stations in 2016-2017, and more planned for 2018
| Program Branch will |  |  | Program will perform |  |  | Chemicals
| continue to ensure |  |  | inspections at facilities |  |  | Devision
| compliance with PCB |  |  | within the R3 states
| TSCA regulations through |  |  | based on potential for
| its PCB inspection and |  |  | PCB releases, cumulative
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
| enforcement program. |  |  | burden on EJ
| Inspections will be |  |  | communities, or
| targeted based on |  |  | permitting. The R3 Toxics
| potential for releases, |  |  | Program Branch will also
| cumulative burden on EJ |  |  | responds to on
| communities, or |  |  | tips/complaints that
| permitting. The R3 Toxics |  |  | involve potential for
| Program Branch will also |  |  | illegal disposal and
| responds to on |  |  | significant risk.
tips/complaints that
involve potential for
illegal disposal and
significant risk.
1.12 | The EPA R3 LCD Office of |  |  | 1.12.1 Overall |  |  | Lockheed |  |  | Upal Ghosh and UMBC researchers were involved in carbon
| Materials Management |  |  | performance target is |  |  | Martin; MDE; |  |  | amendment work for use in remediation activities. Tech
| will continue to partner |  |  | completion of remedial |  |  | will require |  |  | decisions for remediation may be useful as case studies to
| with the Maryland |  |  | actions specified in the |  |  | EPA approval |  |  | inform other remediation activities (e.g. Anacostia)
| Department of |  |  | Feasibility Study |  |  | of a Risk
| Environment to oversee |  |  | approved by MDE and |  |  | Based
| the PCB clean up at the |  |  | EPA Region III. |  |  | Disposal
| Lockheed Martin plant |  |  | Incremental steps include |  |  | Approval
| located in Middle River, |  |  | permit applications, |  |  | Application
| Maryland. The Middle |  |  | approvals, mobilization, |  |  | (RBDAA)
| River facility, which is |  |  | sediment removal,
| located on Cowpen Creek, |  |  | confirmatory sampling, in
| is considered to be a |  |  | situ treatment
| major contributor to PCBs |  |  | amendment application,
post-closure
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
| in the Bay. Phase 2 of the clean-up is commencing. |  |  | bioaccumulation monitoring, and a 5-year review submittal
1.13 | The Chesapeake Bay |  |  | 1.13.1 CBC will, in turn, |  |  | CBC
| Commission will work |  |  | pursue action within our
| collaboratively with the |  |  | member state General
| Bay Program partners to |  |  | Assemblies and the
| identify legislative, |  |  | United States Congress.
| budgetary and policy |  |  | See CBC Resolution #14-1
| needs to advance the |  |  | for additional information
| goals of the Chesapeake |  |  | on the CBC’s participation
| Watershed Agreement. |  |  | in the management
strategies.
Management Approach 2: Education and Awareness | [13 empty] | Management Approach 2: Education and Awareness
2.1 | Develop PMP guidance |  |  | 2.1.1 Contingent upon |  |  | VA DEQ (The |  |  | 2021 |  |  |  | On-going. Importance of document is recognized within DEQ as it has become a component of the Agency's Strategic Plan. | On-going with future activities needed. A guidance document is being developed in collaboration with VA DEQ's NPDES Water Permit Program.
| document for the control |  |  | completion of VA DEQ’s |  |  | document
| and reduction of PCBs in |  |  | work to evaluate and |  |  | will be
| NPDES regulated |  |  | assess cross-jurisdiction |  |  | Virginia
| stormwater and |  |  | applicability |  |  | Specific, but
| wastewater including an | [5 empty] | can serve as a
| inventory of stormwater | [5 empty] | prototype for
| BMP options. This | [5 empty] | a larger
| document would provide | [5 empty] | effort)
guidance to all Bay
jurisdictions in
implementing PCB load
reductions established for
dischargers through local
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
TMDL development while recognizing the need for flexibility in PMP design. Develop guidance for unregulated sources of PCBs for use in developing implementation plans under TMDLs.
2.2 | Working with local government and non- profit organizations, the TCW will inform the public regarding risks from consuming contaminated fish by developing communications materials and corresponding procedures for their dissemination throughout the targeted communities. |  |  | 2.2.1 Secure GIT Project funding. |  |  | Diversity Action Team |  |  | GIT Project funding was awarded in early 2016 Release of first phase (poster/infographic) expected early 2018
|  |  |  | 2.2.2 Inventory existing approaches to issuing fish consumption advisories and study effectiveness of and compliance with those advisories in order to develop enhanced tools |  |  | Project award recipient in coordination with DAT and TCW |  |  | Included in final report
|  |  |  | 2.2.3 Test the new tools and work on optimization |  |  | Project award recipient in coordination with DAT and TCW |  |  | Completed through on-site testing at Annacostia River festivals
|  |  |  | 2.2.4 Implement and disseminate new tools in order to explore the |  |  | Bay Program partners |  |  | Final product including Users' Guide will be released Summer 2020 |  |  |  |  | Completed. No specific follow-up planned after roll-out; however, TCW should consider follow-on activities.
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
extent to which diverse populations are located in areas where fish advisories are being issued, using EPA’s EJSCREEN tool.
2.3 | Compile education materials regarding existing procedures and best practices for containment and prevention of release of PCBs. |  |  | 2.3.1 Identify potential resources |  |  | TCW | [6 empty] | No progress | Remove
|  |  |  | 2.3.2 Compile education materials | [9 empty] | No progress | Remove
Management Approach 3: Voluntary Programs | [13 empty] | Management Approach 3: Voluntary Programs
3.1 | Coordinate a voluntary action program to reduce transformers and other PCB containing equipment (e.g., fluorescent light ballasts). Include those classified as PCB free (less than 50 ppm) Provide to program participants information on remediating PCB contamination on-site from historical releases of |  |  | 3.1.1 Identify a project lead |  |  | TCW | [7 empty] | GIT Funding project completed.
|  |  |  | 3.1.2 Estimate location and volume of PCB- containing equipment |  |  | Contingent upon available resources | [7 empty] | GIT Funding project completed.
|  |  |  | 3.1.3 Estimate costs of replacing PCB-containing equipment | [10 empty] | GIT Funding project completed.
|  |  |  | 3.1.4 Identify potential incentives and present summary of cost information to land owners | [10 empty] | GIT Funding project completed. removal of PCB light ballasts in schools
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
| these transformers and |  |  | 3.1.5 Obtain commitment | [10 empty] | GIT Funding project completed. TCW should consider follow-on activities including possible joint effort with sustainable schools outcome on voluntary removal of PCB light ballasts
| use EPA’s EJ SCREEN tool |  |  | from land owners to
| to help identify where |  |  | voluntarily replace PCB
| such equipment is located |  |  | containing equipment
| in areas with diverse |  |  | with consideration to
| populations. |  |  | include activities in areas
with diverse populations
Management Approach 4: Science | [13 empty] | Management Approach 4: Science
4.1 | Refine and improve |  |  | 4.1.1 Complete |  |  | TCW |  |  | Further work on trackdown study ongoing. Possibility of a |  |  |  | Ongoing, importance of trackdown highlighted in STAC workshop report, USGS supported lessons learned document | Incomplete, more work needed
| understanding of PCB |  |  | information gathering | [5 empty] | PCB consortium on trackdown and resources in fall 2018 in
| sources to inform the |  |  | and develop a guidance | [5 empty] | coordination with Baltimore Urban Waters Partnership
| Conceptual Model of PCB |  |  | document on best
| fate in the environment |  |  | practices for effective
implementation of PCB
track down studies in the
TMDL context
|  |  |  | 4.1.2 Communicate |  |  | UMBC USGS |  |  | 2018 briefing of completed WWTP study, ongoing study will |  |  |  | Ongoing, briefing anticipated FY21 | Incomplete, more work needed, POC Emily Majcher
|  |  |  | results of completed | [5 empty] | be briefed once complete 2020
research study
investigating the PCB
content of wastewater
biosolids and effluent in
an urban WWTP.
Ongoing studies of fat-oil-
and-grease (FOG)
deposits as potential
source of PCBs in aging
gray infrastructure.
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
4.2 | Inform status and changes |  |  | 4.2.1 Identify barriers and | [9 empty] | Unknown
| in environmental |  |  | opportunities related to
| conditions through the |  |  | more frequent use of EPA
| use of the 1668 congener- |  |  | 1668 for contaminated
| based analytical method, |  |  | sites, wastewater and
| communicate lessons |  |  | regulated and
| learned from innovative |  |  | unregulated stormwater
| monitoring devices, and |  |  | dischargers as a screening
| assess changes over time |  |  | tool (as is underway in
| through the TMDL |  |  | VA) or for a targeted
| implementation plan |  |  | subset of permittees.
| progress |  |  | 4.2.2 Encourage use of | [9 empty] | Unknown
the high-sensitivity
congener-based methods
to analyze PCBs to ensure
that PCB sources are
being characterized
accurately when such
characterization can help
with source identification
|  |  |  | 4.2.3 Communicate |  |  | USGS |  |  | 2018 |  |  |  | Ongoing. Presentations from BUWP conferences included online for jurisdictions to access. Lessons learned document to be completed in 2021 | incomplete, more work needed
innovative monitoring
tools for PCB sampling
(such as high-volume
suspended sediment,
diffusion samplers, and
mussels as an indicator of
bioaccumumation) as
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
part of synthesis report of PCB TMDL workshop
|  |  |  | 4.2.4 Inventory and |  |  | TCW; BUWP, |  |  | 2018 |  |  |  | Ongoing, monitoring progress slower than originally anticipated so reporting of this progress has not been done yet. | Incomplete, needs more work
|  |  |  | update TMDL |  |  | USGS
implementation plans
and monitoring progress,
(methods used) as part of
collaborative Confluence
site
4.3 | BMP Effectiveness for |  |  | 4.3.1 Communicate |  |  | Chesapeake | [6 empty] | Completed, briefed, and included in STAC workshop materials
| removal of Toxic |  |  | results of project that |  |  | Stormwater
| Contaminants |  |  | investigated amount of |  |  | Network and
|  |  |  | PCB reduction across |  |  | TCW
range of BMPs, and their
association with land use
and industrial sources
|  |  |  | 4.3.2 Explore feasibility of |  |  | EPA |  |  | 2018-2019
including qualitative
scoring tools into BMP
implementation scenarios
in Phase 6 CAST
|  |  |  | 4.3.3 Collaborate with |  |  | TCW |  |  | 2018-2019 |  |  |  | Ongoing, briefings to WQGIT, Ag workgroup, stormwater workgroup | Continue to look for ways to cooperate of efforts to explore co-benefit reduction nutrients, sediment and toxic contaminants
other source sector
groups to identify
projects and topics for co-
benefit reduction of PCBs
with nutrients and
sediment reductions.
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
|  |  |  | 4.3.4 Investigate the impact of Stormwater Best Management Practices (BMPs) on PCB loadings to waterways). |  |  | MDE |  |  | 2018-2019 |  |  |  | MDE plans to collect sediment samples from 70 wet ponds for PCB analysis to compare concentrations from BMPs within drainage areas of different land use (residential, commercial, industrial) and PCB era (pre 1980) or non-PCB era development (post 1980). Sampling design and site selection has been completed. Sampling will be scheduled upon return to normal operations at MDE and contract lab. The findings of the study will inform Phase I MS4s in stormwater management decisions to address PCB implementation. | Ongoing with activities planned
|  |  |  | 4.3.5 Communicate ongoing results of the investigations of PCB reduction in biofiltration and enhanced of media in stormwater controls to promote removal of PCBs; include summary in synthesis report of PCB TMDL workshop |  |  | UMCP, UMBC, USGS | [6 empty] | Summarized current status of projects at STAC workshop, in STAC report, and briefed to workgroups. Projects are ongoing and will continue to be briefed when appropriate. | incomplete, needs more work
|  |  |  | 4.3.6 Estimate data needs to include toxic contaminant reduction associated with the implementation of BMPs for sediment and nutrient reduction under the Chesapeake Bay TMDL (e.g., assessment of data needs for CAST) |  |  | TCW |  |  | 2018-2019 |  |  |  | Preliminary meetings held between CBP and workgroup leadership. Determination at that not sufficient data to date. Tabled currently. | incomplete needs more work
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
Management Approach 5: PCB Consortium | [13 empty] | Management Approach 5: PCB Consortium
5.1 | Explore the value and feasibility of creating and sustaining a broader scale forum for collaboration (e.g. a consortium) on PCB TMDLs that are in place and under development across the watershed |  |  | 5.1.1 Form an exploratory team Collect information about the role for a consortium and expected assistance to be provided to TMDL implementers. Estimate the cost of a consortium Evaluate other models (e.g. Chesapeake Conservancy) for methods of funding one or more part-time or full- time positions to manage the operations of the consortium. Prepare a report with jurisdiction input (after WIP III draft in April 2019) that summarizes options, costs and means of sustaining a collaborative forum. |  |  | TCW |  |  | December 2019
5.2 | Present the findings from 5.1 above to the CBP Management Board for a |  |  | 5.2.1 Deliver a presentation of findings and determine next |  |  | TCW |  |  | March 2020
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles Red - action has not been taken or has encountered a serious barrier | [13 empty] | JURISDICTIONS
Action # | Description |  |  | Performance Target(s) |  |  | Responsible Party (or Parties) |  | Geographic Location | Expected Timeline |  |  |  | Current Status (green = adequate progress, yellow = minimal progress, red = inadequate progress) | Select one of the following and provide an explanation: completed and can be removed, completed and additional activities to be planned / already planned, ongoing with activities planned, ongoing with future activities needed, or inadequate progress and revise planned activities / consider removing
| partnership decision on whether to invest in a new collaboration forum or other new approaches to foster collaboration |  |  | steps, if any, from consensus-based decisions by the CBP as to forming a consortium or other actions.
Definitions:
EPA | [5 empty] | U.S. Environmental Protection Agency
DE DNREC | [5 empty] | Delaware Department of Natural Resources and Environmental Control
DOEE | [5 empty] | District of Columbia Department of Energy and Environment
MDE | [5 empty] | Maryland Department of the Environment
MD DNR | [5 empty] | Maryland Department of Natural Resources
NYS DEC | [5 empty] | New York State Department of Environmental Control
PA DEP | [5 empty] | Pennsylvania Department of Environmental Protection
VA DEQ | [5 empty] | Virginia Department of Environmental Quality
WV DEP | [5 empty] | West Virginia Department of Environmental Protection
USGS | [5 empty] | U.S. Geological Survey
FWS | [5 empty] | U.S. Fish and Wildlife Service
UMCES | [5 empty] | University of Maryland Center for Environmental Science
UMBC | [5 empty] | University of Maryland Baltimore County
NOAA | [5 empty] | National Oceanic and Atmospheric Administration
USDA | [5 empty] | U.S. Department of Agriculture
NRCS | [5 empty] | National Resource Conservation Service
DoD | [5 empty] | U.S. Department of Defense
USACE | [5 empty] | U.S. Army Corps of Engineers
DOT | [5 empty] | Department of Transportation
SRBC | [5 empty] | Susquehanna River Basin Commission
CBP | [5 empty] | Chesapeake Bay Program Partnership
CBPO | [5 empty] | Chesapeake Bay Program Office
WQGIT | [5 empty] | Water Quality Goal Implementation Team
STAC | [5 empty] | Scientific and Technical Advisory Committee
MB | [5 empty] | Chesapeake Bay Program's Management Board
PSC | [5 empty] | Chesapeake Bay Program's Principles' Staff Committee
WIP | [5 empty] | Watershed Implementation Plan
TMDL | [5 empty] | Total Maximum Daily Load
DAT | [5 empty] | Chesapeake Bay Program Diversity Action Team
HSCD | [5 empty] | EPA Hazardous Site Cleanup Division
TSCA | [5 empty] | Toxic Substance Control Act
PMP | [5 empty] | Pollution Minimization Plan
ASTSWMO | [5 empty] | Association of State and Territorial Solid Waste Management Officials
CSN | [5 empty] | Chesapeake Stormwater Network