## Sheet1
WORK PLAN ACTIONS
Green - action has been completed or is moving forward as planned Yellow - action has encountered minor obstacles
Red - action has not been taken or has encountered a serious barrier
Action # | Description | Performance Target(s) | Responsible Party(s) | Geographic Location | Status (Nov. 2018) | Completion Date
Management Approach 1: Monitor the rate of conversion of forests, wetlands, and farmland, (and the rate of impervious surface change).
1.1 | Design and implement a manual, stratified sampling approach at the county level and assess land cover change from high resolution imagery circa 2009-2013. | Aquire NAIP imagery for 2009, 2013 | USGS, CBPO GIS Team | Prince George's County, MD | Complete | Spring 2018
|  | Design sampling framework | USGS, CBPO GIS Team | Watershed counties | Initiated | Summer 2019
|  | Classify samples using Land Image Analyst or other software | CBPO Staffers/ Interns | Prince George's County, MD | Not started | Summer 2019
1.2 | Assess land use change throughout the Bay Watershed and region from 1985-2015 using the CBP 2013 high-res land use coupled with the Land Change Analysis and Monitoring Program Database and National Land Cover Database. Compare with assessed change in the mid-Atlantic states from 1984 – 2015 based on the National Resources Inventory. | Work with CBP GIS Team to assign and completed task | USGS, CBPO GIS Team | Watershed counties | Initiated | Summer 2019
1.3 | Assess difference in high resolution land cover maps at the County level. | Quantify change between two independently classified high-res land cover datasets. | CBP Staffers/ Interns | Prince George's County, MD | Initiated | Summer 2019
|  | Compare with results from 1.1. | USGS, CBPO GIS Team |  | Not started
1.4 | Investigate options for monitoring "hot spots" of land change every two years | Review literature of the science and technologies associated with remote sensing and image interpretation as well as consultation with remote sensing professionals | Chesapeake Conservancy | Watershed counties | Initiatated | Fall 2019
|  | Provide recommendations on the most effective and efficient approach |  |  | Initiated
1.5 | Monitor "hot spots" of change | Assess "hot spots" of change from 2013/14 - 2017/18 - 2019/20 - 2021/22 | Chesapeake Conservancy | Watershed counties | Not started | Summer 2019, Summer 2021, and Summer 2023
1.6 | Map and ReMap High-res land cover/use: 2013/14; 2017/18; 2021/22 | Using the best available methods, map high-res land cover/use wall-to-wall every four years, remapping previous years in the process. | Chesapeake Conservancy, University of Vermont | Watershed counties | Initiated | Summer 2020, Summer 2023
Management Approach 2: Quantify the impacts of land conversion on water quality, healthy watersheds, and communities.
2.1 | Quantify impact of land conversion on water quality (explaining changes in nutrient and sediment that relate to monitored and modeled land conversion) | Assess the impact of future 2025 land use scenarios (Land Policy BMPs) on nutrient and sediment pollutant loads | USGS, CBPO GIS Team | Watershed counties | Complete | Fall 2018
|  | Assess the impact of future 2050 land use scenarios on nutrient and sediment loads | USGS, CBPO GIS Team | Watershed counties | Initiated | Summer 2019
2.2 | Quantify impact of land conversion on healthy watersheds and wildlife habitats | Identify specific components of "health" and "habitat" to be evaluated and collect data, 1985- 2015 | CBP Habitat and Healthy Watersheds GITs | State-identified healthy watersheds and habitats of interest | Not started | Spring 2020
|  | Analyze observed changes in land cover/use relative to changes health and habitat metrics (1985 - 2015) | USGS, CBPO GIS Team | State-identified healthy watersheds and habitats of interest | Not started | Fall 2020
|  | Forecast changes in land cover/use through 2050 and relate to potential changes in health and habitat metrics | USGS, CBPO GIS Team | State-identified healthy watersheds and habitats of interest | Not started | Spring 2021
2.3 | Quantify impact of land conversion on communities | Identify specific components of "communities" to be evaluated. | LGAC, LGEI, LUWG, CCP | Watershed counties | Not started | Spring 2020
|  | Conduct literature review on the relationsihp between land change and community components. | TBD? | National | Not started | Fall 2020
|  | Forecast changes in land cover/use through 2050 and relate to potential changes in communities | USGS, CBPO GIS Team | Watershed counties | Not started | Spring 2021
Management Approach 3: Communicate the results to the public, elected officials, and to the Bay Program.
3.1 | Link the results of the Land Use Methods and Metrics Outcome Land Use Options Evaluation Workplan | Participate in the development of a Local Engagement Strategy that will integrate and disseminate results of land use methods and metrics outcome and and land use options evaluation outcomes | LGAC and CBP Local Leadership Workgroup | Watershed counties | Not started | Spring 2021
3.2 | Chesapeake Bay Land Change website | Launch Phase 6 land use data website | USGS, CBPO Web Team | Watershed counties | Complete | Summer 2017
Testing, refinement, expansion
|  | Develop land change forecasts | USGS, LUWG